## Title Page
<Customer Logo>
Customer Name | Washington State University
Deployment Phase | Phase 1 - Deployment
Customer Project Manager
Engagement Manager
Principal Consultant(s)
Integration Consultant(s) | Kristen Flannery
Delivery Assurance Rep(s)
Go-Live Checklist Sign-off Date
Go-Live Date | 2020-12-16
Production Cutover Period (Start Date thru End Date) - Includes Pre-Cutover, Cutover, and Post Cutover Periods | Pre-Cutover Start Date: DD/MM/YYYY End Date: 11/20/2020 Cutover Start Date: 11/20/2020 End Date: 12/16/2020 Post Cutover Start Date: 12/17/2020 End Date: 01/31/2021
Workday Applications Going Live | HCM, ESS, MSS, Talent Management, Compensation, US Payroll, Benefits, Financials
Integrations Going Live
Number of Active Employees Going Live
Number of Countries Going Live | 1
Cutover Checklist

## WSU Cutover Activities
Task | Section | Grouping | Function | Workstream | Target System | Open Questions | Task Description | Start Date | Start Time | End Date | Assigned to (Name(s)) | Status | Area Order | Task Order | Implementation Area | Dependencies | Final Comments / Notes
MPP | 1. Preparation for Cutover | Cutover Team |  |  |  |  | Review & refine cutover plan with workstream leads for input | 2020-05-18 |  | 2020-09-10 | Brant Schroeder, Jane Thomas | Complete
| 1. Preparation for Cutover | DA Review | Payroll | Payroll | WSU6 |  | DA Payroll Review | 2020-07-13 |  | 2020-07-14 | Mel Roberts | Complete
MPP | 1. Preparation for Cutover | Cutover Team |  |  |  |  | Define monitoring, reporting, and logistics (including Zoom) | 2020-07-13 |  | 2020-07-31 | Brant Schroeder, Jane Thomas | In Progress
MPP | 1. Preparation for Cutover | Cutover Team | TECH |  |  |  | Ensure Contingency Plan (i.e. Rollback) plan is established | 2020-07-13 |  | 2020-09-18 | Brant Schroeder, Jane Thomas | In Progress
MPP | 1. Preparation for Cutover | Cutover Team |  |  |  |  | Update / Incorporate Feedback Cutover Plan | 2020-07-13 |  | 2020-09-30 | Brant Schroeder, Jane Thomas | In Progress
| 1. Preparation for Cutover |  | TECH | Conversion | Legacy |  | Determine what are the high-frequency activities performed by the Records group that occur in November/December | 2020-07-14 |  | 2020-07-16 | Jim Lowery/Jay Maylor | Complete
| 1. Preparation for Cutover |  | Payroll | Payroll |  |  | Payroll Compare - CompareEdge (June 1 - June 15) | 2020-07-15 |  | 2020-08-07 | Brigham Hubbard/Mel Roberts | Complete |  |  |  |  | Payroll Compare June 1st half
| 1. Preparation for Cutover | Cutover Team | Integrations |  |  |  | Gather list of WSU integrations | 2020-07-17 |  | 2020-07-31 | Maria Gutierrez / Kristen Flannery | Complete
| 1. Preparation for Cutover | Cutover Team |  |  |  |  | Review & refine cutover plan with Deloitte, WSU leads, Central offices - Modernization team input | 2020-07-24 |  | 2020-08-11 | Brant Schroeder, Jane Thomas | Complete
MPP | 1. Preparation for Cutover | Cutover Team |  |  |  |  | Gather list of Deloitte/WSU Contact information | 2020-07-27 |  | 2020-07-31 | Aditi Gopalan | Complete
MPP | 1. Preparation for Cutover |  | FIN | Core Finance |  |  | Create Plan for Using Default values in Gold Build | 2020-07-31 |  | 2020-08-31 | Brant Schroeder, Gerik Kimble,Jennifer Klein,Joy Morton, kyle Babinski, Ed Nieskes | In Progress
MPP | 1. Preparation for Cutover | Cutover Team |  |  |  |  | Confirm availability of cutover task owners | 2020-08-03 |  | 2020-08-21 | Brant Schroeder, Jane Thomas | In Progress
MPP | 1. Preparation for Cutover | Cutover Team |  |  |  |  | Confirm Contact information & Resource Escalation during Cutover timeframe | 2020-08-03 |  | 2020-08-21 | Brant Schroeder, Jane Thomas | In Progress
MPP | 1. Preparation for Cutover | Cutover Team | PMO |  |  |  | Present WSU Cutover Plan w/ options for virtual go-live | 2020-08-11 |  | 2020-08-11 | Brant Schroeder, Jane Thomas | Complete
MPP | 1. Preparation for Cutover |  | PMO |  |  |  | Conduct Readiness Assessment 3 against Checklist | 2020-08-14 |  | 2020-08-24 | David Boeker, Jennifer Klein, Joy Morton, Mike Corwin (Brant, Jane) | In Progress
MPP | 1. Preparation for Cutover | Cutover Team | TECH |  |  |  | Schedule Table Read of Cutover Plan - Conversions/Integrations | 2020-08-31 |  | 2020-09-11 | Brant Schroeder, Jane Thomas | Complete
MPP | 1. Preparation for Cutover | Cutover Team | FIN |  |  |  | Schedule Table Read of Cutover Plan - Modernization/Central Offices/Technical | 2020-08-31 |  | 2020-09-11 | Brant Schroeder, Jane Thomas | Complete
MPP | 1. Preparation for Cutover | Cutover Team | HCM |  |  |  | Schedule Table Read of Cutover Plan - Modernization/Central Offices/Technical | 2020-08-31 |  | 2020-09-11 | Brant Schroeder, Jane Thomas | Complete
MPP | 1. Preparation for Cutover | Cutover Team | PMO |  |  |  | Decide onsite/virtual approach for Cutover - Virtual decision was reached | 2020-09-01 |  | 2020-09-01 | Jennifer Klein, Joy Morton, Mike Corwin, Matt Skinner | Complete
| 1. Preparation for Cutover |  | Payroll | Conversion |  |  | Load HCM/Payroll Catch-Up data for June 16 - Jun 30 payroll (07/06 snapshot) | 2020-09-01 |  | 2020-09-04 | Brant Schroeder, Jane Thomas | Complete |  |  |  |  | Payroll Compare June 2nd half
| 1. Preparation for Cutover |  | HCM | Recruiting |  |  | Create process to document for HRS creating positions in Workday (for AP and CS) from OPDRS data | 2020-09-01 |  | 2020-11-30 | Bonnie Dennler
| 1. Preparation for Cutover |  | HCM | Recruiting |  |  | Update HRS Recruitment Toolkit | 2020-09-01 |  | 2020-11-30 | Sabrina McPherson, Jon Hurd, Lindsey Evensen, Teddi Phares
| 1. Preparation for Cutover |  | HCM | Recruiting |  |  | Update website templates (i.e. offer letters). | 2020-09-01 |  | 2020-11-30 | Sabrina McPherson, Jon Hurd, Lindsey Evensen
MPP | 1. Preparation for Cutover |  | PMO |  |  |  | Conduct Readiness Assessment 4 against Checklist | 2020-09-15 |  | 2020-09-28 | David Boeker, Jennifer Klein, Joy Morton, Mike Corwin | In Progress
| 1. Preparation for Cutover |  | Payroll | Payroll |  |  | Payroll Compare - CompareEdge (June 16 - June 30) | 2020-09-23 |  | 2020-10-16 | Brigham Hubbard/Mel Roberts | In Progress |  |  |  |  | Payroll Compare June 2nd half
| 1. Preparation for Cutover | Critical Date | Operating Committee |  |  |  | Hard Freeze on Change Requests | 2020-09-25 |  | 2020-09-25 | David Boeker, Jennifer Klein, Joy Morton, Mike Corwin | [5 empty] | Date set to align with UAT scenerio execution completion and end date for Critical/High Defect Resolution
| 1. Preparation for Cutover | Soft Freeze/Hard Freeze | FIN | General Accounting | Legacy |  | Open/Close Cost Centers, Projects, Programs, Departments | 2020-10-01 |  | 2020-10-01 | Gerik Kimble, Chris Conway
| 1. Preparation for Cutover | Communication | HCM | Recruiting | Legacy |  | Post transition announcement to candidates on external WSUJobs site. Incl. internal worker messaging. | 2020-10-01 |  | 2020-10-01 | Sabrina McPherson, Jon Hurd
| 1. Preparation for Cutover | Communication | HCM | Recruiting | Legacy |  | Post transition announcement to OPDRS users on internal OPDRS site. | 2020-10-01 |  | 2020-10-01 | Sabrina McPherson, Jon Hurd
| 1. Preparation for Cutover | Communication | PMO |  |  |  | Send email communications of cutover plan to department, hiring managers, and administrators. | 2020-10-01 |  | 2020-10-15 | HRS/Annie Riedinger/Emily Bailes
| 1. Preparation for Cutover | Communication | HCM | Time/Absence | Legacy |  | Any comp time earned needs to be used by 12/31/2020. Comp must be cashed out By Dec 11. | 2020-10-01 |  | 2020-10-15 | Annie Riedinger, Emily Bailes | [5 empty] | BH: Kendra talking with BU reps to finalize plan. When departments would have to communicate that they want to pay out comp time
| 1. Preparation for Cutover | Communication | HCM | Time/Absence |  |  | Communicate university of time balance & time off collection & work schedule collection | 2020-10-01 |  | 2020-10-15 | Annie Riedinger/Emily Bailes/Emily Goodwin/Dora Tilles
| 1. Preparation for Cutover | Communication |  |  |  |  | Communication reminders for Workday launch (go-live) to Executives, Leaders and Employees | 2020-10-01 |  | 2020-11-02 | Annie Riedinger/Emily Bailes
| 1. Preparation for Cutover | Communication | PMO |  |  |  | Draft communication Workday launch (go-live) to Executives, Leaders and Employees | 2020-10-01 |  | 2020-11-02 | Annie Riedinger/Emily Bailes
| 1. Preparation for Cutover | Pre-Freeze | FIN | Business Assets | Legacy |  | Cutoff for preassigned inventory tag numbers - the issuance of pre-assigned inventory tags will stop | 2020-10-01 |  | 2020-11-19 | George Rhodes/Clint McGregor | [5 empty] | CPM: Preliminary estimated date
| 1. Preparation for Cutover | Communication | FIN |  |  |  | Announce cutover plan to department administrators at FA&O meeting. | 2020-10-05 |  | 2020-10-05 | Joy Morton, Gerik Kimble
MPP | 1. Preparation for Cutover | Cutover Team | HCM/Payroll/Finance |  |  |  | Final Table Read of Cutover Plan - Leads from WSU/Deloitte/Technical | 2020-10-05 |  | 2020-10-16 | Brant Schroeder, Jane Thomas
MPP | 1. Preparation for Cutover | Critical Date | Operating Committee |  |  |  | Finalize WSU Cutover Plan | 2020-10-05 |  | 2020-10-16 | Jay Dumphy, Jennifer Klein, Joy Morton, Mike Corwin, Matt Skinner
| 1. Preparation for Cutover | Communication | Payroll | Payroll |  |  | Communicate Payroll Freeze Dates | 2020-11-20 |  | 2020-12-04 | Annie Riedinger/Emily Bailes
| 1. Preparation for Cutover | Communication | Operating Committee |  |  |  | Communicate soft freeze of FIN transactions for dates 11/20/2020 and hard freeze of 12/23/2020 | TBD |  | TBD | Jennifer Klein, Joy Morton, Mike Corwin, Matt Skinner
| 1. Preparation for Cutover | Communication | Operating Committee |  |  |  | Communicate soft freeze of HR/Payroll transactions for dates 11/20/2020 and hard freeze of 12/04/2020 into TEMPS/PERMS. If hire date is on/after 12/16, input into WD not TEMPS/PERMS. | TBD |  | TBD | Jennifer Klein, Joy Morton, Mike Corwin, Matt Skinner
| 1. Preparation for Cutover | Communication | OCM |  |  |  | Launch Guides for Managers and Employees developed |  |  |  | Annie Riedinger, Emily Bailes
| 2. Pre-Cutover |  | HCM | Recruiting |  |  | Determine what OPDRS security changes are needed post January 2021 (i.e. remove create new posting button to prevent new postings from being submitted). | 2020-09-01 |  | 2020-10-31 | Sabrina McPherson, Jon Hurd, PeopleAdmin
| 2. Pre-Cutover |  | HCM/Payroll | Supervisory Org |  |  | Default Cost Center, Fund, Function, Region for Supervisory Org Restrictions | 2020-09-01 |  | 2020-11-01 | Brigham/Wendy | In Progress
| 2. Pre-Cutover | Communication | HCM | Benefits |  |  | Update Orientation Presentation Materials/Benefits Website for launch | 2020-10-01 |  | 2020-10-01 | Ann Monroe
| 2. Pre-Cutover |  | HCM | Time/Absence |  |  | Collect and load Annual, sick, personal holiday, military leave used, LWOP. | 2020-10-01 |  | 2020-12-01 | Emily Goodwin/Dora Tilles
| 2. Pre-Cutover |  | HCM | Time/Absence |  |  | Collect anticipated time offs from university for 12/1 - 12/15 from departments | 2020-10-01 |  | 2020-12-01 | Emily Goodwin/Dora Tilles
| 2. Pre-Cutover |  | HCM | Time/Absence |  |  | Collect employees who will be on cyclic leave when we launch both from central and from AIS | 2020-10-01 |  | 2020-12-01 | Emily Goodwin/Dora Tilles
| 2. Pre-Cutover |  | HCM | Time/Absence |  |  | Identify employees who are active but not on an appt for launch but will be starting their appt again soon so that we can make sure they are hired or terminated in the system | 2020-10-01 |  | 2020-12-01 | Emily Goodwin/Dora Tilles
| 2. Pre-Cutover | Communication | FIN | Effort Reporting | Legacy |  | Last Paper Effort Cert Period End 8/15 | 2020-10-05 |  | 2020-11-30 | Carrie Johnston/Christine Galbreath
MPP | 2. Pre-Cutover | Soft Freeze/Hard Freeze | FIN | FDM |  |  | Finalize FDM Workbook with values to load, hierarchies, default and allowed worktags | 2020-10-06 |  | 2020-10-30 | Gerik Kimble, Joy Morton
MPP | 2. Pre-Cutover | Soft Freeze/Hard Freeze | FIN | FDM |  |  | Freeze FDM Structure – Master file ready - Locked | 2020-10-06 |  | 2020-10-30 | Gerik Kimble, Joy Morton
MPP | 2. Pre-Cutover |  | TECH | Conversion |  |  | Create Gold Tenant Build Tracker | 2020-10-06 |  | 2020-11-02 | Jane Thomas. Keerthinath Manoharan | Complete
MPP | 2. Pre-Cutover |  | FIN | Core Finance | Legacy |  | FIN Data Cleansing Completed | 2020-10-06 |  | 2020-11-02 | Gerik Kimble/Joy Morton
MPP | 2. Pre-Cutover |  | FIN | Core Finance |  |  | Finalize Finance Crosswalk Changes | 2020-10-06 |  | 2020-11-02 | Gerik Kimble, Joy Morton
MPP | 2. Pre-Cutover |  | HCM | Core HR |  |  | Finalize HCM Crosswalk Changes | 2020-10-06 |  | 2020-11-02 | Jennifer Klein
MPP | 2. Pre-Cutover |  | HCM | Core HR | Legacy |  | HCM Data Cleansing Completed | 2020-10-06 |  | 2020-11-20 | Jennifer Klein
| 2. Pre-Cutover | Cutover Team | MTP | Conversion |  |  | Request 'Create New' Tenant (Gold) | 2020-10-12 |  | 2020-10-12 | Jane Thomas, Mel Roberts | [5 empty] | No earlier than 6 weeks prior to MTP date.
MPP | 2. Pre-Cutover | Cutover Team | TECH | HCM/Payroll/Finance |  |  | Gold/Cutover Kick-Off | 2020-10-12 |  | 2020-10-13 | Brant Schroeder, Jane Thomas
| 2. Pre-Cutover | Cutover Team | MTP | Conversion |  |  | Request to provision Tenant (Gold) | 2020-10-14 |  | 2020-10-14 | Jane Thomas, Mel Roberts | [5 empty] | No earlier than 6 weeks prior to MTP date.
MPP | 2. Pre-Cutover | Critical Date | PMO |  |  |  | Conduct Cutover DA Review | 2020-10-16 |  | 2020-10-16 | Workday, Jane Thomas, David Boeker
MPP | 2. Pre-Cutover | Tenant Readiness and Validation | PMO |  |  |  | Conduct Readiness Assessment 5 against Checklist | 2020-10-16 |  | 2020-10-26 | David Boeker, Jennifer Klein, Joy Morton, Mike Corwin | In Progress
| 2. Pre-Cutover | Cutover Team | MTP | Conversion |  |  | Request - Create Gold Tenant - (forms from customer 14 days prior to the go-live signed) 11/23 - 30 days to make the official request for MTP | 2020-10-18 |  | 2020-10-18 | Jane Thomas, Mel Roberts | [5 empty] | No earlier than 6 weeks prior to MTP date.
MPP | 2. Pre-Cutover | Cutover Team | PMO |  |  |  | Confirm Cutover Plan Delivered | 2020-10-20 |  | 2020-10-20 | David Boeker
| 2. Pre-Cutover | Critical Date | FIN | Controller | Legacy | When is the close for FY2020 | Last day for FY20 year end adjustments for financial statements | 2020-10-26 |  | 2020-10-26 | Chris Conway
| 2. Pre-Cutover |  | HCM | Benefits |  |  | Train Benefits on Hoover templates for Health Savings Accounts and Health Spending(FSA/DCAP) Accounts for 1/1/2021 start dates (in advance of OE) | 2020-10-26 |  | 2020-10-30 | Wendy Weber
MPP | 2. Pre-Cutover | Cutover Team | PMO |  |  |  | Incorporate DA Feedback | 2020-10-28 |  | 2020-11-02 | Brant Schroeder, Jane Thomas
| 2. Pre-Cutover | Critical Date | FIN | Controller | Legacy |  | Books close for FY20, Financial Statements finalized | 2020-10-30 |  | 2020-10-30 | Chris Conway
| 2. Pre-Cutover | Hard Freeze | HCM | Supervisory Org |  |  | Lock Sup Org Structure 11/2/2020 for final R2PM | 2020-11-01 |  | 2020-11-02 | Wendy Weber
| 2. Pre-Cutover | Critical Date | HCM | Benefits | Legacy |  | Open Enrollment | 2020-11-01 |  | 2020-11-30 | Benefits/HCA
| 2. Pre-Cutover |  | HCM | Supervisory Org |  |  | Vacant position list produced for sup org updates (and conversion team) | 2020-11-02 |  | 2020-11-15 | Jim Lowery/Sabrina McPherson
| 2. Pre-Cutover | Cutover Team | TECH | Conversion |  |  | Create JIRA Gold Extract Conversion tickets | 2020-11-12 | 8am | 2020-11-12 | Brant Schroeder
| 2. Pre-Cutover |  | HCM | Supervisory Org |  |  | Update final academic unit people changes to database by 11/19/2020 | 2020-11-14 |  | 2020-11-19 | Wendy Weber
| 2. Pre-Cutover | Freeze Date | FIN | Expenses | Legacy |  | Cash advance requests received by Travel Services by 11/15/2020 | 2020-11-15 |  | 2020-11-15 | Departments
| 2. Pre-Cutover |  | Payroll | Payroll | Legacy |  | Get PMFL (Paid Family and Medical Leave) & Unemployment | 2020-12-18 |  | 2020-12-18 | Jay Maylor, Kim Lawton, Mayra Young
| 3. Cutover | Gold Build | TECH/HCM/FIN | Conversion | Workday |  | Validate/Load Group 4 Extracts | 2002-11-22 |  | 2020-12-01 | Clint McGregor, Wendy Weber, Christine Galbreath, Jim Lowery
| 3. Cutover | Communication | HCM | Recruiting | Legacy |  | Communicate background check processing changes. | 2020-10-01 |  | 2020-10-15 | Sabrina McPherson, Jon Hurd
MPP | 3. Cutover | Production Readiness | Operating Committee |  |  |  | Gate 1 - Prior to Gold Configuration | 2020-10-29 |  | 2020-10-29 | Jay Dumphy, Jennifer Klein, Joy Morton, Mike Corwin
| 3. Cutover | Gold Build | FIN | ITD/Budget/GL | Workday |  | FY20 Rollover Core Budget | 2020-10-30 |  | 2020-12-01 | Chris Conway/Jodi Heins | [5 empty] | Acct_JRNLS_BDGT_Carryforward.csv (06/30 extract date)
| 3. Cutover | Gold Build | FIN | ITD/Budget/GL | Workday |  | FY20 Ending Financial Balances - EIB - ITD Journal | 2020-10-30 |  | 2020-12-01 | Chris Conway/Jodi Heins | [5 empty] | Trial Balance Load, Accounting_Journals.csv
| 3. Cutover | Hard Freeze | HCM | Supervisory Org |  |  | Lock Academic Unit Structure 11/1/2020 for final R2PM | 2020-11-01 |  | 2020-11-02 | Wendy Weber
| 3. Cutover | Gold Build | Security |  | Workday |  | Create Implementer Accounts in Gold | 2020-11-02 |  | 2020-11-02 | Lindsay Emer/Mel Roberts
| 3. Cutover | Gold Build | TECH | Conversion | Workday |  | Request Locations file | 2020-11-02 |  | 2020-11-02 | Karl Riley
| 3. Cutover | Gold Build | FIN | Configuration |  |  | Setup Company | 2020-11-02 |  | 2020-11-02
| 3. Cutover | Gold Build | HCM | Benefits | Legacy |  | Updates and final pre-launch review of Benefits: DOD, Semester by Semester, 480/6/8, Seasonal, 2 year averaging, survivor annuity option, DRS Employment Override Code, Rehire Retirees and Court Ordered coverage lists from Benefits due by 11/13 | 2020-11-02 |  | 2020-11-13 | Wendy Weber
| 3. Cutover |  | HCM | Supervisory Org |  |  | Final Sup Org People Build files to AFOs | 2020-11-02 |  | 2020-11-13 | AFOs
| 3. Cutover | Gold Build | HCM | Benefits | Legacy |  | Validate data between Campus Community and HEPPS pre-conversion file snapshot. (Valid addresses, zipcodes) | 2020-11-02 |  | 2020-11-18 | Stacy Combs
2 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Implementation Suites | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | a | b | Implementation Suites |  | Upgraded in-use suites to v.34.0 or v.34.1 where required due to version retirement
3 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Condition Rule Categories | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | b | a | Setup Data
4 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Phone Device Types | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | b | ba | Setup Data
5 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Address Usage Types | 11/2/2020 |  | 2020-11-20 | Jodi Heins |  | b | bb | Setup Data |  | Needed for Company Setup
8 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Name Types | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | b | bd | Setup Data
9 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Ethnicities | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
10 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Disabilities | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
14 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Genders | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
15 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Gender Identities | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
16 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Sexual Orientations | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
17 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Pronouns | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
18 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Citizenship Statuses | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
19 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Marital Statuses | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
20 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Military Statuses | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
28 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Related Person Relationships | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
30 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee Probation Period Types | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
31 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee Probation Period Reasons | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
34 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Global Identifier Usage Types | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
35 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Government ID Types | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
36 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | License ID Types | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
37 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Passport ID Types | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
38 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Visa ID Types | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
44 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee Types | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | b | cb | Setup Data
45 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Contingent Worker Types | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | b | cc | Setup Data
46 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Termination Categories | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | b | cd | Setup Data
48 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Event Categories and Reasons | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | b | ce | Setup Data
49 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefits Event Categories | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  |  |  | Setup Data
50 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Job Event Categories | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | b | cf | Setup Data
51 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | End Additional Job Categories | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
52 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Undo Move Categories | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
54 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Text Block Categories | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | b | ch1 | Setup Data
61 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Country Predefined Person Name Component Values | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | b | da | Setup Data |  | Predefined Person Name Values
71 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Frequencies | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  |  |  | Setup Data |  | WSU uses 2,088 (not 2,080) as Annualization Factor for Hourly frequency
84 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Quicklinks | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | b | gd | Setup Data
87 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Postal Code Sets | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  |  |  | Setup Data |  | Suraj Kolimi will be loading these
94 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Custom Lists | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | b | z1 | Setup Data |  | Built as needed by respective leads
95 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Profiles | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | c | ac | Organizations
96 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Location Types | 11/2/2020 |  | 2020-11-20 | Kyle Babinski |  | c | ba | Organizations
97 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Location Attributes | 11/2/2020 |  | 2020-11-20 | Kyle Babinski |  |  |  | Organizations
98 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Work Space Levels | 11/2/2020 |  | 2020-11-20 | Kyle Babinski |  | c | bb | Organizations
99 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Location Hierarchies without Superiors | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | c | bc1 | Organizations
100 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Location Hierarchies | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | c | bc2 | Organizations
101 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Locations | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | c | bd | Organizations
106 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Retiree Organizations without Superiors | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | c | i1 | Organizations
107 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Retiree Organizations | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | c | i2 | Organizations
108 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Supervisory Organizations without Superiors | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | c | ja1 | Organizations
109 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Supervisory Organizations | 11/2/2020 |  | 2020-11-20 | Kyle Babinski |  | c | ja2 | Organizations
111 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Unions | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | c | ka | Organizations
112 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Union Membership Types | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | c | kb | Organizations
122 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Hierarchy Structures | 11/2/2020 |  | 2020-11-20 | Kyle Babinski |  | c | r | Organizations
123 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Location Hierarchy Organization Assignments | 11/2/2020 |  | 2020-11-20 | Kyle Babinski |  | c | s | Organizations
156 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Degrees | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | a3 | ai | Talent Management Setup
157 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Educational Institution Types (school types) | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | a3 | aj | Talent Management Setup |  | These are called "school types" in the impl area in CC
159 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Fields of Study | 11/2/2020 |  | 2020-11-20 | Jim Broucek |  | a3 | al | Talent Management Setup
272 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Currency Rate Types | 11/2/2020 |  | 2020-11-20 | Lindsay Emer |  | c | ba | Compensation |  | This is required for Tax Authorities and Company Accounting Details
309 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | To Dos | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | a | Business Processes |  | To be built by individual leads for P1, migrated in phases for P2+ (empty versions for conversion at top and default versions with builds)
310 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Checklists | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | b | Business Processes |  | To be built by individual leads for P1, migrated in phases for P2+ (empty versions for conversion at top and default versions with builds)
311 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Calculated Dates without Dependencies | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | c1 | Business Processes |  | To be built by individual leads for P1, migrated in phases for P2+ (empty versions for conversion at top and default versions with builds)
312 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Calculated Dates | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | c2 | Business Processes |  | To be built by individual leads for P1, migrated in phases for P2+ (empty versions for conversion at top and default versions with builds)
313 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Export Tenant (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | d | Business Processes |  | To be built by individual leads for P1
314 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Condition Rules without Dependencies | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | e1 | Business Processes
315 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Condition Rules | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | e2 | Business Processes
316 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Business Process Definitions | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | fa | Business Processes |  | 21 in error, awaiting updates 6/10
319 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Related Links | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | g | Business Processes |  | To be built by individual leads for P1, migrated in phases for P2+ (empty versions for conversion at top and default versions with builds)
320 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Default Email Text for Alert Notifications | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | h | Business Processes |  | To be built by individual leads for P1, migrated in phases for P2+ (empty versions for conversion at top and default versions with builds)
322 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Inbox Views | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | j | Business Processes |  | To be built by individual leads for P1, migrated in phases for P2+ (empty versions for conversion at top and default versions with builds)
324 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Health Care Classifications | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | aa | Benefits
325 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Health Care Coverage Targets | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | ab | Benefits
326 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Insurance Coverage Targets | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | ac | Benefits
327 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Coverage Types | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | ad | Benefits
328 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Enrollment Event Types | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | ae | Benefits
329 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Annual Rate Types | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | af | Benefits
330 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Annual Credit Types | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | ag | Benefits
331 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Additional Benefits Coverage Targets | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | ah | Benefits
332 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | COBRA Eligibility Reasons | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | ai | Benefits
333 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Provider Identifier Types | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | aj | Benefits
334 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Providers | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | ak | Benefits
335 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Coverage Level Sets | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | b | Benefits
336 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Insurance Coverages | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | c | Benefits
337 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Health Care Rates | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | d | Benefits
338 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Insurance Rates | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | e | Benefits
339 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Credits | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | fa | Benefits
340 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Credit Bundles | 11/2/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | fb | Benefits
369 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Period Schedules (Monthly) and close/lock periods | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | f1 | b | Absence Setup Data
373 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Generic Calculations | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | f1 | d | Absence Setup Data | Payroll setup | Mel Roberts will load this
388 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Create Positions | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | g | ba | Positions, Headcount, and Job Groups
389 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Edit Positions | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | g | bb | Positions, Headcount, and Job Groups
390 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Edit Position Restrictions | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | g | bc | Positions, Headcount, and Job Groups
391 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Freeze Positions | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | g | bca | Positions, Headcount, and Job Groups
392 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Filled Positions | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | g | bd | Positions, Headcount, and Job Groups
393 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Headcount Groups (Manual) | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | g | c | Positions, Headcount, and Job Groups
394 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Job Groups | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | g | d | Positions, Headcount, and Job Groups
397 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Create Job Requisitions | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | g | g | Positions, Headcount, and Job Groups
398 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Edit Job Requisitions | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | g | h | Positions, Headcount, and Job Groups
399 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Requisition Compensation Change | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | g | i | Positions, Headcount, and Job Groups
400 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Work Space | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | g | j | Positions, Headcount, and Job Groups
401 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Create Pre-Hires | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | aa1 | Pre-Hires, Employees, and Contingent Workers
402 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Hire Employees | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ab | Pre-Hires, Employees, and Contingent Workers
403 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Contract Contingent Workers | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ac | Pre-Hires, Employees, and Contingent Workers
404 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Personal Information | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ad | Pre-Hires, Employees, and Contingent Workers
405 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Legal Name | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ae | Pre-Hires, Employees, and Contingent Workers
406 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Preferred Name | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | af | Pre-Hires, Employees, and Contingent Workers
407 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Additional Name | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ag | Pre-Hires, Employees, and Contingent Workers
408 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Maintain Contact Information | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ai | Pre-Hires, Employees, and Contingent Workers
409 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Work Contact Information | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | aia | Pre-Hires, Employees, and Contingent Workers
410 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Home Contact Information | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | aib | Pre-Hires, Employees, and Contingent Workers
411 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Government IDs | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | aj | Pre-Hires, Employees, and Contingent Workers
412 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Passports and Visas | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ak | Pre-Hires, Employees, and Contingent Workers
413 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Licenses | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | al | Pre-Hires, Employees, and Contingent Workers
414 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Other IDs | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | am | Pre-Hires, Employees, and Contingent Workers
415 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Update Effective Dated Employee Compensation (Required) | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ao | Pre-Hires, Employees, and Contingent Workers
416 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Request Compensation Change | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ap | Pre-Hires, Employees, and Contingent Workers
417 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Assign Organizations | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | aq1 | Pre-Hires, Employees, and Contingent Workers
418 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Organization Assignments | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | aq2 | Pre-Hires, Employees, and Contingent Workers
419 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee Position Payroll | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | as | Pre-Hires, Employees, and Contingent Workers
420 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Edit Service Dates | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ba | Pre-Hires, Employees, and Contingent Workers
421 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee Job and Position History | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | bb | Pre-Hires, Employees, and Contingent Workers
422 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee Compensation History | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | bc | Pre-Hires, Employees, and Contingent Workers
423 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee Time Off Events | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | bd | Pre-Hires, Employees, and Contingent Workers
424 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Carryover Balances | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | be | Pre-Hires, Employees, and Contingent Workers
425 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Carryover Override Rules | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | be1 | Pre-Hires, Employees, and Contingent Workers
426 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee Reviews | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | bf | Pre-Hires, Employees, and Contingent Workers
427 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Load Worker Documents | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | bh | Pre-Hires, Employees, and Contingent Workers
428 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Worker Photos | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | bi | Pre-Hires, Employees, and Contingent Workers
429 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Dependents | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ca | Pre-Hires, Employees, and Contingent Workers
430 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Beneficiaries | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | cb | Pre-Hires, Employees, and Contingent Workers
431 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Beneficiaries | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | cc | Pre-Hires, Employees, and Contingent Workers
432 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Emergency Contacts | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | cc2 | Pre-Hires, Employees, and Contingent Workers
433 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Change Benefits for Life Event | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | cd | Pre-Hires, Employees, and Contingent Workers
434 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Jobs | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ce | Pre-Hires, Employees, and Contingent Workers
435 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Annual Rate | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | cf | Pre-Hires, Employees, and Contingent Workers
436 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Annual Credit | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | cg | Pre-Hires, Employees, and Contingent Workers
437 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Worker Wellness Data | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ch | Pre-Hires, Employees, and Contingent Workers
438 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee T1 Withholding Elections | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ci | Pre-Hires, Employees, and Contingent Workers
439 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee W-4 Withholding Elections | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | cj | Pre-Hires, Employees, and Contingent Workers
440 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | COBRA Participant Eligibility | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ck | Pre-Hires, Employees, and Contingent Workers
441 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Manage Medicare Information | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | cl | Pre-Hires, Employees, and Contingent Workers
442 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Medicare Part D EGWP | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | cm | Pre-Hires, Employees, and Contingent Workers
443 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee One-Time Payments | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | da | Pre-Hires, Employees, and Contingent Workers
444 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Request One-Time Payment | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | da1 | Pre-Hires, Employees, and Contingent Workers
445 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee Stock Grant Events | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | db | Pre-Hires, Employees, and Contingent Workers
446 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee True Up Payments | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | dc | Pre-Hires, Employees, and Contingent Workers
447 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Future Payment Plan Assignments | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | dd | Pre-Hires, Employees, and Contingent Workers
448 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Add Additional Job | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ea | Pre-Hires, Employees, and Contingent Workers
449 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | End Additional Job | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | eb | Pre-Hires, Employees, and Contingent Workers
450 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Start International Assignment | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ec | Pre-Hires, Employees, and Contingent Workers
451 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | End International Assignment | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ed | Pre-Hires, Employees, and Contingent Workers
452 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee Contracts | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ee | Pre-Hires, Employees, and Contingent Workers
453 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Add Retiree Status | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ef | Pre-Hires, Employees, and Contingent Workers
454 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Remove Retiree Status | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | eg | Pre-Hires, Employees, and Contingent Workers
455 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Union Membership | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ei | Pre-Hires, Employees, and Contingent Workers
456 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Worker Pools | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ej | Pre-Hires, Employees, and Contingent Workers
457 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Provisioning Group Assignments | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | g | Pre-Hires, Employees, and Contingent Workers
458 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Social Network Accounts | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | h | Pre-Hires, Employees, and Contingent Workers
459 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Job Change | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | za | Pre-Hires, Employees, and Contingent Workers
460 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Employee Leave of Absence Events | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | zc | Pre-Hires, Employees, and Contingent Workers
461 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Terminate Employees | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | zd | Pre-Hires, Employees, and Contingent Workers
462 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | End Contingent Worker Contracts | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | ze | Pre-Hires, Employees, and Contingent Workers
463 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Former Workers | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | zy | Pre-Hires, Employees, and Contingent Workers
464 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Former Worker Attachments | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | h | zz | Pre-Hires, Employees, and Contingent Workers
467 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Integration System Security Segments | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i1 | c | Security Segments |  | Coordinate with Kristen Flannery and Akriti
470 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Compensation Setup Security Segments | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i1 | f | Security Segments |  | Coordinate with Kristen Flannery and Akriti
472 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Request Type Security Segment | 11/2/2020 |  | 2020-11-20 | Lindsay Emer |  | i1 | i | Security Segments |  | Mel Roberts already loaded for UAT-WSU9
473 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | User-Based Groups without Dependencies (Initial Load) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i2 | a1 | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
474 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | User-Based Groups (Initial Load) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i2 | a2 | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
475 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Assignable Roles without Dependencies (Initial Load) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i2 | b | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
476 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Role-Based Security Groups (Constrained) (Initial Load) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i2 | ca | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
477 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Role-Based Security Groups (Unconstrained) (Initial Load) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i2 | cb | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
480 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Organization-Based Security Groups (Constrained) (Initial Load) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i2 | e1 | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
485 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | 2-Integration System Security Groups (Unconstrained) (Initial Load) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i2 | hb | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
488 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Intersection Security Groups (Initial Load) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i2 | j | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
489 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Aggregation Security Groups (Initial Load) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i2 | k | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
491 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Segment-Based Security Groups (Initial Load) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i2 | m | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
492 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Assignable Roles (Initial Load) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i2 | na | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
493 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Configure Domain Security Policies (Initial Load) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i2 | o | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
494 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Business Process Security Policies (Initial Load) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i2 | p | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
495 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Enable Functional Areas & Activate Pending Security Policy Changes (Initial Load) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | i2 | q | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
561 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Add Academic Appointments | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | n | ra | Higher Education
562 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Update Academic Appointments | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | n | rb | Higher Education |  | EIB often used to link to Named Professorships - EIB load
564 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Create Named Professorship | 11/2/2020 |  | 2020-11-20 | Jane Thomas |  | n | sa | Higher Education |  | EIB load
567 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Email Templates | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | a | b | Setup Data
571 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Calculated Fields for Setup Data | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | a | f | Setup Data |  | 6/10: 83 of 4,808 in error 5/26: 4,400 of 4,808 loaded; remaining tied to configurations for Absence, Benefits, Compensation, Financials, and Time Tracking
573 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Workcart Link Overrides | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | a | h | Setup Data
574 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | SAML SSO Links | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | a | k | Setup Data
575 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Quicklinks | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | a | l | Setup Data
576 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Quicklink Groups | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | a | m | Setup Data
612 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Integration System Security Segments | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | c | b | Security Segments
613 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Message Queue Security Segments | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | c | c | Security Segments
640 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | 1-Create Integration System Security Groups (Constrained) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | r | Configurable Security
641 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | 2-Create Integration System Security Groups (Unconstrained) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | t | Configurable Security
643 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Create Intersection Security Groups | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | w | Configurable Security |  | No records
644 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Create Aggregation Security Groups | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | x | Configurable Security
645 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Segment-Based Security Groups | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | y | Configurable Security
647 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Create Segment-Based Security Groups | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | aa | Configurable Security
649 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Business Process Security Policies | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | ac | Configurable Security
651 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Create Business Process Security Policies | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | d | ae | Configurable Security
654 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | User-Based Security Group Assignments | 11/2/2020 |  | 2020-11-20 | Lindsay Emer |  | d | ai | Configurable Security
655 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Role-Based Security Group Assignments | 11/2/2020 |  | 2020-11-20 | Lindsay Emer |  | d | aj | Configurable Security
656 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Assign Role-Based Security Groups | 11/2/2020 |  | 2020-11-20 | Lindsay Emer |  | d | al | Configurable Security
668 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payment Election Rules without Dependencies | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | f | g | Payment Information |  | Jodi Heins revised them 3/9, reference IDs updated 3/10
669 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payment Election Rules | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | f | h | Payment Information |  | Jodi Heins revised them 3/9, reference IDs updated 3/10
680 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | External Sources for Integration | 11/2/2020 |  | 2020-11-20 | Gurparshad |  | g | e | Customer and Supplier Setup
1002 | 3. Cutover | Gold Build | Tech | Configuration | Workday |  | Condition Rules without Dependencies | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | u | d | Business Processes
1009 | 3. Cutover | Gold Build | Tech | Configuration | Workday |  | Default Email Text for Alert Notifications | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | u | k | Business Processes |  | Converted over existing from prior build. Each person responsible for BP updates - details on separate tracker.
1011 | 3. Cutover | Gold Build | Tech | Configuration | Workday |  | Custom Validation Rules without Dependencies | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | v | b | Custom Validations and Worktag Rules
1012 | 3. Cutover | Gold Build | Tech | Configuration | Workday |  | Custom Validation Rules | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | v | c | Custom Validations and Worktag Rules
1028 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Expense Credit Cards | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | y | c | Worker Expense Preferences and Credit Cards |  | Will be loaded via integrations
1078 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Authentication Selector | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | ac | a | Tenant
1079 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Tenant Setup - Payroll | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ac | b | Tenant
1080 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | IP Range | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | ac | c | Tenant
1083 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Announcement Rules without Dependencies | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ac | f | Tenant
1084 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Announcement Rules | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ac | g | Tenant
1085 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Announcements Worklets | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ac | h | Tenant
1086 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Tenant Setup - System | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ac | i | Tenant
1087 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Tenant Setup - Search | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ac | j | Tenant
1088 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Tenant Setup - Global | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ac | k | Tenant
1089 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Tenant Setup - Language Options | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ac | l | Tenant
1090 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Tenant Setup - Security | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ac | m | Tenant
1091 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Tenant Setup - BP & Notifications | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ac | n | Tenant
1092 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Tenant Setup - Integrations | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ac | o | Tenant
1094 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Tenant Setup - Worklets | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ac | q | Tenant
1095 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Tenant Challenge Questions | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | ac | r | Tenant
1096 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Authentication Policy | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | ac | s | Tenant
1097 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Access Restrictions | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | ac | t | Tenant
1098 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Activate Authentication Policy | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | ac | u | Tenant
1099 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Worklet Configurations | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ac | v | Tenant
1101 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Tenant Setup - Reporting and Analytics | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ac | x | Tenant
1102 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Multi Factor Authentication Providers | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | ac | y | Tenant
1104 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Organization Type Exception Audit (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | a | Audit Reports
1105 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Audit Locations for Membership in Organizations (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | b | Audit Reports
1107 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Organization Assignment Exception Audit (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | d | Audit Reports
1108 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Contact Information Security Audit Report (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | e | Audit Reports
1110 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Condition Rule Exception Audit (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | g | Audit Reports
1111 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Business Process Definitions with Integration Steps using Deprecated Fields (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | h | Audit Reports
1113 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Report Specific Calculated Field Exception Audit (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | j | Audit Reports
1114 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Integration Exception Audit (Manual) | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | ad | k | Audit Reports
1115 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | All Custom Reports with "Do Not Use" Items (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | l | Audit Reports
1116 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Validate Composite Reports (Manual) | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | ad | m | Audit Reports
1117 | 3. Cutover | Gold Build | Tech | Configuration | Workday |  | Organization Exception Audit (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | n | Audit Reports
1118 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Audit Positions for Membership in Organizations (Manual) | 11/2/2020 |  | 2020-11-20 | Kyle Babinski |  | ad | o | Audit Reports
1119 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Security Exception Audit (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | p | Audit Reports
1120 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Unfilled Assigned Roles Audit (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | q | Audit Reports
1121 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Business Process Exception Audit (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | r | Audit Reports
1122 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Condition Rules using Deprecated Fields (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | s | Audit Reports
1123 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Custom Report Exception Audit (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | t | Audit Reports
1124 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Scheduled Future Reports Exception Audit (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | u | Audit Reports
1129 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Worklet Mapping Exception Audit (Manual) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ad | z | Audit Reports |  | Certified clear as of 11/27/2019 at 7:40 AM (PT) -- will need re-review before UAT build after integrations migration in December
1130 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Password Rules | 11/2/2020 |  | 2020-11-20 | Kristen Flannery |  | ae | a | Deployment
1132 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Employee System Users | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ae | c | Deployment
1133 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Contingent Worker System Users | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | ae | d | Deployment
1157 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Period Schedules for Payroll | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | a | a | Calendars |  | Ready for updates for Time Tracking and Absence Plan Mappings
1158 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | 1-FLSA Work Period Calendar Rules without Dependencies | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | a | b1 | Calendars
1159 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | 2-FLSA Work Period Calendar Rules | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | a | b2 | Calendars
1160 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | 6-FLSA Work Period Calendar | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | a | b6 | Calendars |  | Follow-up prior to calculation start - to Build FLSA Events
1161 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Run Categories | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | b | a | Run Categories and Pay Groups | Gross/Net Pay Accumulators
1162 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Pay Groups | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | b | b | Run Categories and Pay Groups | Organization Subtypes | Shells load -- additional connections performed manually in the Pay Run Groups and Pay Group Automatic Assignment Rules Steps
1163 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Pay Run Groups | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | b | c | Run Categories and Pay Groups | Pay Groups, Run Categories, and Period Schedules
1164 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Pay Group Automatic Assignment Rules & Update Pay Groups with Rules | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | b | d | Run Categories and Pay Groups | Compensation Plans | Pay Group Assignment Rules are created, awaiting update on Pay Groups once Compensation is assigned
1165 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Enable Custom Worktags (confer with Financials and Time) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | c | ba | Setup Data
1166 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Custom Worktags (confer with Financials and Time) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | c | bb | Setup Data
1167 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Sample Check Images (review with Financials) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | c | ca | Setup Data
1168 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payment Types (review with Financials) | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | c | cb | Setup Data |  | Payment types exists in wsu2 (much smaller list than in E2E)
1169 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payroll Reporting Codes | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | c | d | Setup Data
1173 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payroll State Tax Treaty Withholding Rules | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | c | g | Setup Data
1174 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payroll Action Reason | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | c | i | Setup Data | Run Categories
1175 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Related Calculations | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e2 | a | Payroll Calculations |  | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1176 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Pay Component Groups | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e2 | b | Payroll Calculations |  | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1177 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Balance Periods for Payroll | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e2 | c | Payroll Calculations | calculation layers | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1178 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Earnings | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e2 | d | Payroll Calculations | calculation layers | 46 erros (3/10/2020) awaiting compensation elements
1179 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Deductions | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e2 | e | Payroll Calculations | calculation layers | 4 errors (3/10/2020) awaiting benefit plans
1180 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Net Pay Validation and Arrears | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e2 | f | Payroll Calculations | Deductions
1181 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Pay Accumulations | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e2 | g | Payroll Calculations | calculation layers | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1182 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Pay Balances | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e2 | h | Payroll Calculations | calculation layers | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1183 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Pay Component Group Tax Authority Exceptions | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e2 | i | Payroll Calculations | Pay Component Groups | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1186 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Constant Value Calculations | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e3 | a | Generic Calculations |  | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1187 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Aggregate Calculations | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e3 | b | Generic Calculations | calculation layers | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1188 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Arithmetic Calculations | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e3 | c | Generic Calculations | calculation layers | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1189 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Build Date Calculations | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e3 | d | Generic Calculations | calculation layers | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1190 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Conditional Calculations | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e3 | e | Generic Calculations | calculation layers | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1191 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Constant Date Calculations | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e3 | f | Generic Calculations |  | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1192 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Date Difference Calculations | 11/2/2020 |  | 2020-11-20 | Mel Roberts |  | e3 | g | Generic Calculations | calculation layers | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
| 3. Cutover | Critical Date | HCM | Benefits |  |  | Request DRS History File for Gold Build be provided on 11/20/2020 | 2020-11-02 |  | 2020-11-20 | Wendy Weber
| 3. Cutover | Critical Date | HCM | Benefits |  |  | Request HCA Pay1 File for Gold Build be provided on 11/20/2020 | 2020-11-02 |  | 2020-11-20 | Wendy Weber
| 3. Cutover | Gold Build | HCM/Payroll/FIN | Configuration |  |  | Configure Gold Tenant for HCM, Payroll and Finance | 2020-11-02 |  | 2020-11-20 | Kyle Babinski, Mel Roberts, Ed Nieskes
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Disable appropriate Finance Business Processes | 2020-11-02 |  | 2020-11-20 | Ed Nieskes
| 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Edit Tenant Setup - Disable Beneficiary, Emergency Contact and Dependent Linking (mark the box) | 2020-11-02 |  | 2020-11-20 | Suraj Kolimi, Kyle Babinski
| 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Mark Position Term as 'not' required for Position Assignment for Hire load | 2020-11-02 |  | 2020-11-20 | Kyle Babinski
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Open the accounting Period for Customer Invoice and suggest that all invoices have a 7/1/xxxx accounting date which is the same on the extract. | 2020-11-02 |  | 2020-11-20 | Ed Nieskes
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Register Assets Worktags - Maintain Worktag Usage - On Register Assets extract below business object are provided as worktags, 1. Cost Center 2. Fund 3. Function 4. Region 5. Alternate Reporting 6. Program 7. Gift 8. Grant But only Cost Center, Fund, Function, Region and Project are the allowed worktags as per the config. | 2020-11-02 |  | 2020-11-20 | Ed Nieskes
| 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Set Up Academic Pay Period | 2020-11-02 |  | 2020-11-20 | Jim Broucek/Shawn Ismail
| 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Set Up Academic Unit Hierarchy | 2020-11-02 |  | 2020-11-20 | Jim Broucek/Shawn Ismail
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Set up the Allow Accounting in Arrears – it’s on the Company Accounting Details. | 2020-11-02 |  | 2020-11-20 | Ed Nieskes
| 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Verify Job Catalog (double check that Job Profiles/Classes all loaded properly) - Job Profiles tie to Job Classes | 2020-11-02 |  | 2020-11-20 | Thresa Skeslien Jenkins
| 3. Cutover | Gold Build | HCM/Payroll/FIN | Configuration |  |  | Configure Gold Tenant for HCM, Payroll and Finance | 2020-11-02 |  | 2020-11-20 | Kyle Babinski, Mel Roberts, Ed Nieskes
1193 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Date Extract Calculations | 11/2/2020 |  |  | Mel Roberts |  | e3 | h | Generic Calculations | calculation layers | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1194 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Date Increment or Decrement Calculations | 11/2/2020 |  |  | Mel Roberts |  | e3 | i | Generic Calculations | calculation layers | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1195 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Instance Set Comparison Calculations | 11/2/2020 |  |  | Mel Roberts |  | e3 | j | Generic Calculations | calculation layers | 5 in error (3/15/2020), awaiting supervisory organization updates
1196 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Logic Calculations | 11/2/2020 |  |  | Mel Roberts |  | e3 | k | Generic Calculations | calculation layers | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1197 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Lookup Table Setups | 11/2/2020 |  |  | Mel Roberts |  | e3 | l | Generic Calculations | calculation layers | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1198 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Advanced Lookup Tables | 11/2/2020 |  |  | Mel Roberts |  | e3 | m | Generic Calculations |  | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1199 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Lookup Calculations | 11/2/2020 |  |  | Mel Roberts |  | e3 | n | Generic Calculations | Lookup Tables | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1200 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Value Comparison Calculations | 11/2/2020 |  |  | Mel Roberts |  | e3 | o | Generic Calculations | calculation layers | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1201 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Instance Value Calculations | 11/2/2020 |  |  | Mel Roberts |  | e3 | p | Generic Calculations | calculation layers | CAUTION: For migration of existing calculations in P2+, Absence and Payroll calculations are loaded in order: 1. Time calculation tags, then 2. Absence setups without calculations having dependencies to Payroll or Time calculations, then 3. Time Tracking setups, then 4. Payroll calculations, then 5. Absence calculations linked to Payroll, then 6. Generic Calculations are last. If not performed in order, incomplete calculations that cannot be deleted or updated may be generated in Absence or Payroll.
1202 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Pay Component Security Segments | 11/2/2020 |  |  | Mel Roberts |  | f1 | d | Security Segments | Earnings and Deductions
1203 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Account Posting Rule Set (Updates for Payroll) | 11/2/2020 |  |  | Mel Roberts |  | h1 | f | Payroll Accounting | Earnings and Deductions | Brigham completed Payroll updates, reviewed with Mel Roberts
1204 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Ledger Years and Periods (Verify Configured, with Periods Open and Ready for Payroll) | 11/2/2020 |  |  | Mel Roberts |  | h1 | k | Payroll Accounting | Companies
1205 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | 1-Fringe Benefit Commitment Rules without Dependencies | 11/2/2020 |  |  | Mel Roberts |  | h2 | a1 | Commitment Accounting | Companies, Earnings and Deductions
1206 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | 2-Fringe Benefit Commitment Rules | 11/2/2020 |  |  | Mel Roberts |  | h2 | a2 | Commitment Accounting | Companies, Earnings and Deductions
1207 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payroll Commitment Rules | 11/2/2020 |  |  | Mel Roberts |  | h2 | b | Commitment Accounting | Companies, Earnings, and Compensation Elements
1218 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Assign Employees to Pay Group | 11/2/2020 |  |  | Mel Roberts |  | i1 | b | Worker Pay Group Assignments | Employees and Pay Groups | Corrected Loads and setup new report to flag invalide Pay Group Assignments, provided logic correction to Conversion team
1220 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Worker Tax Treaties | 11/2/2020 |  |  | Mel Roberts |  | j1 | a | Tax Treaties | Employees and Conpanies
1221 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Worker W-4 Withholdings (Public) | 11/2/2020 |  |  | Mel Roberts |  | j2 | a | Worker Tax Withholding Elections (USA) | Employees and Companies
1222 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Worker FICA Medicare Withholdings | 11/2/2020 |  |  | Mel Roberts |  | j2 | b | Worker Tax Withholding Elections (USA) | Employees and Companies
1223 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Worker FICA OASDI Withholdings | 11/2/2020 |  |  | Mel Roberts |  | j2 | c | Worker Tax Withholding Elections (USA) | Employees and Companies
1226 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Worker State Withholdings | 11/2/2020 |  |  | Mel Roberts |  | j2 | f | Worker Tax Withholding Elections (USA) | Employees and Companies
1227 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Worker SUTA Withholdings | 11/2/2020 |  |  | Mel Roberts |  | j2 | g | Worker Tax Withholding Elections (USA) | Employees and Companies
1235 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payroll Involuntary Withholding Orders | 11/2/2020 |  |  | Mel Roberts |  | j2 | o | Worker Tax Withholding Elections (USA) | Employees and Companies | Manually entered by Payroll Team - to be updated between builds with new/inactivation orders and debt balance updates
1238 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Company Federal Payroll Tax Reporting | 11/2/2020 |  |  | Mel Roberts |  | k | a | Company Tax Reporting (USA) | Companies | Phase X build document needed for WSU (starting with Company Federal Payroll Tax Reporting) to enable Tax Location Mapping for 2021+
1239 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Company State and Local Tax Reporting | 11/2/2020 |  |  | Mel Roberts |  | k | b | Company Tax Reporting (USA) | Companies
1240 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Company State and Local Year End Tax Reporting | 11/2/2020 |  |  | Mel Roberts |  | k | c | Company Tax Reporting (USA) | Companies
1245 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Batch Data | 11/2/2020 |  |  | Mel Roberts |  | l | a | Payee Input Data | Employees and Pay Groups
1246 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payee Input Data | 11/2/2020 |  |  | Mel Roberts |  | l | b | Payee Input Data | Employees and Pay Groups
1247 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | History Payments | 11/2/2020 |  |  | Mel Roberts |  | l | c | Payee Input Data | Employees, Company and Pay Group Assignments
1248 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | History Payments (Import) | 11/2/2020 |  |  | Mel Roberts |  | l | d | Payee Input Data | Employees, Company and Pay Group Assignments
1249 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payroll Deduction Recipients | 11/2/2020 |  |  | Mel Roberts |  | m | a | Worker Withholding Orders and Deduction Recipients |  | Few additional created ad hoc due to new withholding orders
1250 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Deduction Recipients | 11/2/2020 |  |  | Mel Roberts |  | m | b | Worker Withholding Orders and Deduction Recipients
1251 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Worker Withholding Orders | 11/2/2020 |  |  | Mel Roberts |  | m | c | Worker Withholding Orders and Deduction Recipients | Deduction Recipents | Manually entered by Payroll Team - to be updated between builds with new/inactivation orders and debt balance updates
1253 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payslip Configuration | 11/2/2020 |  |  | Mel Roberts |  | n | a | Payslip Configuration and Paycheck Delivery | Pay Component Groups and Related Calculations | Update needed after Absence Plan balances to show on payslip determined.
1254 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Company Payroll Printing Rules | 11/2/2020 |  |  | Mel Roberts |  | n | b | Payslip Configuration and Paycheck Delivery | Companies
1255 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Paycheck Delivery Methods | 11/2/2020 |  |  | Mel Roberts |  | n | c | Payslip Configuration and Paycheck Delivery | Companies
1256 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Paycheck Delivery | 11/2/2020 |  |  | Mel Roberts |  | n | d | Payslip Configuration and Paycheck Delivery | Employees, Company and Pay Group Assignments | Validated with Brigham, Payroll Printing Options set automatically (print out all Retirees, Terminated workers, and persons that opt-in via self-service). All employees can print own payslip as well.
1257 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Paycheck Delivery (Public) | 11/2/2020 |  |  | Mel Roberts |  | n | e | Payslip Configuration and Paycheck Delivery | Employees, Company and Pay Group Assignments
1259 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payment Election Enrollment | 11/2/2020 |  |  | Mel Roberts |  | o | b | Worker Payment Elections | Payment Election Options and Employees
1260 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Earning and Employee Deduction Costing Allocations | 11/2/2020 |  |  | Mel Roberts |  | p | a | Costing Allocations | Earnings and Deductions
1261 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Employer Paid Expense Costing Allocations | 11/2/2020 |  |  | Mel Roberts |  | p | b | Costing Allocations | Earnings and Deductions
1262 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Fringe Benefit Recovery Costing Allocations | 11/2/2020 |  |  | Mel Roberts |  | p | c | Costing Allocations | Earnings and Deductions
1263 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Costing Allocations | 11/2/2020 |  |  | Mel Roberts |  | p | d | Costing Allocations | Employees, Earnings and Deductions
1264 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | 1-Maintain Payroll Audit Configurations - Compare Periods | 11/2/2020 |  |  | Mel Roberts |  | q | a | Additional Configuration | Pay Components
1265 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | 2-Maintain Payroll Audit Configurations - Results by Period | 11/2/2020 |  |  | Mel Roberts |  | q | b | Additional Configuration | Pay Components | Starter set to kickoff P1. Payroll Team (Kim, Brigham and Rick) to build upon the audit configurations as we go.
1266 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payroll Register by Period Configurations | 11/2/2020 |  |  | Mel Roberts |  | q | c | Additional Configuration | Earnings and Deductions
1267 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payroll Tax Filing Configuration | 11/2/2020 |  |  | Mel Roberts |  | q | d | Additional Configuration | Earnings and Deductions | Groupings for ADP integration
1268 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payroll Results CRF Mappings | 11/2/2020 |  |  | Mel Roberts |  | q | e | Additional Configuration | Pay Components | List to grow as outbound integrations require report fields with payroll data placeholders
1269 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Pay Result CRF Maps (Manual) | 11/2/2020 |  |  | Mel Roberts |  | q | e1 | Additional Configuration | Pay Components | List to grow as outbound integrations require report fields with payroll data placeholders
1270 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Pay Results CRF Mappings - Balance Period Mappings | 11/2/2020 |  |  | Mel Roberts |  | q | e2 | Additional Configuration | Pay Components | Mapped YTDs for Cal Year, Tax Year, and Fiscal Year
1271 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Work Shift Days Worked | 11/2/2020 |  |  | Mel Roberts |  | q | f | Additional Configuration | Work Shifts
1272 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | W-2 Configuration | 11/2/2020 |  |  | Mel Roberts |  | q | g | Additional Configuration | Pay Components, Companies and Tax Years | Brigham completed Payroll updates, reviewed with Mel Roberts
1273 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Payroll Year End Form Box Configuration | 11/2/2020 |  |  | Mel Roberts |  | q | g2 | Additional Configuration | Pay Components, Companies and Tax Years
1276 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Tenant Setup - Payroll | 11/2/2020 |  |  | Mel Roberts |  | s | ch | Tenant
1277 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Maintain Dashboards: Central Payroll and WSU Modernization | 11/2/2020 |  |  | Mel Roberts |  | s | ci | Tenant
1278 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Tenant Setup - Financials (payroll update for sequence generators) | 11/2/2020 |  |  | Mel Roberts |  | s | cj | Tenant
1279 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Worklet Configurations | 11/2/2020 |  |  | Mel Roberts |  | s | e | Tenant
1280 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Unassigned Roles Audit (Manual) | 11/2/2020 |  |  | Mel Roberts |  | t | bc | Audit Reports
1285 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Calculated Field Exception Audit (Manual) | 11/2/2020 |  |  | Mel Roberts |  | t | ea | Audit Reports
1286 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Scheduled Future EIBs Exception Audit (Manual) | 11/2/2020 |  |  | Mel Roberts |  | t | ef | Audit Reports
1287 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Audit - Missing Direct Deposit Payment Elections (Manual) | 11/2/2020 |  |  | Mel Roberts |  | t | f | Audit Reports
1288 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Taxable and Subject Wages Conversion | 11/2/2020 |  |  | Mel Roberts |  | v | a | Taxable and Subject Wages Conversion | Employees, Company and Pay Group Assignments
1293 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Audit Reports | 11/2/2020 |  |  | Mel Roberts |  | f1 | k | Absence Setup Data
1296 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Build Out FLSA Periods with New Start Date | 11/2/2020 |  |  | Mel Roberts |  | x | x | Additional Configuration
1297 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Tenant Analyzer | 11/2/2020 |  |  | Mel Roberts |  | zg | z | Tenant Analyzer | HCM, PAY, FIN setup | Post-copy follow-up for smoke test/resolve
1313 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Period Schedules (complete Time-to-Payroll updates) | 11/2/2020 |  |  | Mel Roberts |  | f | a | Calendars
1314 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Profile Groups | 11/2/2020 |  |  | Mel Roberts |  | i | f | Tenant
1319 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Calculated Fields Audit | 11/2/2020 |  |  | Mel Roberts |  | a |  | Reports and Integrations
1320 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Gauge Ranges | 11/2/2020 |  |  | Kristen Flannery |  | ba |  | Reports and Integrations
1321 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Analytic Indicators | 11/2/2020 |  |  | Kristen Flannery |  | bb |  | Reports and Integrations
1322 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Formatting Styles | 11/2/2020 |  |  | Kristen Flannery |  | bc |  | Reports and Integrations
1323 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Excel Template Attachments | 11/2/2020 |  |  | Kristen Flannery |  | bd |  | Reports and Integrations
1324 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Facet Range Groups | 11/2/2020 |  |  | Kristen Flannery |  | be |  | Reports and Integrations
1325 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Prompt Sets | 11/2/2020 |  |  | Kristen Flannery |  | bf |  | Reports and Integrations
1326 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Outline Structures | 11/2/2020 |  |  | Kristen Flannery |  | bg |  | Reports and Integrations
1327 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Field Value Groups | 11/2/2020 |  |  | Kristen Flannery |  | bh |  | Reports and Integrations
1328 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Report Tags | 11/2/2020 |  |  | Kristen Flannery |  | c |  | Reports and Integrations
1329 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Delivered Business Form Layout Token Values | 11/2/2020 |  |  | Kristen Flannery |  | d |  | Reports and Integrations
1330 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Custom Business Form Stylesheet Attachments | 11/2/2020 |  |  | Kristen Flannery |  | ea |  | Reports and Integrations
1331 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | 1-Custom Business Form Report Design Attachments | 11/2/2020 |  |  | Kristen Flannery |  | eb |  | Reports and Integrations
1332 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | 2-Custom Business Form Report Design Translation Attachments | 11/2/2020 |  |  | Kristen Flannery |  | ec |  | Reports and Integrations
1333 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Business Form Layouts | 11/2/2020 |  |  | Kristen Flannery |  | ed |  | Reports and Integrations
1334 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Custom Data Sources | 11/2/2020 |  |  | Kristen Flannery |  | ee |  | Reports and Integrations
1335 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Custom Dashboards | 11/2/2020 |  |  | Kristen Flannery |  | f0 |  | Reports and Integrations
1336 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Trended Worker Setup | 11/2/2020 |  |  | Kristen Flannery |  | f1 |  | Reports and Integrations
1337 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Base Custom Reports | 11/2/2020 |  |  | Kristen Flannery |  | fa |  | Reports and Integrations
1338 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Custom Reports | 11/2/2020 |  |  | Kristen Flannery |  | fb |  | Reports and Integrations
1339 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | nBox Setup | 11/2/2020 |  |  | Kristen Flannery |  | fc |  | Reports and Integrations
1340 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Excel Template Configurations | 11/2/2020 |  |  | Kristen Flannery |  | fd |  | Reports and Integrations
1341 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Saved Filters (Manual) | 11/2/2020 |  |  | Kristen Flannery |  | fda |  | Reports and Integrations
1342 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Analytic Metric Values | 11/2/2020 |  |  | Kristen Flannery |  | fe |  | Reports and Integrations
1343 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Report Groups | 11/2/2020 |  |  | Mel Roberts |  | fea |  | Reports and Integrations
1344 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Custom Dashboard Configurations | 11/2/2020 |  |  | Kristen Flannery |  | ff |  | Reports and Integrations
1345 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | PGP Public Keys | 11/2/2020 |  |  | Kristen Flannery |  | ga |  | Reports and Integrations
1346 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | x509 Public Keys | 11/2/2020 |  |  | Kristen Flannery |  | gb |  | Reports and Integrations
1347 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | 1-Integration Notification Condition Rules without Dependencies | 11/2/2020 |  |  | Kristen Flannery |  | h1 |  | Reports and Integrations
1348 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | 2-Integration Notification Condition Rules | 11/2/2020 |  |  | Kristen Flannery |  | h2 |  | Reports and Integrations
1349 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Integration Tags | 11/2/2020 |  |  | Kristen Flannery |  | hi |  | Reports and Integrations
1350 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | XSLT Attachment Transformation | 11/2/2020 |  |  | Kristen Flannery |  | hj |  | Reports and Integrations
1351 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Web Service Data Source | 11/2/2020 |  |  | Kristen Flannery |  | hk |  | Reports and Integrations
1352 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Integration Systems (Manual) | 11/2/2020 |  |  | Kristen Flannery |  | i |  | Reports and Integrations
1353 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Integration Systems (New) | 11/2/2020 |  |  | Kristen Flannery |  | i2 |  | Reports and Integrations
1354 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Integration System Users | 11/2/2020 |  |  | Kristen Flannery |  | j |  | Reports and Integrations
1355 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Template Model Condition Rules without Dependencies | 11/2/2020 |  |  | Kristen Flannery |  | k1 |  | Reports and Integrations
1356 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Template Model Condition Rules | 11/2/2020 |  |  | Kristen Flannery |  | k2 |  | Reports and Integrations
1357 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Template Models | 11/2/2020 |  |  | Kristen Flannery |  | k3 |  | Reports and Integrations
1358 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | EIB Definitions (Manual / Config Package) | 11/2/2020 |  |  | Lindsay Emer |  | l |  | Reports and Integrations
1359 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Subscriptions | 11/2/2020 |  |  | Kristen Flannery |  | m |  | Reports and Integrations
1360 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Scheduled Future Processes | 11/2/2020 |  |  | Kristen Flannery |  | n |  | Reports and Integrations
1361 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Reference IDs | 11/2/2020 |  |  | Kristen Flannery |  | o |  | Reports and Integrations
1362 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Update Tenant Setup - Payroll - for Continuous Pay Calculation Setup (for each tenant, except payroll testing tenant, post-refresh copy) | 11/2/2020 |  |  | Mel Roberts |  | n | d | Tenant | Pay Groups
1363 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Update Tenant Setup - Reporting - for Worker Indexing (for each tenant, post-refresh copy) | 11/2/2020 |  |  | Mel Roberts |  | n | e | Tenant | Worker Data Conversion Completed | 7/6 MR: Launched 'Create Trending Worker Data' task and validated the 'Maintain Trended Worker Data' basics were set up.
1366 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Inactivate Pay Calculations after Pay History validation | 11/2/2020 |  |  | Mel Roberts |  | d | ae | Payroll Calculations |  | E2E only on 12/6 -- Pay Compare when ready to calc Cycle 1
1367 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Review and Revise Custom Reports with Do Not Use items (fields, data sources, filters, prompts, etc.) and/or Deprecated Items | 11/2/2020 |  |  | Mel Roberts |  | d | af | Reports and Integrations
1368 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Review and Revise Dashboards with Security errors | 11/2/2020 |  |  | Mel Roberts |  | d | ag | Reports and Integrations
1369 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Tenant Analyzer, updated after inactivations and calculation updates | 11/2/2020 |  |  | Mel Roberts |  | d | ah | Payroll Calculations
1370 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Re-run all Exception Audits post-copy for Testing preparation | 11/2/2020 |  |  | Mel Roberts |  | d | ai | Reports and Integrations |  | 7/6 MR: Received confirmation from HCM and FIN teams that the results were shared and being addressed.
1371 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Re-run the Build FLSA Work Period Calendar Events process - Sunday-to-Saturday weeks, starting first week of pay history year | 11/2/2020 |  |  | Mel Roberts |  | d | aj | Payroll Calculations |  | 7/6 MR: Was re-run after initial pay calculation (would not stick until then)
1375 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Update Pay Groups with Corrected Ovverride First Processing Period after Pay History is Loaded | 11/2/2020 |  |  | Mel Roberts |  | zg | a | Pay Groups
1376 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Update Period Schedule with Time Tracking Eligibility Rule | 11/2/2020 |  |  | Mel Roberts |  | zg | b | Period Schedule
1377 | 3. Cutover | Gold Build | PAY | Configuration | Workday |  | Update Run Category with Updated PCGs | 11/2/2020 |  |  | Mel Roberts |  | zg | c | Run Category
1378 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | User-Based Groups without Dependencies (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | a1 | Configurable Security
1379 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | User-Based Groups (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | a2 | Configurable Security
1380 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Assignable Roles without Dependencies (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | b | Configurable Security
1381 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Role-Based Security Groups (Constrained) (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | ca | Configurable Security
1382 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Role-Based Security Groups (Unconstrained) (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | cb | Configurable Security
1383 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Job-Based Security Groups (Constrained) (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | da | Configurable Security
1384 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Job-Based Security Groups (Unconstrained) (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | db | Configurable Security
1385 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Organization-Based Security Groups (Constrained) (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | e1 | Configurable Security
1386 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Organization-Based Security Groups (Unconstrained) (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | e2 | Configurable Security
1387 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Location-Based Security Groups (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | f | Configurable Security
1388 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Compensation Level-Based Security Groups (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | g | Configurable Security
1389 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | 1-Integration System Security Groups (Constrained) (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | ha | Configurable Security
1390 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | 2-Integration System Security Groups (Unconstrained) (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | hb | Configurable Security
1391 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Intersection Security Groups (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | j | Configurable Security
1392 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Aggregation Security Groups (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | k | Configurable Security
1393 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Segment-Based Security Groups (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | l | Configurable Security
1394 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Assignable Roles (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | m | Configurable Security
1395 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Configure Domain Security Policies (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | na | Configurable Security
1396 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Business Process Security Policies (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | o | Configurable Security
1397 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Enable Functional Areas & Activate Pending Security Policy Changes (Update Load) | 11/2/2020 |  |  | Mel Roberts |  | i2 | p | Configurable Security
1399 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Verify Trended Workers Configuration for Tenants | 11/2/2020 |  |  | Mel Roberts |  | na | na | Reports and Integrations |  | 7/6 MR: Launched 'Create Trending Worker Data' task and validated the 'Maintain Trended Worker Data' basics were set up.
1400 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Migrate in 'Extract' custom reports | 11/2/2020 |  |  | Mel Roberts |  | na | na | Reports and Integrations
1401 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Migrate in 'Data Validation' custom reports | 11/2/2020 |  |  | Mel Roberts |  | na | na | Reports and Integrations
1402 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Migrate in custom reports for Worker Profile | 11/2/2020 |  |  | Mel Roberts |  | na | na | Reports and Integrations
1403 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Configure Worker Profile | 11/2/2020 |  |  | Mel Roberts |  | na | na | Reports and Integrations
1404 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Migrate in custom reports for Central Payroll dashboard | 11/2/2020 |  |  | Mel Roberts |  | na | na | Reports and Integrations
1405 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Migrate in custom reports for WSU Modernization dashboard | 11/2/2020 |  |  | Mel Roberts |  | na | na | Reports and Integrations
1406 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Configure Central Payroll dashboard | 11/2/2020 |  |  | Mel Roberts |  | na | na | Reports and Integrations
1407 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Configure WSU Modernization dashboard | 11/2/2020 |  |  | Mel Roberts |  | na | na | Reports and Integrations
1408 | 3. Cutover | Gold Build | TECH | Configuration | Workday |  | Configure Home Page | 11/2/2020 |  |  | Mel Roberts |  | na | na | Reports and Integrations
1419 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Edit Tenant Setup Global (Enable Western Script) | 11/2/2020 |  |  | Jim Broucek |  | na | na | Setup Data
| 3. Cutover | Gold Build | FIN | Configuration |  |  | Begin Loading FDM Values | 2020-11-03 |  | 2020-11-03
MPP | 3. Cutover |  | Security |  |  |  | Capture R2PM template updates for Supervisory Orgs/Academic Units | 2020-11-03 |  | 2020-11-05 | Stacy Combs, Lindsay Emer
MPP | 3. Cutover |  | Security |  |  |  | Capture R2PM template updates for updated FDM values | 2020-11-03 |  | 2020-11-05 | Stacy Combs, Lindsay Emer
77 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Pay Rate Types | 2020-11-04 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
93 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Job Profiles (without compensation info) | 2020-11-04 |  | 2020-11-20 | Jim Broucek |  | b | kd | Setup Data |  | First load without compensation info. Comp info will go in second load when comp is migrated.
129 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Job Classification Groups | 2020-11-04 |  | 2020-11-20 | Jim Broucek |  | a2 | e | Job Setup
130 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Workers Compensation Codes | 2020-11-04 |  | 2020-11-20 | Jim Broucek |  | a2 | f | Job Setup
131 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Job Families | 2020-11-04 |  | 2020-11-20 | Jim Broucek |  | a2 | g | Job Setup
132 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Job Family Groups | 2020-11-04 |  | 2020-11-20 | Jim Broucek |  | a2 | h | Job Setup
135 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Profiles | 2020-11-04 |  | 2020-11-20 | Jim Broucek |  | a2 | ja | Job Setup
136 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Job Profiles (with compensation info) | 2020-11-04 |  | 2020-11-20 | Jim Broucek |  | a2 | k | Job Setup |  | Will load once compensation grades have been built
139 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Work Shifts | 2020-11-04 |  | 2020-11-20 | Jim Broucek |  | a2 | m | Job Setup
145 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Maintain Employee Probation Period Types | 2020-11-04 |  | 2020-11-20 | Jim Broucek |  | a2 | ra | Job Setup
591 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Companies | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | b | j | Organizations
592 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Cost Center Hierarchies without Superiors | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | b | l | Organizations
593 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Cost Center Hierarchies | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | b | m | Organizations
594 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Cost Centers | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | b | n | Organizations
595 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Region Hierarchies without Superiors | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | b | o | Organizations
596 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Region Hierarchies | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | b | p | Organizations
597 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Regions | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | b | q | Organizations
598 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Custom Organizations without Dependencies | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | b | r | Organizations
599 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Custom Organizations | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | b | s | Organizations
602 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Fund Types | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | b | x | Organizations
603 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Funds | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | b | y | Organizations
604 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Fund Hierarchies | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | b | z | Organizations
607 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Programs | 2020-11-06 |  | 2020-11-20 | Wilson Ye |  | b | ac | Organizations
608 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Program Hierarchies | 2020-11-06 |  | 2020-11-20 | Wilson Ye |  | b | ad | Organizations
660 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Fiscal Schedules | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | e | a | Fiscal Schedules
661 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Fiscal Posting Intervals | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | e | b | Fiscal Schedules
662 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Fiscal Summary Schedules | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | e | c | Fiscal Schedules
663 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Fiscal Years | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | e | d | Fiscal Schedules
861 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Ledger Account Types | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | l | a | Ledger, Budget, and Journal Setup
862 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Ledger Types | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | l | b | Ledger, Budget, and Journal Setup
987 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Ledgers | 2020-11-06 |  | 2020-11-20 | Jodi Heins |  | s | a | Ledgers and Budgets
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Add Out of Country Location | 2020-11-09 |  | 2020-11-09 | Ed Nieskes, Kyle Babinski
| 3. Cutover | Gold Build | FIN | Configuration |  |  | Begin building files to load default/allowed worktags | 2020-11-09 |  | 2020-11-09 | Wilson Ye
| 3. Cutover | Gold Build | TECH | Conversion | Workday |  | Validation/Load of Location Hierarchies and Locations with Superior | 2020-11-09 |  | 2020-11-10 | Brigham Hubbard, Karl Riley, Jemima Joseph
| 3. Cutover | Gold Build | TECH | Conversion | Workday |  | Validation/Load of Supervisory Organizations and Supervisory Org with Superior | 2020-11-09 |  | 2020-11-10 | Wendy Weber,Brad Dudra, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Benefits | Workday |  | Take grandfathered "only in if already enrolled in" rule off Grandfathered plans. Take 'currently enrolled in' requirement off other plans to allow conversion enrollments. | 2020-11-09 |  | 2020-11-19 | Suraj Kolimi
| 3. Cutover | Gold Build | HCM | Benefits | Workday |  | Take off Cross Plan Dependency from HSA / CDHP plansake Ross plan depend | 2020-11-09 |  | 2020-11-19 | Suraj Kolimi
| 3. Cutover |  | HCM | Benefits |  |  | Train Benefits on Hoover templates for Delta Load Transactions | 2020-11-09 |  | 2020-11-19 | Wendy Weber
1156 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Worktag Balancing Configuration (Manual) | 2020-11-10 |  | 2020-11-20 | Jodi Heins |  | ag | c | Worktag Rules |  | Needs to be done before any transactions
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Worktag Balancing - Financial Rules (if necessary) | 2020-11-10 |  |  | Jodi Heins |  | ag | d | Worktag Rules
| 3. Cutover | Gold Build | HCM | Conversion | Legacy |  | Validate data between PayNet and HEPPS for sync pre-conversion file snapshot. (SEIB field) | 2020-11-11 |  | 2020-11-18 | Jay Maylor
32 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Localization Settings | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
33 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Optional Fields | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data | Security load | Not in migraton recipe; advanced load
53 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Document Categories | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | b | cg | Setup Data
59 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Address Components by Country | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data |  | Factory defaults already available in country load - only run ' Populate Recruiting Address Components' task
60 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Name Components by Country | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data |  | Factory defaults already available in country load - no action needed
72 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Recruiting Sources | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data |  | This is a Recruiting module item
76 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Background Check Statuses | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
91 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Questions | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data
92 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Questionnaires | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  |  |  | Setup Data |  | Used by BP' reference needs to be removed prior to load and then add back manually
113 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Committee Types | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | c | la | Organizations |  | Requirements added
116 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Committee Membership Types | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | c | ld | Organizations |  | Requirements added
117 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Committees | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | c | le | Organizations | Supervisory Organization load | Requirements added
224 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Prospect Statuses | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a4 | a | Recruiting Setup
225 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Prospect Types | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a4 | j | Recruiting Setup
226 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Recruiting Dispositions | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a4 | b | Recruiting Setup
227 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Background Check Packages | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a4 | e | Recruiting Setup |  | RAID item
230 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Candidate Tags | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a4 | e | Recruiting Setup |  | Not in migraton recipe; advanced load
237 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Assessment Statuses | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a4 | i | Recruiting Setup |  | Use 0 for boolean values where not required, else they get loaded
238 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Recruiting Assessment Tests | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a4 | i | Recruiting Setup
242 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | 1-Job Requisition Condition Rules without Dependencies | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a4 | i | Recruiting Setup |  | None
243 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | 2-Job Requisition Condition Rules | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a4 | i | Recruiting Setup |  | Advanced Load
249 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Interview Types | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a4 | i | Recruiting Setup |  | Not in migraton recipe; advanced load
250 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Job Application Templates | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a4 | m | Recruiting Setup |  | Update the default template's Ref ID in target tenant to be 'staff' template ref id as in source tenant
253 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Veteran Statuses | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a4 | p | Recruiting Setup
256 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Job Posting Template Content | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a4 | h | Recruiting Setup | Calculated fields | Manual
257 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Candidate List Assignments | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a4 | h | Recruiting Setup |  | OX
260 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Maintain Veteran Status Identification Form | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a5 | ca | Compliance Setup |  | Text comes over, but not the values - configure those manually
262 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Form I-9 Set Up | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a5 | d | Compliance Setup |  | External Form I-9 source values do not migrate; setup manually
263 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Form I-9 Set Up - Internal Audit Reason | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a5 | e | Compliance Setup
264 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Form I-9 Set Up - External Form I-9 Sources | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a5 | ce | Compliance Setup |  | iLoad
264 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Form I-9 Set Up - Internal Audit Conclusion | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a5 | f | Compliance Setup
265 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | External Disability Self Identification Record | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | a5 | h | Compliance Setup |  | No action for setup. This is worker level data, not setup
465 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Document Category Security Segments | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | i1 | a | Security Segments |  | Mel Roberts already loaded for UAT-WSU9
496 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Activate Pending Security Policy Changes (Manual) (Initial Load) | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | i2 | s | Configurable Security |  | Coordinate with Kristen Flannery and Akriti
497 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Onboarding Reasons | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | i3 | a | Onboarding
499 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Onboarding Setup Templates | 2020-11-11 |  | 2020-11-20 | Jim Broucek |  | i3 | c | Onboarding | BP load - onboarding setup
1372 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Job Posting Templates | 2020-11-11 |  |  | Jim Broucek |  | a4 | h | Recruiting Setup | Job Posting Template Content and Job Requisition Condition Rules | Manual
1373 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Maintain Veteran Statuses for Candidates | 2020-11-11 |  |  | Jim Broucek |  | a5 | ca | Compliance Setup |  | Values come over but not the text; be sure to include the website link in text
| 3. Cutover |  | TECH | Conversion |  |  | Create Confluence Gold Extract Reviews | 2020-11-12 | 8am | 2020-11-12 | Brant Schroeder
1420 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Configure Optional Fields (HCM BPs) | 2020-11-12 |  |  | Jim Broucek |  | na | na | Additional Configuration
1421 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Forms/Documents | 2020-11-12 |  |  | Jim Broucek |  | na | na | Additional Configuration
MPP | 3. Cutover |  | Security |  |  |  | AFO's return R2PM spreadsheets to the Security team | 2020-11-13 |  | 2020-11-13 | Stacy Combs, Lindsay Emer
543 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | 1-Academic Appointment Identifier Types | 2020-11-13 |  | 2020-11-20 | Shawn Ismail |  | n | a | Higher Education
544 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | 2-Academic Appointment Identifiers | 2020-11-13 |  | 2020-11-20 | Shawn Ismail |  | n | b | Higher Education
545 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Academic Rank Titles | 2020-11-13 |  | 2020-11-20 | Shawn Ismail |  | n | c | Higher Education
546 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Academic Tenure Statuses | 2020-11-13 |  | 2020-11-20 | Shawn Ismail |  | n | d | Higher Education
547 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Academic Track Type Categories | 2020-11-13 |  | 2020-11-20 | Shawn Ismail |  | n | e | Higher Education
548 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Academic Track Type Category Groups | 2020-11-13 |  | 2020-11-20 | Shawn Ismail |  | n | f | Higher Education
549 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Academic Track Types | 2020-11-13 |  | 2020-11-20 | Shawn Ismail |  | n | g | Higher Education
551 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Maintain Academic Periods | 2020-11-13 |  | 2020-11-20 | Shawn Ismail |  | n | i | Higher Education
555 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Academic Unit Subtypes | 2020-11-13 |  | 2020-11-20 | Shawn Ismail |  | n | m | Higher Education
556 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Academic Units | 2020-11-13 |  | 2020-11-20 | Shawn Ismail |  | n | n | Higher Education |  | <SI 2/19> As per my conversation with Wendy, will wait for feedback from Provost Office, Deans, and units before building AUHs/AUs.Expecting an update from Wendy the early part of the week of 2/24.
557 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Academic Unit Hierarchies | 2020-11-13 |  | 2020-11-20 | Shawn Ismail |  | n | o | Higher Education |  | <SI 2/19> As per my conversation with Wendy, will wait for feedback from Provost Office, Deans, and units before building AUHs/AUs.Expecting an update from Wendy the early part of the week of 2/24.
560 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Work Status Rule Sets | 2020-11-13 |  | 2020-11-20 | Shawn Ismail |  | n | qb | Higher Education
| 3. Cutover |  | FIN | Expenses | Legacy |  | Remove ability to create new TEVs and remove ability to route TEVs to Travel Services. | 2020-11-15 |  | 2020-11-15 | Allyson Comstock,Karen Kellerman | [5 empty] | Travel Expense Voucher (TEV)
| 3. Cutover | Gold Build | HCM | Benefits |  |  | Identify additional Benefits eligibility overrides and add to EIB (LWOP, multiple positions, federal employees, whitcom, fall-outs) | 2020-11-15 |  | 2020-11-23 | Steven Perkins
| 3. Cutover | Manual - EIB | HCM | Benefits | Workday |  | Identify people in "Enrollment Window" and add to EIB to update their Retirement plans for "pre-choice" coded plans. | 2020-11-15 |  | 2020-12-15 | Wendy Weber
| 3. Cutover | Soft Freeze/Hard Freeze | FIN | Awards | Legacy |  | Award Setups/Closures | 2020-11-15 |  | 2020-12-18 | Departments/ ORSO/SPS | [5 empty] | Grants that are termed before 12/31/2020 prioritized for closure
| 3. Cutover | Soft Freeze/Hard Freeze | FIN | Awards/General Accounting | Legacy |  | FACTS - Updates/Changes | 2020-11-15 |  | 2020-12-18 | Chris Conway
| 3. Cutover | Gold Build | TECH | Conversion |  |  | Check for hard coded dates for go-live impacts for 12/16/2020 | 2020-11-16 |  | 2020-11-19 | Brad Dudra, Keerthinath Manoharan, Jemima Joseph, Karl Riley
| 3. Cutover | Conversion | HCM | Benefits |  |  | Build Semester By Semester, 70/5/12, Min 8, Seasonal, Survivor Annuity Option and DRS Employment Override Code files | 2020-11-16 |  | 2020-11-20 | Steven Perkins
| 3. Cutover |  | HCM | Benefits |  |  | Pull and merge Date of Death File (S drive and HEPPS data) | 2020-11-16 |  | 2020-11-20 | Steven Perkins
| 3. Cutover | Critical Date | PMO |  | Workday |  | Open Workday Case to Move Gold to Production in partner center - Forms signed by WSU 14 days prior to go-live (duration of MTP in Portland) | 2020-11-18 |  | 2020-11-18 | David Boeker
| 3. Cutover |  | HCM | Benefits |  |  | Check CBFLE-Retirement for blanks (based on aging out) add to supplemental file. Ages will have to be adjusted for conversion. | 2020-11-18 |  | 2020-11-20 | Wendy Weber
| 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Disable Phone Validation on the tenant (Edit Tenant Setup - Global) | 2020-11-18 |  | 2020-11-20 | Kyle Babinski
| 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Disable Postal Code validation on the tenant (Edit Tenant Setup - System) | 2020-11-18 |  | 2020-11-20 | Kyle Babinski
| 3. Cutover |  | Security |  |  |  | Transform the HCM/Finance/Central spreadsheets | 2020-11-18 |  | 2020-11-20 | Tom Woods, Wendy Weber
MPP | 3. Cutover | Production Readiness | Operating Committee |  |  |  | Gate 2 - Prior to Gold Conversion | 2020-11-19 |  | 2020-11-19 | Jay Dumphy, Jennifer Klein, Joy Morton, Mike Corwin
| 3. Cutover | Gold Build | TECH | Conversion |  |  | Notify Deloitte implementers that the build is starting - Config/BP testing needs to be completed before copy to WSU5 | 2020-11-19 |  | 2020-11-19 | Jane Thomas, Mel Roberts, Kyle Babinski, Ed Nieskes
| 3. Cutover | Gold Build | HCM/Payroll/FIN | Configuration | Workday |  | Verify setups are complete for HCM, Payroll and Finance prior to conversion | 2020-11-19 |  | 2020-11-20 | Ed Nieskes, Kyle Babinski
70 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | 2-Compensation Elements and Groups | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  |  |  | Compensation
78 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Business Asset Disposal Types | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  |  |  | Setup Data
277 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Compensation Grades | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | c | ea | Compensation
278 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Compensation Grade Hierarchies | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | c | eb | Compensation
285 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | One-Time Payment Plans | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | c | k | Compensation
287 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Compensation Plans | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | c | m | Compensation
288 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Compensation Packages | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | c | n | Compensation
290 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | 2-Compensation Eligibility Rules | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | c | o2 | Compensation
300 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Compensation Review Participation Rules | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | c | w | Compensation
303 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Period Activity Units | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | c | ya | Compensation
304 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Period Activity Categories | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | c | yb | Compensation
305 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Period Activity Tasks | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | c | yc | Compensation
306 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Period Activities | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | c | yd | Compensation
307 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Period Activity Rate Matrices | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | c | ye | Compensation
308 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Merit Statement Rules | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | c | z | Compensation |  | <SI 7/6> - This task is dependent on the merit statement, which is currently being developed, and cannot be completed until the merit statement is available.
368 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Off Types | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | a | Absence Setup Data
370 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Balance Periods | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | c | Absence Setup Data
371 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Off Unit of Time Conversion Calculations | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | ca | Absence Setup Data | Generic Calcs | Need generic calcs in before I can do this
372 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Offs | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | d | Absence Setup Data |  | used iLoad when Advanced Load would only fail
373 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Absence Accruals | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | e | Absence Setup Data
374 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Off Plans | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | f | Absence Setup Data |  | used iLoad when Advanced Load would only fail
375 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Absence Balances | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | g | Absence Setup Data
377 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Leave of Absence Rules | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | h2 | Absence Setup Data
378 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Leave Reasons | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | h3 | Absence Setup Data
379 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Leave of Absence Families | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | i | Absence Setup Data
381 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Calendar Rules | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | j2 | Absence Setup Data | Employees loaded
382 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Holiday Calendars | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | k | Absence Setup Data
383 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Work Schedule Calendars | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | k | Absence Setup Data
384 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Work Schedule Calendar Groups | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | k | Absence Setup Data
385 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Configure Absence Type Groups | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | k | Absence Setup Data
386 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Leave Type Security Segments | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | k | Absence Setup Data
387 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Team Absence Calendar | 2020-11-20 |  | 2020-11-20 | Sydney MacBain |  | f1 | k | Absence Setup Data
552 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Academic Pay Periods | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | n | j | Higher Education
553 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Academic Pay Eligibility | 2020-11-20 |  | 2020-11-20 | Shawn Ismail |  | n | k | Higher Education |  | Job Family tie (Shawn Ismail, Kyle Babinski, Mel Roberts)
568 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Unit of Measure Dimensions | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | a | c | Setup Data
569 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Units of Measure | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | a | d | Setup Data | Unit of Measure Dimensions
570 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Item Identifier Type | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | a | e | Setup Data
572 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Spend Transaction Instructions | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | a | g | Setup Data
577 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Financial Messages | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | a | o | Setup Data
579 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Hierarchy Levels | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | a | q | Setup Data
581 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | 1099 MISC and 1042-S Withhold Mapping | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | a | v | Setup Data | Tax Authorities
585 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Enable Custom Worktags | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | a | z | Setup Data
588 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Organization Types without Dependencies | 2020-11-20 |  | 2020-11-20 | Mel Roberts |  | b | a | Organizations
589 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Organization Types | 2020-11-20 |  | 2020-11-20 | Mel Roberts |  | b | b | Organizations
590 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Organization Subtypes | 2020-11-20 |  | 2020-11-20 | Mel Roberts |  | b | c | Organizations
609 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Object Class Sets | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | b | ae | Organizations
664 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Aging Groups | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | e | a | Payment Information
666 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Payment Terms | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | f | e | Payment Information
667 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Payment Types | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | f | f | Payment Information
671 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Tax Applicability | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | f | j | Payment Information
672 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Invoice Adjustment Reasons | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | f | k | Payment Information
673 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Receivable Writeoff Reasons | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | f | l | Payment Information
675 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Payment Handling Instructions | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | f | n | Payment Information
676 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Customer Categories | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | a | Customer and Supplier Setup
678 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Reasons for Customer Status Change | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | c | Customer and Supplier Setup
679 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Customer Statement Print Layouts | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | d | Customer and Supplier Setup |  | BIRT
681 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Consolidated Customer Invoice Print Layouts | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | f | Customer and Supplier Setup |  | BIRT
682 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Contract Amendment Types | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | g | Customer and Supplier Setup
683 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Customer Contract Types | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | h | Customer and Supplier Setup
686 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Schedule Types | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | k | Customer and Supplier Setup
688 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Invoice Types | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | m | Customer and Supplier Setup
689 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Billing Cycles | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | n | Customer and Supplier Setup
690 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Dispute Reasons | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | o | Customer and Supplier Setup
691 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Collection Codes | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | p | Customer and Supplier Setup
692 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Customer Payment Application Reasons | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | q | Customer and Supplier Setup
693 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | 1-Customer Payment Application Condition Rules without Dependencies | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | r | Customer and Supplier Setup
694 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | 2-Customer Payment Application Condition Rules | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | s | Customer and Supplier Setup
695 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | 3-Customer Payment Application Rules | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | t | Customer and Supplier Setup
696 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | 4-Customer Payment Application Rule Sets | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g | u | Customer and Supplier Setup
697 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Categories | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | v | Customer and Supplier Setup
698 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Groups | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | w | Customer and Supplier Setup
699 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Reasons for Supplier Status Change | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | x | Customer and Supplier Setup
700 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Request for Quote Types | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | y | Customer and Supplier Setup
701 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Request for Quote Print Layouts | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | z | Customer and Supplier Setup
702 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Request for Quote Award Reasons | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | aa | Customer and Supplier Setup
703 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Contract Types | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | ab | Customer and Supplier Setup
704 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Contract Print Layouts | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | ac | Customer and Supplier Setup
705 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Requisition Types | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | ad | Customer and Supplier Setup
707 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Purchase Order Print Layouts | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | af | Customer and Supplier Setup
708 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Return Reasons | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | ag | Customer and Supplier Setup
709 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Accounts Match Exception Reasons | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | ah | Customer and Supplier Setup
710 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | 1-Supplier Accounts Match Condition Rules without Dependencies | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | ai | Customer and Supplier Setup
711 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | 2-Supplier Accounts Match Condition Rules | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | aj | Customer and Supplier Setup
712 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Accounts Match Rules | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | ak | Customer and Supplier Setup
713 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Accounts Match Rule Sets | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | al | Customer and Supplier Setup
714 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Accounts Match Override Reasons | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | am | Customer and Supplier Setup
715 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Shipping Terms | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | an | Customer and Supplier Setup
716 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Shipping Methods | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | g | ao | Customer and Supplier Setup
719 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Customers without Dependencies | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g1 | b | Customers |  | Conversion Item Sept 6
720 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Customers | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g1 | c | Customers |  | Conversion Item Sept 6
721 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Customer Invoice Business Form Layout Rules | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g1 | d | Customers |  | Conversion - BIRT
724 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Customer Contracts | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g1 | f | Customers |  | Conversion Item Sept 6
728 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Customer Contracts Amendment | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | g1 | j | Customers |  | Conversion Item
732 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Asset Types | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | h | a | Item and Asset Setup
733 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Asset Classes | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | h | b | Item and Asset Setup
734 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Depreciation Profiles | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | h | c | Item and Asset Setup
735 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Revenue Categories | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | h | d | Item and Asset Setup
736 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Revenue Category Hierarchies | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | h | e | Item and Asset Setup
737 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Sales Item Groups | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | h | f | Item and Asset Setup
738 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Sales Items | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | h | g | Item and Asset Setup
739 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Spend Categories | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | h | h | Item and Asset Setup | Tax Applicability, Asset Type, Asset Class
740 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Spend Category Hierarchies | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | h | i | Item and Asset Setup
743 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Expense Item Groups | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | h | l | Item and Asset Setup
744 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Expense Policy Groups | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | h | m | Item and Asset Setup
745 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Expense Rate Table Rules without Dependencies | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | h | n | Item and Asset Setup
746 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Expense Rate Table Rules | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | h | o | Item and Asset Setup
748 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Expense Items | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | h | q | Item and Asset Setup
750 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Business Purposes for Expense Reports | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | h | s | Item and Asset Setup
752 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Expense Report Print Layouts | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | h | u | Item and Asset Setup
753 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Asset Pooling Rules | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | h | v | Item and Asset Setup
754 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Asset Cost Adjustment Reasons | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | h | w | Item and Asset Setup
755 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Asset Impairment Reasons | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | h | x | Item and Asset Setup
756 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Asset Disposal Types | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | h | y | Item and Asset Setup
757 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Asset Removal Reasons | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | h | z | Item and Asset Setup
762 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Financial Institutions | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | a | Banking
763 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Check Print Layouts | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | b | Banking
764 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Tenant Default Check Print Layouts | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | c | Banking
766 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Settlement Run Custom Filters | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | e | Banking
771 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Ad Hoc Bank Transaction Purposes | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | j | Banking
772 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Ad Hoc Bank Transaction Templates | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | k | Banking |  | Dependency on FDM loaded
773 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Bank Reconciliation Reasons | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | l | Banking
777 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | First Notice Condition Rules | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | p | Banking
778 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Matching Rule Sets | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | q | Banking
779 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | First Notice Item Rules | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | r | Banking
781 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Bank Accounts | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | t | Banking
791 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Bank Statement Custom Code Sets | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | ad | Banking |  | WSU does not use this according to current knowledge
792 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Bank Fee Service Codes | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | ae | Banking
793 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Signature Methods | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | af | Banking
794 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Authority Types | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | ag | Banking
795 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Signers | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | ah | Banking | Hires | Douglas Wilcox, Nancy Youlden and Danielle Hess all not in system.
796 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Signatories | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | ai | Banking | Hires | Douglas Wilcox, Nancy Youlden and Danielle Hess all not in system. Not able to add signatories for investement accounts
797 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Check Print Layouts with Report Design | 2020-11-20 |  | 2020-11-20 | Mel Roberts |  | i | aj | Banking | Business Form Layouts
798 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Bank Routing Rules | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | i | ak | Banking
799 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Investment Pools | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | j | a | Endowments
800 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Gift Purpose Types | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | j | b | Endowments
801 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Gift Purposes | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | j | c | Endowments
802 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Gift Types | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | j | d | Endowments
803 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Release Levels | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | j | e | Endowments
804 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Restricted By Values | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | j | f | Endowments
805 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Honorarium Types | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | j | g | Endowments
806 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Originations | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | j | h | Endowments
809 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Gift Hierarchies | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | j | k | Endowments
810 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Donor Types | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | j | l | Endowments
824 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Investment Statement Line Types | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | j | z | Endowments
825 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Investment Profiles | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | j | aa | Endowments
829 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | 1099 Categories | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | k | a | Tax Setup
830 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Tax Categories | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | k | b | Tax Setup
831 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | 1099 and 1096 Print Form Layouts | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | k | c | Tax Setup |  | Default
832 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Tax Authorities | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | k | d | Tax Setup
833 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Tax Rates | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | k | e | Tax Setup
834 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Tax Codes | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | k | f | Tax Setup
835 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Withholding Tax Rates | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | k | h | Tax Setup
836 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Transaction Tax Rates | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | k | i | Tax Setup | Tax Applicability, Tax Authorities
837 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Transaction Tax Codes | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | k | j | Tax Setup
838 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Withholding Tax Codes | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | k | k | Tax Setup
859 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Tax Recoverability Objects | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | k | af | Tax Setup | Tax Applicability
863 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Budget Entry Types | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | l | c | Ledger, Budget, and Journal Setup
864 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Budget Amendment Types | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | l | d | Ledger, Budget, and Journal Setup
865 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Budget Structures | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | l | e | Ledger, Budget, and Journal Setup
866 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Journal Sources | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | l | f | Ledger, Budget, and Journal Setup
867 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Journal Source Mapping to Operational Transactions | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | l | g | Ledger, Budget, and Journal Setup
868 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Book Codes | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | l | h | Ledger, Budget, and Journal Setup
869 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Books | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | l | i | Ledger, Budget, and Journal Setup
870 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Integration Worktag Mapping Source System | 2020-11-20 |  | 2020-11-20 | Kristen Flannery |  | l | j | Ledger, Budget, and Journal Setup
871 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Integration Worktag Mapping | 2020-11-20 |  | 2020-11-20 | Kristen Flannery |  | l | k | Ledger, Budget, and Journal Setup
873 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Asset Books | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | m | a | Asset Accounting
874 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Asset Book Rules | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | m | b | Asset Accounting
875 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Company Asset Books | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | m | c | Asset Accounting
878 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Account Sets | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | n | b | Financial Accounting Setup |  | Need ledger accounts
879 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Account Control Rule Sets | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | n | c | Financial Accounting Setup |  | Need to go back and adjust after conversion loads
880 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Account Posting Rule Sets | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | n | d | Financial Accounting Setup |  | Need ledger accounts
881 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Year End Closing Rules | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | n | j | Financial Accounting Setup |  | Need ledger accounts
882 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | 1-Ledger Account Summaries without Dependencies | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | n | l | Financial Accounting Setup |  | Need ledger accounts
883 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | 2-Ledger Account Summaries | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | n | m | Financial Accounting Setup |  | Need ledger accounts
884 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | 3-Ledger Account Summaries with Ordered Dependencies | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | n | n | Financial Accounting Setup |  | Need ledger accounts
899 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Sequence Generator Rule Configuration | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | n | af | Financial Accounting Setup
901 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Custom Worktags | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | o | b | Custom Worktags
905 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Gifts | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | o | h | Custom Worktags |  | Conversion item loaded via Hoover
909 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Worktag Usages | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | o | l | Custom Worktags
910 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Customers without Dependencies | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | p | b | Customers, Suppliers, and Payees
911 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Customers | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | p | c | Customers, Suppliers, and Payees
912 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Submit Customer | 2020-11-20 |  | 2020-11-20 | Gurparshad |  | p | d | Customers, Suppliers, and Payees
923 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Suppliers | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | p | s | Customers, Suppliers, and Payees |  | Conversion Item
938 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Success Ratings | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | q | d | Projects, Work, and Business Assets
939 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Importance Ratings | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | q | e | Projects, Work, and Business Assets
942 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Work Priorities | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | q | h | Projects, Work, and Business Assets
944 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Risk Severities | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | q | j | Projects, Work, and Business Assets
945 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Risk Statuses | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | q | k | Projects, Work, and Business Assets
949 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Project Hierarchies | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | q | o | Projects, Work, and Business Assets
950 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Project Hierarchy Configurations | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | q | p | Projects, Work, and Business Assets
960 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Projects without Dependencies | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | q | z | Projects, Work, and Business Assets
961 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Projects | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | q | aa | Projects, Work, and Business Assets
967 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Project Risks | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | q | ag | Projects, Work, and Business Assets
975 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Update Asset Depreciation Schedules | 2020-11-20 |  | 2020-11-20 | Wilson Ye |  | q | aq | Projects, Work, and Business Assets
989 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Budget Templates | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | s | c | Ledgers and Budgets
992 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Budget Treatment Rules | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | s | f | Ledgers and Budgets |  | Review with Ed and Chris
994 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Allocation Definitions | 2020-11-20 |  | 2020-11-20 | Paulo |  | t | b | Allocations |  | One allocation definition (Gift Fee) is dependent on loading Gift custom worktag
996 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Allocation Group Sets | 2020-11-20 |  | 2020-11-20 | Paulo |  | t | d | Allocations
997 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Allocation Group Set Dependencies | 2020-11-20 |  | 2020-11-20 | Paulo |  | t | e | Allocations
998 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Financial Condition Rule | 2020-11-20 |  | 2020-11-20 | Paulo |  | t | f | Allocations
1017 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Worktag Type Precedence Configuration | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | v | h | Custom Validations and Worktag Rules
1027 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Corporate Credit Card Accounts | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | y | b | Worker Expense Preferences and Credit Cards |  | Follow up with Kristin 2/22
1033 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Effort Certification Reason Change Codes | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | a | Effort Certification and Grants
1034 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | 2-Effort Certification Eligibility Rules | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | b | Effort Certification and Grants
1035 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Effort Certifying Text | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | c | Effort Certification and Grants
1036 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Effort Certification Types | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | d | Effort Certification and Grants
1037 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | F&A Cost Basis Types | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | e | Effort Certification and Grants
1038 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | F&A Revenue Allocation Profiles | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | f | Effort Certification and Grants
1039 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | F&A Cost Rate Definition Locations | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | g | Effort Certification and Grants
1040 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | F&A Cost Rate Type Types | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | h | Effort Certification and Grants
1041 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | F&A Cost Rate Definition Names | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | i | Effort Certification and Grants
1042 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | F&A Rate Agreements | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | j | Effort Certification and Grants
1043 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | F&A Waived Expense Allocation Profiles | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | k | Effort Certification and Grants |  | Need FDM values to fully configure
1044 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | F&A Exceptions | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | l | Effort Certification and Grants
1045 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | F&A Object Class Mapping | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | m | Effort Certification and Grants
1046 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Catalog of Federal Domestic Assistance | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | n | Effort Certification and Grants
1047 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Spend Restrictions | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | o | Effort Certification and Grants
1048 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Amendment Reasons | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | p | Effort Certification and Grants
1049 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Purpose Codes | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | q | Effort Certification and Grants
1050 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Sponsor Award Types | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | r | Effort Certification and Grants
1051 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Sponsor Types | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | s | Effort Certification and Grants
1054 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Posting Interval Groups | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | v | Effort Certification and Grants
1056 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Summary Schedules | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | x | Effort Certification and Grants
1058 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Personnel Responsibilities | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | z | Effort Certification and Grants
1059 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Group | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | aa | Effort Certification and Grants
1060 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Lifecycle Statuses | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | ad | Effort Certification and Grants
1061 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | NSF Codes | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | ag | Effort Certification and Grants
1063 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Task Types and Groups | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | ai | Effort Certification and Grants
1064 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Task Statuses | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | aj | Effort Certification and Grants
1067 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Special Condition Types | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | am | Effort Certification and Grants
1068 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Attachment Categories | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | an | Effort Certification and Grants
1073 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Contact Types | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | as | Effort Certification and Grants
1074 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Salary Caps | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | at | Effort Certification and Grants |  | Requires pay component groups to be loaded first
1075 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Task List Templates | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | au | Effort Certification and Grants
1076 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Salary Over The Cap Type | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | av | Effort Certification and Grants
1077 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Lifecycle Status Update Rules | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | z | aw | Effort Certification and Grants
1082 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Sequence Generators | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | ac | e | Tenant
1093 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Tenant Setup - Financials | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | ac | p | Tenant
1103 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Receivables Aging Worklet Configuration | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | ac | z | Tenant
1125 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Duplicate Supplier Taxpayer ID Number Report (Manual) | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | ad | v | Audit Reports |  | Report migrated
1126 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | 1099 MISC Audit Report (Manual) | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | ad | w | Audit Reports |  | Report migrated
1128 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Audit Awards With Invalid Object Class Set Configuration (Manual) | 2020-11-20 |  | 2020-11-20 | Nigel Chong-You |  | ad | y | Audit Reports
1131 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Payment Card Industry Password Rules | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | ae | b | Deployment |  | Default
1155 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Worktag Balancing Transaction Rule Sets | 2020-11-20 |  | 2020-11-20 | Jodi Heins |  | ag | b | Worktag Rules
| 3. Cutover | Critical Date | TECH | Conversion |  |  | Begin Conversion Activities | 2020-11-20 |  | 2020-11-20 | Brant Schroeder, Jane Thomas
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse |  | Delete all extracts in the UAT folder on SFTP and Archive | 2020-11-20 | 5pm | 2020-11-20 | Brad Dudra
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse |  | Delete DUMPY check sum | 2020-11-20 | 5pm | 2020-11-20 | Brad Dudra
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse |  | Gold Data Warehouse build | 2020-11-20 |  | 2020-11-20 | Brant Schroeder, Jane Thomas
| 3. Cutover | Critical Date | TECH | Conversion | Gold Data Warehouse |  | HEPPS SnapShot Date (anything needed for the 1/11/2021 check will have to be caught up via Delta Loads or Manual Entries (Hoover, EIB or UI) following this date) | 2020-11-20 |  | 2020-11-20 | Brant Schroeder, Jane Thomas
| 3. Cutover |  | FIN | Expenses | Legacy |  | Travel expense vouchers approved by Travel Services by 11/20/2020. | 2020-11-20 |  | 2020-11-20 | Jodi Heins
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Classifications | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  |  |  | Customer and Supplier Setup
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Purchase Order Types | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  | f | ia | Customer and Supplier Setup
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Procurement Close Reasons | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  |  |  | Customer and Supplier Setup
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Miscellaneous Payment Categories | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  |  |  | Customer and Supplier Setup
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Miscellaneous Payee Categories | 2020-11-20 |  | 2020-11-20 | Lindsay Emer |  |  |  | Customer and Supplier Setup
| 3. Cutover | Soft Freeze/Hard Freeze | FIN | Business Assets | Legacy |  | Cutoff for preassigned inventory tag numbers | 2020-11-20 |  | 2020-12-04 | George Rhodes/Clint McGregor | [5 empty] | CPM: Preliminary estimated date
| 3. Cutover | Soft Freeze/Hard Freeze | FIN | Awards | Legacy |  | Enter Payroll/Cost Share and Allocations Information | 2020-11-20 |  | 2020-12-04 | Grant Managers
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Compensation | Legacy |  | Update Employee Compensation | 2020-11-20 |  | 2020-12-04 | Joe Wagner
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Core HR | Legacy |  | Change Personal Information | 2020-11-20 |  | 2020-12-04 | Jim Lowery
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Core HR | Legacy |  | Contract Contingent Worker | 2020-11-20 |  | 2020-12-04 | Jim Lowery
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Core HR | Legacy |  | Terminate Employee | 2020-11-20 |  | 2020-12-04 | Jim Lowery
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Core HR | Legacy |  | Add Academic Appointment | 2020-11-20 |  | 2020-12-04 | Jim Lowery
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Core HR | Legacy |  | Appointment Changes in HEPPS | 2020-11-20 |  | 2020-12-04 | HRS
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Core HR | Legacy |  | Change Contact Information | 2020-11-20 |  | 2020-12-04 | Jim Lowery
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Core HR | Legacy |  | Change Government ID | 2020-11-20 |  | 2020-12-04 | Jim Lowery
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Core HR | Legacy |  | Create/Edit Named Professorship (coordinate with Gifts) | 2020-11-20 |  | 2020-12-04 | Sabrina McPherson
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Core HR | Legacy |  | Edit Position | 2020-11-20 |  | 2020-12-04 | Jim Lowery
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Core HR | Legacy |  | End Additional Job/Academic Appointments | 2020-11-20 |  | 2020-12-04 | Jim Lowery
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Core HR | Legacy |  | End Contract Contingent Worker Contract | 2020-11-20 |  | 2020-12-04 | Jim Lowery
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Core HR | Legacy |  | Enter hires into AIS | 2020-11-20 |  | 2020-12-04 | Lisa Neal
| 3. Cutover | Communication | Payroll | Payroll | Legacy |  | Communicate Costing Allocations, Position Control Entries, Retro Costing Allocations | 2020-11-20 |  | 2020-12-04 | Annie Riedinger, Emily Bailes | [5 empty] | Must have communication by last half of September for department
| 3. Cutover | Soft Freeze/Hard Freeze | Payroll | Payroll | Legacy |  | Last HEPPS update in Legacy will be Dec 4, 2020, any accounting adjustments need to be in to position control/payroll before this date | 2020-11-20 |  | 2020-12-04 | Kim Lawton, Karen Wuestney | [5 empty] | BH: This will need to align with the last conversion.
| 3. Cutover | Communication | Payroll | Payroll | Legacy |  | Payroll Costing Allocations > 12/04/2020 will NOT be converted | 2020-11-20 |  | 2020-12-04 | Annie Riedinger, Emily Bailes | [5 empty] | Must have communication by last half of September for department
| 3. Cutover | Soft Freeze/Hard Freeze | Payroll | Payroll | Legacy |  | Change elective deductions (CougTechnical, UREC, Parking should be low volume) | 2020-11-20 |  | 2020-12-04 | Kim Lawton | [5 empty] | BH: This will need to align with the last conversion. All elective deductions after last snapshot will need to be loaded using a catch-up load
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Recruiting | Legacy |  | Close OPDRS postings from job sites - open until filled | 2020-11-20 |  | 2020-12-11 | Sabrina McPherson, Jon Hurd
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Recruiting | Legacy |  | Complete (fill or cancel) recruitment efforts within OPDRS | 2020-11-20 |  | 2020-12-11 | Sabrina McPherson, Jon Hurd
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Recruiting | Legacy |  | Last day to allow OPDRS postings | 2020-11-20 |  | 2020-12-13 | Sabrina McPherson, Jon Hurd
| 3. Cutover | Manual - UI or EIB | HCM | Core HR | Legacy |  | Log job change transactions into template (EIB or UI) | 2020-11-20 |  | 2020-12-15 | Central HR, Lisa Neal
| 3. Cutover | Communication | HCM | Core HR | Legacy | Freeze system | Remove access to Departments, i.e. TEMPS | 2020-11-20 |  | 2020-12-15 | Lisa Neal, Jay Maylor, Karl Riley
| 3. Cutover | Soft Freeze/Hard Freeze | Payroll | Payroll | Legacy | Follow up with a report out of MyWSU | Change Name, SSN, Date of Birth - entered into MyWSU | 2020-11-20 |  | 2020-12-15 | Kim Lawton, Justin Hughes | [5 empty] | BH: No conversion of data because it does not exist in AIS. This will be a Manual Entry - UI into Workday. Track name changes from 11/20 - 12/15
| 3. Cutover | Manual - UI | FIN | Business Assets | Legacy |  | Capture legacy asset modifications | 2020-11-20 |  | 2020-12-23 | George Rhodes/Clint McGregor
1208 | 3. Cutover | Gold Build | Fin | Configuration | Workday |  | Check Print Layouts (review with Financials) | 2020-11-20 |  |  | Wilson Ye |  | h3 | aa | Banking
1209 | 3. Cutover | Gold Build | Fin | Configuration | Workday |  | Tenant Default Check Print Layout (review with Financials) | 2020-11-20 |  |  | Wilson Ye |  | h3 | ab | Banking
1210 | 3. Cutover | Gold Build | Fin | Configuration | Workday |  | Check Print Layouts with Report Design (review with Financials) | 2020-11-20 |  |  | Wilson Ye |  | h3 | ac | Banking
1211 | 3. Cutover | Gold Build | Fin | Configuration | Workday |  | Financial Institutions (review with Financials) | 2020-11-20 |  |  | Wilson Ye |  | h3 | b | Banking
1213 | 3. Cutover | Gold Build | Fin | Configuration | Workday |  | Bank Accounts (review with Financials) | 2020-11-20 |  |  | Wilson Ye |  | h3 | d | Banking | Financial Institutions
1214 | 3. Cutover | Gold Build | Fin | Configuration | Workday |  | Bank Routing Rules (review with Financials) | 2020-11-20 |  |  | Wilson Ye |  | h3 | e | Banking | Companies
1292 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Custom Object for Intermittent leave | 2020-11-20 |  |  | Sydney MacBain |  | f1 | k | Absence Setup Data
1294 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | EIB for Accrual /Override adjustments | 2020-11-20 |  |  | Sydney MacBain |  | f1 | k | Absence Setup Data
1295 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | EIB for Time Off Plan Overrides | 2020-11-20 |  |  | Sydney MacBain |  | f1 | k | Absence Setup Data
1297 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Work Shifts | 2020-11-20 |  |  | Sydney MacBain |  | f1 | k | Absence Setup Data | HCM Positions load
1298 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Questionnaires | 2020-11-20 |  |  | Sydney MacBain |  | f1 | k | Absence Setup Data |  | Completed by Praveen in USI
1299 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | 2-Time Tracking Eligibility Rules | 2020-11-20 |  |  | Sydney MacBain |  | e | a2 | Time Tracking Setup Data
1299 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | EIB For Time Off Events | 2020-11-20 |  |  | Sydney MacBain |  | f1 | k | Absence Setup Data
1300 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Calculation Tags | 2020-11-20 |  |  | Sydney MacBain |  | e | b | Time Tracking Setup Data
1301 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Code Groups | 2020-11-20 |  |  | Sydney MacBain |  | e | c | Time Tracking Setup Data
1302 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Entry Codes | 2020-11-20 |  |  | Sydney MacBain |  | e | d | Time Tracking Setup Data
1303 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Tracking Submit Texts | 2020-11-20 |  |  | Sydney MacBain |  | e | e | Time Tracking Setup Data
1304 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Entry Templates | 2020-11-20 |  |  | Sydney MacBain |  | e | f | Time Tracking Setup Data
1305 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Calculation Groups | 2020-11-20 |  |  | Sydney MacBain |  | e | g | Time Tracking Setup Data
1306 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Calculations | 2020-11-20 |  |  | Sydney MacBain |  | e | h | Time Tracking Setup Data
1309 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Entry Validations | 2020-11-20 |  |  | Sydney MacBain |  | e | j2 | Time Tracking Setup Data
1310 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Time Manager Approval Setups | 2020-11-20 |  |  | Sydney MacBain |  | e | m | Time Tracking Setup Data
1312 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Overtime Request Codes | 2020-11-20 |  |  | Sydney MacBain |  | e | o | Time Tracking Setup Data
1315 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Alert Rules without Dependencies | 2020-11-20 |  |  | Sydney MacBain |  | k | da1 | Deployment
1316 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Alert Rules | 2020-11-20 |  |  | Sydney MacBain |  | k | da2 | Deployment
1317 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Alerts | 2020-11-20 |  |  | Sydney MacBain |  | k | db | Deployment
1374 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Receivables Overpayment Reasons | 2020-11-20 |  |  | Gurparshad |  | e | n | Payment Information
1398 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Enable Continuous Pay Calculation for Tenants | 2020-11-20 |  |  | Mel Roberts |  | na | na | Payroll |  | 7/6 MR: Initiated in wsu9 tenant after payroll test tenant copy
1409 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Position Budget - Set up Plan Structure | 2020-11-20 |  |  | Mel Roberts |  | na | na | Budgets
1410 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Position Budget - Set up Plan Templates for current and next fiscal year w/ future year dimensions (if any) | 2020-11-20 |  |  | Mel Roberts |  | na | na | Budgets
1411 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Verify / Update Payroll Commitment Options for Company | 2020-11-20 |  |  | Mel Roberts |  | na | na | Budgets |  | 7/6 MR: Dependent upon confirmation of multi-year options to move forward (or not) for FY2021
1412 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Run - Create Initial Payroll Commitments (after verifying ledger periods status is Open for All Periods for Base and Future Years included in Payroll Commitment), verify through completion | 2020-11-20 |  |  | Mel Roberts |  | na | na | Budgets |  | 7/6 MR: Dependent upon confirmation of multi-year options to move forward (or not) for FY2021
1413 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Run - Create Position Budget Group | 2020-11-20 |  |  | Mel Roberts |  | na | na | Budgets |  | 7/6 MR: Dependent upon confirmation of multi-year options to move forward (or not) for FY2021
1414 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Run - Mass Generate Position Budgets (references the position budget group), verify through completion | 2020-11-20 |  |  | Mel Roberts |  | na | na | Budgets |  | 7/6 MR: Dependent upon confirmation of multi-year options to move forward (or not) for FY2021
1415 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Set - Daily Reminder to Run - Create Payroll Commitment Adjustments (for testing tenants requiring daily updates) | 2020-11-20 |  |  | Mel Roberts |  | na | na | Budgets
1416 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Set - Daily Reminder to Run - Position Budget Group and Mass Generate Position Budgets (for testing tenants requiring daily updates) | 2020-11-20 |  |  | Mel Roberts |  | na | na | Budgets
1417 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Set - Daily Reminder to Run - Export Tenant (for all testing tenants requiring daily tenant backup) | 2020-11-20 |  |  | Mel Roberts |  | na | na | Tenants
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Account Translation Method and Rule set | 2020-11-20 |  |  | Jodi Heins |  |  |  | Tenant Setup
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Add Account Control Rules Set | 2020-11-20 |  |  | Jodi Heins |  |  |  | Tenant Setup
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Cycle thru "Edit Company XXX" | 2020-11-20 |  |  | Jodi Heins |  |  |  | Tenant Setup
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Policy Restriction _ Travel Expense | 2020-11-20 |  |  | Jodi Heins |  |  |  | Tenant Setup
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Maintan Payment Election Rule | 2020-11-20 |  |  | Jodi Heins |  |  |  | Tenant Setup
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Make sure ledger periods are open | 2020-11-20 |  |  | Jodi Heins |  |  |  | Ledger Perod
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Worktag Precendence | 2020-11-20 |  |  | Jodi Heins |  |  |  | Tenant Setup
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Maintain Accounting Adjustment Reason Code | 2020-11-20 |  |  | Jodi Heins |  |  |  | Tenant Setup
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Review Allocations | 2020-11-20 |  |  | Jodi Heins |  |  |  | Allocations
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Period Close Activity Groups | 2020-11-20 |  |  | Jodi Heins |  |  |  | Tenant Setup
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Get Rid of Function Subtype | 2020-11-20 |  |  | Jodi Heins |  |  |  | Ledger Period
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Ensure Custom Orgs setup includes hierarchies | 2020-11-20 |  |  | Jodi Heins |  |  |  | Tenant Setup
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Load budgets prior to creating parent hierarchy | 2020-11-20 |  |  | Jodi Heins |  |  |  | Budgets
| 3. Cutover | Gold Build | TECH | Conversion | Workday |  | Copy Gold tenant prior to conversion as a rollback tenant (Gold to WSU5) | 2020-11-21 | 2am | 2020-11-21 | Jane Thomas, Mel Roberts
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse |  | Fix any missing data by resyncing the data (HCA File (11/20/2020) file), (DRS file (11/20/2020), GLMAST, PAREXT) | 2020-11-21 | 8am- 11am | 2020-11-21 | Brad Dudra, Jay Maylor
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse |  | Check last load date on all XW tables: ValidateCrosswalks.sql | 2020-11-21 | 11am-11:15am | 2020-11-21 | Jay Maylor
| 3. Cutover | Gold Build | FIN | Conversion | Gold Data Warehouse |  | DoNotUse_GRANTS (save copy of most current Grant IDs; no conversion impact, but feeds into XW_ACCOUNTS) | 2020-11-21 | 8am-12pm | 2020-11-21 | Christine Galbreath
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse |  | Load Finance/HCM Crosswalks in data warehouse | 2020-11-21 | 8am- 11am | 2020-11-21 | Brad Dudra
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse |  | Rebuild staging tables | 2020-11-21 | 12:30pm-2:00pm | 2020-11-21 | Brad Dudra
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse |  | Reload HCA and drop Benefits extracts | 2020-11-21 | 5pm | 2020-11-21 | Brad Dudra, Wendy Weber
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse |  | Reload Supplier Parent/Child Crosswalk | 2020-11-21 | 11am-11:15am | 2020-11-21 | Brad Dudra
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse |  | Run DUMPY against the Gold schema in the Conversion Warehouse | 2020-11-21 | 1:30pm-3:30pm | 2020-11-21 | Brad Dudra, Karl Riley
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse |  | Run FDM/Validation reports | 2020-11-21 | 4pm-6pm | 2020-11-21 | Keerthinath Manahoran
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse |  | Run XWs to Gold\xw | 2020-11-21 | 4:30pm-5pm | 2020-11-21 | Brad Dudra
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse |  | Send out notification to WSU/Deloitte functional/Technical | 2020-11-21 | 5pm | 2020-11-21 | Brant Schroeder, Jane Thomas
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse |  | Snapshot Conversion Warehouse - Gold | 2020-11-21 | 2pm-3pm | 2020-11-21 | Daniel Ornelas
| 3. Cutover | Gold Build | TECH | Conversion | Gold Data Warehouse | Issue - 145, 141,135, EDB01 (VSAM) segment are failing to connect - may need to run separately - do we need to control access to the mainframe? Jay - job ran at 7am - purges inactive users that could have conflicted | Sync data to conversion warehouse from external systems | 2020-11-21 | 3am-9am | 2020-11-21 | Daniel Ornelas | [5 empty] | Solution: Create an additional incremental load for the segments with conflicting issues
| 3. Cutover | Gold Build | FIN | Conversion | Gold Data Warehouse |  | Update Sponsor Transformation File and place on SFTP | 2020-11-21 | 8am-12pm | 2020-11-21 | Christine Galbreath
| 3. Cutover | Gold Build | FIN | Conversion | Gold Data Warehouse |  | Update Supplier Parent/Child Crosswalk | 2020-11-21 | 10:30am - 11am | 2020-11-21 | Ken Dragoo
| 3. Cutover | Gold Build | FIN | Conversion | Gold Data Warehouse |  | Update XW_ACCOUNTS ((add newly-created accounts and move terminated accounts to the Inactive tab) - need to be SharePoint | 2020-11-21 | 8am-12pm | 2020-11-21 | Christine Galbreath
| 3. Cutover | Gold Build | FIN | Conversion | Gold Data Warehouse |  | Update XW_GRANTS_COST_CENTER (update cost center related worktag mapping per feedback from AFOs and confirm all new accounts map to a valid cost center) | 2020-11-21 | 8am-12pm | 2020-11-21 | Christine Galbreath
| 3. Cutover | Conversion | HCM | Benefits |  |  | Build DRS Job Classification Flag File | 2020-11-21 |  | 2020-11-23 | Wendy Weber
| 3. Cutover | Gold Build | TECH | Conversion |  |  | Create Conversion BP's / take off custom validations on Supplier Change Event BP | 2020-11-21 |  | 2020-11-24 | Keerthinath Manoharan, Jemima Joseph, Lindsay Emer
| 3. Cutover | Gold Build | TECH/HCM/FIN | Conversion/Group1 |  |  | Validate/Load Group 1 Extracts | 2020-11-21 |  | 2020-11-24 | Jim Lowery, Sabrina McPherson, Wendy Weber, Steven Perkins, George Rhodes, Ken Dragoo, Hally Rohla
| 3. Cutover | Gold Build | HCM | Conversion/Group1 |  |  | APPLICANTS | 2020-11-22 | 8 AM to 12 PM | 2020-11-22 | Jim Lowery/Sabrina McPherson/Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group1 |  |  | CREATE_POSITIONS (Position Custom Object - Change Management) | 2020-11-22 | 8 AM to 12 PM | 2020-11-22 | Jim Lowery/Sabrina McPherson/Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group1 |  |  | HIRE_EMPLOYEES (Modhelp 2429) | 2020-11-22 | 8 AM to 12 PM | 2020-11-22 | Jim Lowery/Sabrina McPherson/Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group1 | Workday |  | ADD_ACADEMIC_APPOINTMENTS_AFFILIATES | 2020-11-22 | 1 PM to 4 PM | 2020-11-23 | Jim Lowery, Sabrina McPherson, Wendy Weber, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group1 | Workday |  | CONTRACT_CONTINGENT_WORKERS | 2020-11-22 | 1 PM to 4 PM | 2020-11-23 | Jim Lowery, Sabrina McPherson, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group1 | Workday |  | ADD_ADDITIONAL_JOB | 2020-11-22 | 1 PM to 4 PM | 2020-11-23 | Jim Lowery, Sabrina McPherson, Hally Rohla, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group1 | Workday |  | CHANGE_PERSONAL_INFORMATION | 2020-11-22 | 1 PM to 4 PM | 2020-11-23 | Jim Lowery, Sabrina McPherson, Jemima Joseph
| 3. Cutover | Gold Build | FIN | Conversion/Group1 | Workday |  | SUPPLIERS w/ supplemental | 2020-11-22 | 8 AM to 10 AM | 2020-11-23 | Ken Dragoo, George Rhodes, Jemima Joseh
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | EDIT_POSITION_ACADEMIC_PAY_PERIOD | 2020-11-22 | 8 AM to 11 AM | 2020-11-24 | Joe Wagner, Keerthinath Manoharan
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | SPONSORS | 2020-11-22 | 8 AM to 12 PM | 2020-11-24 | Christine Galbreath, Jemima Joseph
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | GRANTS (xwalk on 11/20) | 2020-11-22 | 8 AM to 12 PM | 2020-11-24 | Christine Galbreath, Keerthinath Manoharan
| 3. Cutover | Gold Build | Payroll | Conversion/Group2 | Workday |  | Letters Of Credit | 2020-11-22 | 1 PM to 5 PM | 2020-11-24 | Christine Galbreath, Nigel Chong-You
| 3. Cutover | Gold Build | Payroll | Conversion/Group2 | Workday |  | PAYEE_INPUT_DATA (deduction crosswalk) | 2020-11-22 | 8 AM to 12 PM | 2020-11-24 | Brigham Hubbard, Jemima Joseph
| 3. Cutover | Gold Build | Payroll | Conversion/Group2 | Workday |  | ASSIGN_EMPLOYEES_TO_PAY_GROUPS | 2020-11-22 | 8 AM to 12 PM | 2020-11-24 | Brigham Hubbard, Jemima Joseph
| 3. Cutover | Gold Build | Payroll | Conversion/Group2 | Workday |  | PAYMENT_ELECTION_ENROLLMENT | 2020-11-22 | 1 PM to 5 PM | 2020-11-24 | Brigham Hubbard, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | WORKER_W4_WITHHOLDINGS - w/ supplemental | 2020-11-22 | 1 PM to 5 PM | 2020-11-24 | Brigham Hubbard, Jemima Joseph
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | CUSTOMERS_CONTRACT | 2020-11-22 | 1 PM to 5 PM | 2020-11-25 | Clint McGregor, George Rhodes, Keerthinath Manoharan
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | SUPPLIERS_ADDRESS with Supplemental (18 records) - Note: validate Addesses before moving forward | 2020-11-22 | 8 AM to 12 PM | 2020-11-25 | Ken Dragoo, George Rhodes, Keerthinath Manoharan
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | SUPPLIER_PHONE | 2020-11-22 | 8 AM to 12 PM | 2020-11-25 | Ken Dragoo, George Rhodes, Keerthinath Manoharan
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | SUPPLIER_EMAIL | 2020-11-22 | 8 AM to 12 PM | 2020-11-25 | Ken Dragoo, George Rhodes, Keerthinath Manoharan
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | SUPPLIER_CONTRACT | 2020-11-22 | 1 PM to 3 PM | 2020-11-25 | Ken Dragoo, George Rhodes, Keerthinath Manoharan
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | SUPPLIER_CONTRACT_GOOD_LINES | 2020-11-22 | 1 PM to 3 PM | 2020-11-25 | Ken Dragoo, George Rhodes, Keerthinath Manoharan
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | SUPPLIER_CONTRACT_SERVICE_LINES | 2020-11-22 | 1 PM to 3 PM | 2020-11-25 | Ken Dragoo, George Rhodes, Keerthinath Manoharan
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | GIFTS w/ default worktags | 2020-11-22 | 8 AM to 4 PM | 2020-11-27 | Joan Wilmotte, , Jemima Joseph
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | CUSTOMERS | 2020-11-22 | 8 AM to 12 PM | 2020-11-27 | Clint McGregor, George Rhodes, Jemima Joseph
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | CUSTOMER_ADDRESS | 2020-11-22 | 8 AM to 12 PM | 2020-11-27 | Clint McGregor, George Rhodes, Jemima Joseph
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | CUSTOMER_EMAIL | 2020-11-22 | 1 PM to 5 PM | 2020-11-27 | Clint McGregor, George Rhodes, Jemima Joseph
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | CUSTOMER_PHONE | 2020-11-22 | 1 PM to 5 PM | 2020-11-27 | Clint McGregor, George Rhodes, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group3 | Workday |  | DEFAULT_COMPENSATION | 2020-11-22 | 12 PM to 5 PM | 2020-11-30 | Joe Wagner, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group3 | Workday |  | REQUEST_COMPENSATION_CHANGE_ALLOWANCE | 2020-11-22 | 12 PM to 5 PM | 2020-11-30 | Joe Wagner, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group3 | Workday |  | REQUEST_COMPENSATION_CHANGE_PAY | 2020-11-22 | 12 PM to 5 PM | 2020-11-30 | Joe Wagner, Keerthinath Manoharan
| 3. Cutover | Gold Build | FIN | Conversion/Group4 | Workday |  | SALES_ITEMS | 2020-11-22 | 8 AM to 5 PM | 2020-11-30 | Clint McGregor, Keerthinath Manoharan
341 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Surcharges | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | fc | Benefits
342 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Individual Rates | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | g | Benefits
343 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Eligibility Rules without Dependencies | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | h1 | Benefits |  | Eligibility rules will be udpated for Gold once HCM values are finalized for assignment terms
344 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Eligibility Rules | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | h2 | Benefits |  | Eligibility rules will be udpated for Gold once HCM values are finalized for assignment terms
345 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Jobs Rules | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | ia | Benefits
346 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Jobs Rules By Group | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | ib | Benefits
347 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Enrollment Event Rules | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | j | Benefits
348 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Groups | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | k | Benefits
349 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Enrollment Instructions | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | l | Benefits
350 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Electronic Signatures | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | m | Benefits
351 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Plans | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | n | Benefits
352 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Cross Plan Dependencies | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | o | Benefits
353 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Plan Year Definitions | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | p | Benefits
354 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Benefit Defaults | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | q | Benefits
355 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Retirement Savings Employee Contribution Allocation | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | ra | Benefits
356 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Retirement Savings Employer Contribution Allocation | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | rb | Benefits
358 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Passive Event Rule | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | ta | Benefits
359 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Passive Alert Rules | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | tb | Benefits
360 | 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Passive Event Batch | 11/23/2020 |  | 2020-11-20 | Suraj Kolimi |  | e | tc | Benefits
| 3. Cutover | Gold Build | HCM | Conversion/Security |  |  | EMPLOYEE_SYSTEM_USERS | 2020-11-23 | 8AM | 2020-11-23 | Jane Thomas, Mel Roberts
| 3. Cutover | Gold Build | HCM | Conversion/Security | Workday |  | CONTINGENT_WORKER_SYSTEM_USERS | 2020-11-23 | 8AM | 2020-11-23 | Jane Thomas, Mel Roberts
| 3. Cutover | Gold Build | HCM | Conversion/Security | Workday |  | Load System Users file - SYSTEM.USERS.csv/Validator Account Setup | 2020-11-23 | 1PM | 2020-11-23 | Lindsay Emer
| 3. Cutover | Gold Build | HCM | Conversion/Security |  |  | Okta/SSO setup for Modernization Team with direct link | 2020-11-23 | 1PM | 2020-11-23 | Stacy Combs, Lindsay Emer
| 3. Cutover | Gold Build | HCM | Conversion/Security | Workday |  | Data Validation Reports - in addition GR, KD custom reports | 2020-11-23 | 1PM | 2020-11-23 | Mel Roberts
| 3. Cutover | Gold Build | HCM | Conversion/Group1 | Workday |  | CHANGE_GOVERNMENT_IDS | 2020-11-23 | 8 AM to 10 AM | 2020-11-23 | Jim Lowery, Sabrina McPherson, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group1 | Workday |  | CHANGE_PREFERRED_NAME | 2020-11-23 | 8 AM to 10 AM | 2020-11-23 | Jim Lowery, Sabrina McPherson, Hally Rohla, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group1 | Workday |  | MAINTAIN_CONTACT_INFORMATION_ADDRESS (Primary) | 2020-11-23 | 11AM to 2PM | 2020-11-23 | Jim Lowery, Wendy Weber, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group1 | Workday |  | MAINTAIN_CONTACT_INFORMATION_PHONE (Primary) | 2020-11-23 | 11AM to 2PM | 2020-11-23 | Jim Lowery, Wendy Weber, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group1 | Workday |  | MAINTAIN_CONTACT_INFORMATION_PHONE (Alternate) | 2020-11-23 | 11AM to 2PM | 2020-11-23 | Jim Lowery, Wendy Weber, Keerthinath Manoharan
| 3. Cutover |  | Security |  |  |  | Validate against hire/position id's and provide the corrected list | 2020-11-23 |  | 2020-11-24 | Wendy Weber, Stacy Combs
| 3. Cutover | Gold Build | HCM | Conversion/Group1 | Workday |  | MANAGER_POSITION_ASSIGN_TO_SUPORG* | 2020-11-23 | 3PM to 5PM | 2020-11-24 | Wendy Weber, Steven Perkins, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group1 | Workday |  | ASSIGN_ORGANIZATIONS including CUSTOM ORGS | 2020-11-23 | 3PM to 5PM | 2020-11-24 | Wendy Weber, Jim Lowery, Sabrina McPherson, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | DEPENDENTS (HCA file received on xx/xx) w/ Supplemental | 2020-11-23 | 3 PM to 5 PM | 2020-11-24 | Wendy Weber, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | MAINTAIN_CONTACT_INFORMATION_ADDRESS (Extract for Dependent fallouts - Primary & Alternate) | 2020-11-23 | 3 PM to 5 PM | 2020-11-24 | Jim Lowery, Wendy Weber, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | SWITCH_PRIMARY_JOB | 2020-11-23 | 3 PM to 5 PM | 2020-11-24 | Sabrina McPherson, Wendy Weber, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | EDIT_POSITION_FOR_DRS_ELIGIBILITY | 2020-11-23 | 8 AM to 12 PM | 2020-11-24 | Wendy Weber, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | CHANGE_OTHER_IDS - Survivor Annuity Option | 2020-11-23 | 8 AM to 12 PM | 2020-11-24 | Wendy Weber, Suraj Kolimi
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | CHANGE_OTHER_IDS - Y2/N2 ACA data | 2020-11-23 | 8 AM to 12 PM | 2020-11-24 | Steven Perkins, Wendy Weber, Suraj Kolimi
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | CHANGE_OTHER_IDS - DRS Override Employment Type Code | 2020-11-23 | 8 AM to 12 PM | 2020-11-24 | Steven Perkins, Wendy Weber, Suraj Kolimi
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | EDIT_ADDITIONAL_WORKER_DATA - Semester by Semester | 2020-11-23 | 8 AM to 12 PM | 2020-11-24 | Steven Perkins, Wendy Weber, Suraj Kolimi
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | EDIT_ADDITIONAL_WORKER_DATA - Seasonal Employees | 2020-11-23 | 8 AM to 12 PM | 2020-11-24 | Steven Perkins, Wendy Weber, Suraj Kolimi
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | EDIT_ADDITIONAL_WORKER_DATA - Employees 480 hrs/6 mo/min 8 per month | 2020-11-23 | 8 AM to 12 PM | 2020-11-24 | Wendy Weber, Steve Perkins, Suraj Kolimi
MPP | 3. Cutover |  | Security |  | Workday |  | Create WD User Accounts in Gold (after hires) - Validate Only | 2020-11-23 |  | 2020-11-25 | Mel Roberts
MPP | 3. Cutover | Gold Build | Security |  |  |  | Give Mod Team Validation View - Only Access in Gold | 2020-11-23 |  | 2020-11-25 | Mel Roberts
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | EDIT_ADDITIONAL_WORKER_DATA - Student Credits | 2020-11-23 | 1 PM to 4 PM | 2020-11-25 | Steven Perkins, Wendy Weber, Suraj Kolimi
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | EDIT_ADDITIONAL_WORKER_DATA - DRS 70/5/12 | 2020-11-23 | 1 PM to 4 PM | 2020-11-25 | Wendy Weber, Steven Perkins, Suraj Kolimi
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | EDIT_ADDITIONAL_WORKER_DATA - DRS History Load | 2020-11-23 | 1 PM to 4 PM | 2020-11-25 | Steven Perkins, Wendy Weber, Suraj Kolimi
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | CUSTOM_ID_BENEFITS_OVERRIDE_ELIGIBILITY | 2020-11-23 | 1 PM to 4 PM | 2020-11-25 | Wendy Weber,, Suraj Kolimi
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | CHANGE_PASSPORTS_AND_VISAS | 2020-11-23 | 1 PM to 4 PM | 2020-11-25 | Steven Perkins, Wendy Weber, Jemima Joseph
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | SUBRECIPIENTS (without address reference) | 2020-11-23 | 8 AM to 4 PM | 2020-11-25 | Christine Galbreath, Keerthinath Manoharan
| 3. Cutover | Gold Build | FIN | Conversion/Group2 | Workday |  | SUBRECIPIENTS (with address reference) | 2020-11-23 | 8 AM to 4 PM | 2020-11-25 | Christine Galbreath, Keerthinath Manoharan
| 3. Cutover | Hard Freeze | HCM | Supervisory Org |  |  | Final Role to Position Mapping templates | 2020-11-23 |  | 2020-11-25 | Steven Perkins, Wendy Weber
| 3. Cutover | Gold Build | HCM | Conversion/Group2 | Workday |  | Task - Request Post Validate on CBFLE | 2020-11-23 | 1 AM to 9AM | 2020-11-26 | Wendy Weber, Jemima Joseph
| 3. Cutover | Gold Build | TECH/HCM/FIN | Conversion | Workday |  | Validate/Load Group 2 Extracts | 2020-11-23 |  | 2020-11-28 | Jim Lowery, Wendy Weber, Christine Galbreath, Brigham Hubbard, Joe Wagner, Steven Perkins, Joan Wilmotte, George Rhodes, Clint McGregor, Ken Dragoo
| 3. Cutover | DA Review | FIN |  | WSU9 |  | DA Functional Review | 2020-11-23 |  | 2020-11-30 | Ed Nieskes
| 3. Cutover | DA Review | HCM |  | WSU9 |  | DA Functional Review | 2020-11-23 |  | 2020-11-30 | Kyle Babinski
| 3. Cutover | Gold Build | TECH/HCM/FIN | Conversion | Workday |  | Validate/Load Group 3 Extracts | 2020-11-23 |  | 2020-11-30 | Christine Galbreath, George Rhodes, Jim Lowery, Hally Rohla, David Rovetto, Ken Dragoo, Joe Wagner
| 3. Cutover | Gold Build | FIN | Conversion/Group3 | Workday |  | Grant Hierarchy updates | 2020-11-23 | 8 AM to 4 PM | 2020-11-30 | Christine Galbreath, Nigel Chong-You
| 3. Cutover | Gold Build | FIN | Conversion/Group3 | Workday |  | Gift Hierarchy updates | 2020-11-23 | 8 AM to 4 PM | 2020-11-30 | Joan Wilmotte, Nigel Chong-You
| 3. Cutover | Gold Build | FIN | Conversion/Group3 | Workday |  | SUPPLIER_CONTRACT_SUBAWARDS | 2020-11-23 | 8 AM to 4 PM | 2020-11-30 | Christine Galbreath/George Rhodes, Keerthinath Manoharan
| 3. Cutover | Gold Build | FIN | Conversion/Group3 | Workday |  | SUBMIT_CATALOG_LOAD (Office Depot) | 2020-11-23 | 8 AM to 4 PM | 2020-11-30 | David Rovetto, Lindsay Emer
| 3. Cutover | Gold Build | FIN | Conversion/Group3 | Workday |  | SUPPLIER_ROYALTY_PAYEES | 2020-11-23 | 8 AM to 4 PM | 2020-11-30 | Ken Dragoo, Lindsay Emer
| 3. Cutover | Gold Build | FIN | Conversion/Group3 | Workday |  | SUPPLIER_CONTACT_INFORMATION - Foreign Supplier Address | 2020-11-23 | 8 AM to 4 PM | 2020-12-01 | Ken Dragoo/George Rhodes, Lindsay Emer
| 3. Cutover | Gold Build | FIN | Conversion/Group3 | Workday |  | CONNECT_SUPPLIER_ADDRESS - Order-From | 2020-11-23 | 8 AM to 4 PM | 2020-12-01 | Ken Dragoo/George Rhodes, Lindsay Emer
| 3. Cutover | Gold Build | FIN | Conversion/Group3 | Workday |  | CONNECT_SUPPLIER_ADDRESS - Remit-To | 2020-11-23 | 8 AM to 4 PM | 2020-12-01 | Ken Dragoo/George Rhodes, Lindsay Emer
| 3. Cutover | Gold Build | HCM | Conversion/Group5 | Workday |  | REQUEST_COMPENSATION_CHANGE_PAY_ANNUITY | 2020-11-23 | 8 AM to 10 AM | 2020-12-01 | Joe Wagner, Keerthinath Manoharan
| 3. Cutover | Gold Build | FIN | Conversion/Group5 | Workday |  | DONORS | 2020-11-23 | 8 AM to 4 PM | 2020-12-02 | Joan Wilmotte, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Configuration | Workday |  | Configure Create Workday Account on Hire - ensure email notifications are off | 2020-11-23 |  |  | Jim Broucek
| 3. Cutover | Gold Build | HCM | Conversion/Group3 | Workday |  | UNION_MEMBERSHIP | 2020-11-24 | 8 AM to 9 AM | 2020-11-30 | Jim Lowery, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group3 | Workday |  | EDIT_SERVICE_DATES | 2020-11-24 | 8 AM to 9 AM | 2020-11-30 | Hally Rohla, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group3 | Workday |  | MANAGE_EDUCATION | 2020-11-24 | 9 AM to 10 AM | 2020-11-30 | Jim Lowery, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group4 | Workday |  | CUSTOM_ID_BENEFITS_OVERRIDE_ELIGIBILITY | 2020-11-24 | 8 AM to 12 PM | 2020-11-30 | Wendy Weber, Suraj Kolimi
| 3. Cutover | Gold Build | HCM | Conversion/Group4 | Workday |  | CHANGE_BENEFITS_FOR_LIFE_EVENT_ADDITIONAL w/ supplemental | 2020-11-24 | 8 AM to 12 PM | 2020-11-30 | Wendy Weber, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group4 | Workday |  | CHANGE_BENEFITS_FOR_LIFE_EVENT_HEALTH | 2020-11-24 | 8 AM to 12 PM | 2020-11-30 | Wendy Weber, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group4 | Workday |  | CHANGE_BENEFITS_FOR_LIFE_EVENT_HEALTH - Tobacco/Spouse surcharge | 2020-11-24 | 8 AM to 12 PM | 2020-11-30 | Wendy Weber, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group4 | Workday |  | CHANGE_BENEFITS_FOR_LIFE_EVENT_HEALTH_SAVINGS | 2020-11-24 | 8 AM to 12 PM | 2020-11-30 | Wendy Weber, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group4 | Workday |  | CHANGE_BENEFITS_FOR_LIFE_EVENT_INSURANCE w/supplemental | 2020-11-24 | 1 PM to 5 PM | 2020-11-30 | Wendy Weber, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group4 | Workday |  | CHANGE_BENEFITS_FOR_LIFE_RETIREMENT_SAVINGS w/ supplemental | 2020-11-24 | 1 PM to 5 PM | 2020-11-30 | Wendy Weber, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group4 | Workday |  | SUPERVISORY_ORGANIZATION_RESTRICTIONS | 2020-11-24 | 1 PM to 5 PM | 2020-11-30 | Wendy Weber, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group4 | Workday |  | CHANGE_BENEFITS_FOR_LIFE_EVENT_HEALTH_SPENDING w/ supplemental | 2020-11-24 | 1 PM to 5 PM | 2020-12-01 | Wendy Weber, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group4 | Workday |  | CHANGE_BENEFITS_HEALTH_SPENDING_WAIVE | 2020-11-24 | 1 PM to 5 PM | 2020-12-01 | Wendy Weber, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group4 | Workday |  | CHANGE_BENEFITS_FOR_LIFE_EVENT_HEALTH_SAVINGS_WAIVE | 2020-11-24 | 1 PM to 5 PM | 2020-12-01 | Wendy Weber, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group4 | Workday |  | FORM_I-9_EXTERNAL_LOAD | 2020-11-24 | 10 AM to 11 AM | 2020-12-01 | Jim Lowery, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group5 | Workday |  | FORM I-9_EXTERNAL_LOAD_SECTION3 | 2020-11-24 | 10 AM to 11 AM | 2020-12-01 | Jim Lowery, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group5 | Workday |  | WORKER_WELLNESS_DATA | 2020-11-24 | 8 AM to 10 AM | 2020-12-01 | Wendy Weber, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group5 | Workday |  | CREATE_NAMED_PROFESSORSHIP | 2020-11-24 | 8 AM to 10 AM | 2020-12-01 | Sabrina McPherson, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group5 | Workday |  | ADD_ACADEMIC_APPOINTMENTS | 2020-11-24 | 1 PM to 5 PM | 2020-12-01 | Jim Lowery, Keerthinath Manoharan
| 3. Cutover | Gold Build | HCM | Conversion/Group5 | Workday |  | MAINTAIN_CONTACT_INFORMATION_ADDRESS_ALTERNATE | 2020-11-24 | 1 PM to 5 PM | 2020-12-01 | Jim Lowery, Wendy Weber, Keerthinath Manoharan
| 3. Cutover | Gold Build | TECH/HCM/FIN | Conversion | Workday |  | Validate/Load Group 5 Extracts | 2020-11-24 |  | 2020-12-02 | Wendy Weber, Jim Lowery, Sabrina McPherson, Joe Wagner, Joan Wilmotte
| 3. Cutover | Gold Build | HCM | Conversion/Group5 | Workday |  | TERMINATE_EMPLOYEES | 2020-11-24 | 1 PM to 5 PM | 2020-12-02 | Jim Lowery, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group5 | Workday |  | ADD_RETIREE_STATUS | 2020-11-24 | 1 PM to 5 PM | 2020-12-02 | Wendy Weber, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group5 | Workday |  | CHANGE_PERSONAL_INFORMATION_DOD | 2020-11-24 | 1 PM to 5 PM | 2020-12-02 | Jim Lowery/Wendy, Jemima Joseph
| 3. Cutover | Gold Build | HCM | Conversion/Group5 | Workday |  | GRANT CUSTOM OBJECTS - Accession Number/CAHNRS Project Code | 2020-11-24 | 1 PM to 5 PM | 2020-12-02 | Christine Galbreath, Nigel Chong-You
| 3. Cutover | Gold Build | HCM | Conversion/Group5 | Workday |  | GIFT CUSTOM OBJECTS - Gift Owner/Associated Spendable Gift/Market Value/Distribution Status/Term Start | 2020-11-24 | 8 AM to 4 PM | 2020-12-02 | Joan Wilmotte, Nigel Chong-You
| 3. Cutover | Gold Build | HCM | Reporting | Workday |  | Migrate HCM/Finance Reports | 2020-11-25 |  | 2020-12-05 | Jason Stucki, Corinna Lo, Kristen Flannery
| 3. Cutover |  | Security |  |  |  | Transform the data and validating the security assignments | 2020-11-25 |  | 2020-12-05 | Tom Woods, Stacy Combs, Kohdy Pierce, Lindsay Emer
MPP | 3. Cutover | Critical Date |  |  | Workday |  | Submit Go-live Checklist and Authorization form to Workday | 2020-11-30 |  | 2020-11-30 | David Boeker | [5 empty] | At least 48 hrs prior to MTP (attach to MTP case)
| 3. Cutover | Hard Freeze | FIN | Expenses | Legacy |  | Cash advance requests processed by Travel Services by 11/30/2020 | 2020-11-30 |  | 2020-11-30 | Allyson Comstock,Karen Kellerman
| 3. Cutover | Communication | FIN | General Accounting | Legacy |  | Submit accounting journals July - November by 11/30 | 2020-11-30 |  | 2020-11-30 | Chris Conway | [5 empty] | CC: Gives a few days to reconcile late Nov payments.
605 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Grants | 2020-12-01 |  | 2020-11-20 | Nigel Chong-You |  | b | aa | Organizations |  | Conversion item loaded via Hoover
747 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Expense Rate Tables | 2020-12-01 |  | 2020-11-20 | Lindsay Emer |  | h | p | Item and Asset Setup |  | EIB Load
749 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Spend Data | 2020-12-01 |  | 2020-11-20 | Lindsay Emer |  | h | r | Item and Asset Setup |  | EIB Load
808 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Gifts | 2020-12-01 |  | 2020-11-20 | Nigel Chong-You |  | j | j | Endowments |  | Conversion item loaded via Hoover
811 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Donors | 2020-12-01 |  | 2020-11-20 | Nigel Chong-You |  | j | m | Endowments |  | Conversion Item - For P2 - only loaded a single donor
812 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Donor Contributions | 2020-12-01 |  | 2020-11-20 | Nigel Chong-You |  | j | n | Endowments |  | Conversion item loaded via Hoover
924 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Contact Information | 2020-12-01 |  | 2020-11-20 | Lindsay Emer |  | p | t | Customers, Suppliers, and Payees |  | Conversion Item
926 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Contracts | 2020-12-01 |  | 2020-11-20 | Lindsay Emer |  | p | x | Customers, Suppliers, and Payees |  | Conversion Item
973 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Register Business Assets | 2020-12-01 |  | 2020-11-20 | Wilson Ye |  | q | ao | Projects, Work, and Business Assets |  | Conversion
974 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Edit Business Assets | 2020-12-01 |  | 2020-11-20 | Wilson Ye |  | q | ap | Projects, Work, and Business Assets |  | Conversion
1052 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Sponsors | 2020-12-01 |  | 2020-11-20 | Nigel Chong-You |  | z | t | Effort Certification and Grants |  | Conversion item loaded via Hoover
1055 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Schedules | 2020-12-01 |  | 2020-11-20 | Nigel Chong-You |  | z | w | Effort Certification and Grants |  | Conversion item loaded via Hoover
1057 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Award Contracts | 2020-12-01 |  | 2020-11-20 | Nigel Chong-You |  | z | y | Effort Certification and Grants |  | Conversion item loaded via Hoover
1069 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Subrecipients | 2020-12-01 |  | 2020-11-20 | Nigel Chong-You |  | z | ao | Effort Certification and Grants |  | Conversion item loaded via Hoover
1072 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Subawards | 2020-12-01 |  | 2020-11-20 | Nigel Chong-You |  | z | ar | Effort Certification and Grants |  | Conversion item loaded via Hoover
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Travel Cities | 2020-12-01 |  | 2020-11-20 | Lindsay Emer |  |  |  | Item and Asset Setup |  | EIB Load
| 3. Cutover | Communication | HCM | Recruiting |  |  | Communicate with candidates of canceled recruitment efforts to reapply in Workday. | 2020-12-01 |  | 2020-12-01 | Sabrina McPherson, Jon Hurd
| 3. Cutover | Communication | HCM | Recruiting |  |  | Communicate with internal workers on new way to apply for jobs. | 2020-12-01 |  | 2020-12-01 | Annie Riedinger, Emily Bailes
| 3. Cutover | Conversion | HCM | Benefits |  |  | Update benefits packets to remove forms for enrollments captured in Workday | 2020-12-01 |  | 2020-12-15 | Ann Monroe
| 3. Cutover | Critical Date | Payroll | Payroll | Legacy |  | Comp Time Payout in legacy Payroll | 2020-12-01 |  | 2020-12-15 | Jackie Meyer | [5 empty] | BH: Kendra talking with BU reps to finalize plan. When departments would have to communicate that they want to pay out comp time.
| 3. Cutover | Critical Date | Payroll | Payroll | Legacy |  | Process last WSU legacy payroll - Pay date December 24 | 2020-12-01 |  | 2020-12-18 | Kim Lawton | [5 empty] | BH:first half of Dec 2020 which would be the Dec 24th paycheck.
1053 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Letters Of Credit | 2020-12-02 |  | 2020-11-20 | Nigel Chong-You |  | z | u | Effort Certification and Grants |  | Requires Sponsors and Bank Accounts to be loaded
| 3. Cutover | Gold Build | TECH | Smoke Testing | Workday |  | Copy Gold tenant prior to MTP for smoke testing (Gold to WSUx) | 2020-12-03 |  | 2020-12-05 | Jane Thomas, Mel Roberts
606 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Grant Hierarchies | 2020-12-04 |  | 2020-11-20 | Nigel Chong-You |  | b | ab | Organizations |  | Conversion item loaded via Hoover
925 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Order-From Connections | 2020-12-04 |  | 2020-11-20 | Lindsay Emer |  | p | u | Customers, Suppliers, and Payees |  | EIB Load
930 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Catalogs | 2020-12-04 |  | 2020-11-20 | Lindsay Emer |  | p | ab | Customers, Suppliers, and Payees |  | EIB Load
931 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Catalog Loads | 2020-12-04 |  | 2020-11-20 | Lindsay Emer |  | p | ac | Customers, Suppliers, and Payees |  | EIB Load
1018 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Related Worktag Usage | 2020-12-04 |  | 2020-11-20 | Jodi Heins |  | v | i | Custom Validations and Worktag Rules |  | After conversion
1019 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Default Values for Worktags | 2020-12-04 |  | 2020-11-20 | Jodi Heins |  | v | j | Custom Validations and Worktag Rules |  | After conversion
1020 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Related Worktags | 2020-12-04 |  | 2020-11-20 | Jodi Heins |  | v | k | Custom Validations and Worktag Rules |  | After conversion
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Suppliers - Supplier Royalty Payees | 2020-12-04 |  | 2020-11-20 | Lindsay Emer |  | p | s | Customers, Suppliers, and Payees |  | EIB Load
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Contact Information - Foreign Addresses | 2020-12-04 |  | 2020-11-20 | Lindsay Emer |  | p | t | Customers, Suppliers, and Payees |  | EIB Load
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Supplier Remit-To Connections | 2020-12-04 |  | 2020-11-20 | Lindsay Emer |  | p | u | Customers, Suppliers, and Payees |  | EIB Load
| 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Internal Service Providers | 2020-12-04 |  | 2020-11-20 | Lindsay Emer |  |  |  | Customers, Suppliers, and Payees |  | EIB Load
| 3. Cutover |  | HCM | Compensation | Legacy | Prob to Perm activity/HR Core (12/1 - 12/2) | Last legacy PID runs on 12/04/2020, effective 12/01/2020 | 2020-12-04 |  | 2020-12-04 | Jay Maylor, Joe Wagner
| 3. Cutover | Critical Date | HCM | Benefits |  |  | Pull and hold DCP Inbound INT053 change files from ppd | 2020-12-05 |  | 2020-12-05 | Wendy Weber
| 3. Cutover |  | HCM | Benefits |  |  | Pull Copy of INT170 from DRS folder and hold for processing | 2020-12-05 |  | 2020-12-05 | Wendy Weber
| 3. Cutover |  | TECH |  |  |  | Ensure the URL Link to Workday system is enabled | 2020-12-07 |  | 2020-12-15 | Brant Schroeder
| 3. Cutover | Soft Freeze/Hard Freeze | HCM | Recruiting | Legacy |  | Freeze on Requisitions on by departments, security change, or denying new postings | 2020-12-07 |  | 2020-12-16 | Sabrina McPherson, Jon Hurd
| 3. Cutover |  | Security | Conversion |  |  | Convert Role Based Security (R2PM) | 2020-12-08 |  | 2020-12-09 | Stacy Combs, Lindsay Emer, Tom Woods, Kohdy Pierce, Keerthinath
| 3. Cutover |  | TECH | Conversion | Workday |  | Load Costing Allocations from 12/5/2020 snapshot | 2020-12-09 |  | 2020-12-09 | Brad Dudra/Keerthinath/Jemima Manoharan
| 3. Cutover |  | Security |  | Workday |  | Smoke Test Security and Assignments in Production | 2020-12-09 |  | 2020-12-11 | Mel Roberts,Kohdy Pierce,Stacy Combs,Tom Woods,Lindsay Emer
MPP | 3. Cutover | Go/No-Go | TECH |  |  |  | Technicalnical Go/No Go decision | 2020-12-10 |  | 2020-12-10 | Mike Corwin, David Boeker, Brant Schroeder, Karl Riley, Jane Thomas
| 3. Cutover | Integrations | HCM | Recruiting |  |  | INT005 - myWSU - Demographic Data Update - SI - Inbound | 2020-12-10 |  | 2020-12-10 | Sabrina McPherson
| 3. Cutover | Integrations | HCM | Recruiting |  |  | INT131 - myWSU - Demographic Data - CCW - Outbound | 2020-12-10 |  | 2020-12-10 | Sabrina McPherson
| 3. Cutover | Integrations | HCM | Recruiting |  |  | INT177 - myWSU - Affiliates - Inbound | 2020-12-10 |  | 2020-12-10 | Sabrina McPherson
MPP | 3. Cutover |  | Security |  |  |  | Okta/SSO setup for Modernization Team with direct link | 2020-12-10 |  | 2020-12-15 | Kohdy Pierce, Todd Weston, Brant Schroeder
| 3. Cutover | Manual - UI | HCM | Benefits | Workday |  | Enter CBFLE-Insurance and CBFLE-Additional fallouts-manually | 2020-12-10 |  | 2020-12-15 | Wendy Weber
| 3. Cutover | Conversion | HCM | Benefits |  |  | Identify data items to fix for catch up loads and fix. Including missing position terms, dates of birth. Also, temporarily adjust date of birth for age range changes that happen "in the window" for special handling. | 2020-12-10 |  | 2020-12-15 | Wendy Weber
| 3. Cutover | Manual - UI | HCM | Benefits |  |  | Identify People missing LTD enrollments because they are in active approved claims - Enroll them manually and add LTD Claim Stop period | 2020-12-10 |  | 2020-12-15 | Wendy Weber
| 3. Cutover | Manual - UI | HCM | Benefits |  |  | Identify the Retirement Plan "3" (in enrollment window) and launch enrollments | 2020-12-10 |  | 2020-12-15 | Wendy Weber
| 3. Cutover | Integrations | HCM | Benefits | Workday |  | INT066 - DRS - Benefits Objects - SI - Inbound (BP initiated integration) | 2020-12-10 |  | 2020-12-15 | Wendy Weber
| 3. Cutover | Delta Load | HCM | Benefits |  |  | Load Health Savings (12/10 - 12/15) - 11/20 (file will be updated by Wendy) | 2020-12-10 |  | 2020-12-15 | Wendy Weber
| 3. Cutover | Delta Load | HCM | Benefits | Workday |  | NAVIA data - Health Spending (Load between 12/10 - 12/15) | 2020-12-10 |  | 2020-12-15 | Wendy Weber
| 3. Cutover | Manual - UI | HCM | Benefits | Workday |  | Process Age Outs (Dependents) and Age Ups (Retirement) | 2020-12-10 |  | 2020-12-15 | Wendy Weber
| 3. Cutover | Manual - UI | HCM | Benefits | Workday |  | Put dates of birth back for those adjusted for cutover (retirement participants aging up and run events to correct with appropriate effective dates. ) | 2020-12-10 |  | 2020-12-15 | Wendy Weber
| 3. Cutover | Manual - UI | HCM | Benefits | Workday |  | Rehire Retirees (and verify SRP/benefits) | 2020-12-10 |  | 2020-12-15 | Thresa Skeslien Jenkins
| 3. Cutover | Manual - UI | HCM | Compensation | Workday |  | Enter Post Term Compensation | 2020-12-10 |  | 2020-12-15 | Joe Wagner
| 3. Cutover | Manual - EIB | HCM | Compensation | Workday |  | Run Period Activity Pay EIB | 2020-12-10 |  | 2020-12-15 | Joe Wagner, Shawn Ismail
| 3. Cutover | Manual - UI | HCM | Compensation | Workday |  | Update Employee Compensation | 2020-12-10 |  | 2020-12-15 | Joe Wagner | [5 empty] | Review Reports in Dress Rehearsal
| 3. Cutover |  | HCM | Compensation | Workday |  | Validate and Update Employee Allowance ~50 individuals | 2020-12-10 |  | 2020-12-15 | Joe Wagner | [5 empty] | 6 hours
| 3. Cutover | Manual - UI | HCM | Core HR | Workday |  | Change Contact Information | 2020-12-10 |  | 2020-12-15 | Jim Lowery
| 3. Cutover | Manual - UI | HCM | Core HR | Workday |  | Enter Academic Appointment changes between 11/20 - 12/15 | 2020-12-10 |  | 2020-12-15 | Jim Lowery/Provost Office
| 3. Cutover | Manual - UI | HCM | Core HR | Workday |  | Hire Employees - Manual | 2020-12-10 |  | 2020-12-15 | Jim Lowery
| 3. Cutover | Manual - UI | HCM | Core HR | Workday |  | Manually enter Job Change (remove approvals from BP temporarily) | 2020-12-10 |  | 2020-12-15 | Jim Lowery/Central HR
| 3. Cutover | Manual - UI | Payroll | Payroll | Workday |  | Enter deductions, elective deductions, and name changes in Workday | 2020-12-10 |  | 2020-12-15 | Benjamin Howard | [5 empty] | BH: Manual Entry - UI into WD after this date
| 3. Cutover | Manual - UI | HCM | Recruiting | Workday |  | Manually enter Hire in Workday after recruitment effort is complete in OPDRS. | 2020-12-10 |  | 2020-12-15 | Sabrina McPherson, Jon Hurd
| 3. Cutover | Manual - EIB | HCM | Time/Absence | Workday |  | Business Titles - EIB | 2020-12-10 |  | 2020-12-15 | Jemima Joseph/Emily Goodwin
| 3. Cutover | Manual - EIB | HCM | Time/Absence | Workday |  | Time Off Events - EIB - Department updates after go-live | 2020-12-10 |  | 2020-12-15 | Jemima Joseph/Emily Goodwin
| 3. Cutover | Manual - EIB | HCM | Time/Absence | Workday |  | Time Off Hourly Balances - EIB - For time worked between 12/1 and 12/15 | 2020-12-10 |  | 2020-12-15 | Jemima Joseph/Emily Goodwin
| 3. Cutover | Integrations | HCM | Benefits | Workday |  | Load INT170 DRS Service Credit from held file 12/5/2020 | 2020-12-11 |  | 2020-12-11 | Daniel Ornelas
| 3. Cutover | Integrations | HCM | Benefits | Workday |  | Process TIAA INT052 Seed File | 2020-12-11 |  | 2020-12-11 | Wendy Weber
| 3. Cutover | Manual - UI | HCM | Benefits | Workday |  | Update work locations for eligibility if these individuals are still enrolled in postal code specific plans. Benjamin Piper – 11740367 – update work location on position to “General Campus – WSU Spokane” Logan Cody Steele – 11133858 – update work location on position to “General Campus – WSU Spokane” Michael John Pierson – 10564406 – update work location on position to “Town Square Building 3-WSU Energy Program – Olympia” | 2020-12-11 |  | 2020-12-11 | Wendy Weber
| 3. Cutover | Manual - UI | HCM | Benefits | Workday |  | Update Workday for Court Ordered Coverage /National Medical Support Notices | 2020-12-11 |  | 2020-12-15 | Wendy Weber
| 3. Cutover | Manual - UI | HCM | Benefits | Workday |  | Check Raymond Harris - 11506016 for Retired - Active and Rehire (special code in hire extract) | 2020-12-11 |  | 2020-12-15 | Wendy Weber
| 3. Cutover | Hard Freeze | FIN | A/P | Legacy |  | Final JPMC ACH on 12/12/2020. Transactions posted 12/14/2020 and after will be available to settle in Workday Go Live. | 2020-12-12 |  | 2020-12-12 | Allyson Comstock,Karen Kellerman
MPP | 3. Cutover | Production Readiness | Operating Committee |  |  |  | Gate 3 - Prior to User Go Live | 2020-12-14 |  | 2020-12-14 | Jay Dumphy, Jennifer Klein, Joy Morton, Mike Corwin
| 3. Cutover |  | FIN | Expenses | Legacy |  | Payment request created and final Comdata wire on 12/14/2020 for November account statements. Transactions posted 12/14/2020 and after will be available to settle in Workday Go Live. | 2020-12-14 |  | 2020-12-14 | Allyson Comstock,Karen Kellerman
| 3. Cutover |  | FIN | Expenses | Legacy |  | Payment request created and final JPMC ACH on 12/14/2020. Transactions posted 12/14/2020 and after will be available to settle in Workday Go Live. | 2020-12-14 |  | 2020-12-14 | Allyson Comstock,Karen Kellerman
| 3. Cutover | Critical Date | HCM | Recruiting | Legacy |  | JobElephant no longer scrapes job postings from OPDRS | 2020-12-15 | 5pm | 2020-12-15 | Sabrina McPherson, Jon Hurd
| 3. Cutover |  | HCM | Supervisory Org |  |  | Remove anyone remaining in SP000004 and inactivate | 2020-12-15 |  | 2020-12-15 | Steven Perkins, Wendy Weber
MPP | 3. Cutover |  | Security |  |  |  | Okta/SSO setup for all Users (Employees, Contractors, Affiliates) | 2020-12-15 |  | 2020-12-16 | Kohdy Pierce, Todd Weston, Brant Schroeder
MPP | 3. Cutover | Critical Date | HCM/Payroll/Finance | HCM/Payroll/Finance | Workday |  | HCM/Payroll and Finance (with limited functionality) - Go-Live! | 2020-12-16 |  | 2020-12-16 | Jay Dumphy, Jennifer Klein, Joy Morton, Mike Corwin. Kyle Babinski
| 3. Cutover | Manual - UI | HCM | Benefits | Workday |  | Put Cross Plan Dependency from HSA / CDHP plans back on | 2020-12-16 |  | 2020-12-16 | Suraj Kolimi
| 3. Cutover | Manual - UI | HCM | Benefits | Workday |  | Turn "Only eligible if already enrolled" rule back on Grandfathered plans. | 2020-12-16 |  | 2020-12-16 | Suraj Kolimi
| 3. Cutover |  | HCM | Benefits |  |  | Update Benefits Website for launch | 2020-12-16 |  | 2020-12-16 | Ann Monroe
| 3. Cutover | Integrations | HCM | Core HR | Workday |  | INT159 - AIMS Parking - Bio Demo - Outbound | 2020-12-16 |  | 2020-12-16 | Jim Lowery
| 3. Cutover | Hard Freeze | FIN | A/P | Legacy |  | Lock PaymentNet to departments. Transactions posted 12/15/2020 and after will be available in Workday Go Live. | 2020-12-16 |  | 2020-12-16 | Allyson Comstock | [5 empty] | GR: We need to make sure we remove the ability to recon transactions in PaymentNet on this date.
| 3. Cutover | Integrations | Payroll | Payroll |  |  | INT095 - myWSU - Student FICA Exemption - SI - Inbound | 2020-12-16 |  | 2020-12-16 | Mayra Young
| 3. Cutover | Communication | PMO |  |  |  | Communication Workday launch (go-live) to Executives, Leaders and Employees | 2020-12-16 |  | 2020-12-16 | Annie Riedinger/Emily Bailes
| 3. Cutover | Critical Date | FIN | Expenses | Legacy |  | Expense Reports completed and approved | 2020-12-16 |  | 2020-12-16 | General Accounting
| 3. Cutover | Integrations | Payroll | Payroll |  |  | INT139 - Campus Solutions - Workstudy Payroll Data - SI - Inbound | 2020-12-16 |  | 2020-12-16 | Kim Lawton
| 3. Cutover | Integrations | Payroll | Payroll |  |  | INT163 - Point and Click - Graduate Students Health Insurance - Outbound | 2020-12-16 |  | 2020-12-16 | Holly Sigurdsson
| 3. Cutover | Integrations | Payroll | Payroll |  |  | INT164 - Point and Click - Graduate Students Health Insurance - Inbound | 2020-12-16 |  | 2020-12-16 | Holly Sigurdsson
| 3. Cutover | Integrations | FIN | Expenses |  |  | INT110 - XE.com - Currency Exchange - CCF - Inbound | 2020-12-16 |  | 2020-12-16 | Ken Dragoo
| 3. Cutover | Integrations | FIN | A/R | Workday |  | INT158 - myWSU - FDM - Outbound | 2020-12-16 |  | 2020-12-16 | Clint McGregor
| 3. Cutover |  | TECH |  | Workday |  | Whitelist the URLS | 2020-12-16 |  | 2020-12-16 | Brant Schroeder, Jane Thomas
| 3. Cutover | Critical Date | HCM | Recruiting | Workday |  | JobElephant scrapes job postings from Workday | 2020-12-16 | 8am | 2020-12-16 | Sabrina McPherson, Jon Hurd
| 3. Cutover | Critical Date | HCM | Recruiting | Workday |  | Launch institution landing pages for recruiting | 2020-12-16 | 8am | 2020-12-16 | Adam Turner, Sabrina McPherson, Jon Hurd
| 3. Cutover |  | HCM | Recruiting | Workday |  | New recruitment efforts are conducted in Workday | 2020-12-16 |  | 2020-12-16 | Sabrina McPherson, Jon Hurd
| 3. Cutover | Manual - UI | HCM | Time/Absence | Workday |  | Enter time or request time off - in ESS >= 12/16 | 2020-12-16 |  | 2020-12-16 | Employees
| 3. Cutover | Manual - UI | Payroll | Payroll | Workday |  | Enter Garnishments/levies | 2020-12-16 |  | 2020-12-23 | Mayra Young, Chantelle Boyd | [5 empty] | BH: No conversion of data because it does not exist in AIS. This will be a Manual Entry - UI into Workday.
| 3. Cutover | Integrations | HCM | Core HR | Workday |  | INT001 - Phone Directory - Contact Information - CCW - Outbound | 2020-12-17 |  | 2020-12-17 | Jim Lowery
| 3. Cutover | Integrations | HCM | Core HR | Workday |  | INT045 - International Programs - Hiring and Appointments - EIB - Outbound | 2020-12-17 |  | 2020-12-17 | Jim Lowery
| 3. Cutover | Integrations | HCM | Core HR | Workday |  | INT061a - Oracle WebCenter - Imaging HCM - EIB - Outbound | 2020-12-17 |  | 2020-12-17 | Hally Rohla
| 3. Cutover | Integrations | Payroll | Payroll |  |  | INT019 - AiM - Locations - SI - Inbound | 2020-12-17 |  | 2020-12-17 | Brigham Hubbard
| 3. Cutover | Integrations | HCM | Recruiting |  |  | INT023 - myWSU - Graduate Appointments - EIB - Outbound | 2020-12-17 |  | 2020-12-17 | Sabrina McPherson
| 3. Cutover | Integrations | HCM | Recruiting |  |  | INT070 - HRS - Employee Data - CCW - Outbound | 2020-12-17 |  | 2020-12-17 | Sabrina McPherson
| 3. Cutover |  | FIN | FDM |  |  | Publish FDM Configuration Workbook/OBIEE | 2020-12-21 |  | 2020-01-01 | Brant Schroeder/Brad Dudra/Corinna Lo
| 3. Cutover | Hard Freeze | FIN | Business Assets |  |  | Last day for asset creation, modification, and disposal | 2020-12-23 |  | 2020-12-23 | George Rhodes/Clint McGregor | [5 empty] | Manual / Dual Entry
| 3. Cutover | Manual - UI | FIN | Business Assets | Workday |  | Enter legacy asset modifications | 2020-12-28 |  | 2020-12-31 | George Rhodes/Clint McGregor | [5 empty] | Manual / Dual Entry
1024 | 3. Cutover | Gold Build | FIN | Configuration | Workday |  | Beginning Balance | 2020-12-31 |  | 2020-11-20 | Jodi Heins |  | w | e | Journals and Budget Entries |  | Conversion Item
MPP | 3. Cutover | Critical Date | FIN |  |  |  | Cutover Complete for FIN | 2020-12-31 |  | 2020-12-31 | Jay Dumphy, Jennifer Klein, Joy Morton, Mike Corwin. Ed Nieskes
| 3. Cutover | Critical Date | FIN | Controller | Legacy | When is the depreciation on Capital Assets run? | Calculate annual depreciation for Depreciable Assets for FY2021 | 2021-06-30 |  | 2021-06-30 | George Rhodes/Clint McGregor | [5 empty] | Per Tami Bidle, normally occurs in August.
| 3. Cutover | Gold Build | HCM/FIN |  |  |  | Turn on email notifications & disable email redirect |  |  |  | Kyle Babinski
| 4. Post-Cutover |  | FIN | A/R - Sponsored | Workday |  | On-account payments can be applied to open A/R invoices created through the ITD process | 2020-01-11 |  | 2020-01-11 | Christine Galbreath, Carrie Johnston | [5 empty] | CPM: Date determined based on Internal Closing Schedule for FY2020
| 4. Post-Cutover | Pre-Financial | FIN | ITD/Budget/GL | Workday |  | FY21 Non-core net position file - EIB - ITD Journal | 2020-10-30 |  | 2020-12-01 | Chris Conway/Jodi Heins
| 4. Post-Cutover | Pre-Financial | FIN | ITD/Projects | Workday |  | Project Expenses - EIB - ITD Load Projects | 2020-10-30 |  | 2020-12-31 | TY Siamanson/Ed Nieskes
| 4. Post-Cutover | Post Launch | FIN | ITD/Beginning Balances | Workday |  | Load Debt | 2020-10-30 |  | 2021-01-30 | Kameron | [5 empty] | CPM: Date based on expected day when ECSI will provide monthly reporting to WSU.
| 4. Post-Cutover |  | FIN | Expenses | Legacy |  | Travel expense vouchers received by Travel Services by 11/15/2020. Travel missing this deadline or after 12/15/2020 must be created in Workday Go Live. | 2020-11-15 |  | 2020-11-15 | Departments
| 4. Post-Cutover | Hard Freeze | FIN | Awards | Legacy |  | Grant Transfers (ETR) | 2020-11-15 |  | 2020-12-18 | Departments SPS
| 4. Post-Cutover | Soft Freeze/Hard Freeze | FIN | Awards | Legacy |  | Entering new suppliers/subrecipients/sponsors | 2020-11-15 |  | 2020-12-23 | Purchasing/SPS
| 4. Post-Cutover | Critical Date | FIN | ITD/Beginning Balances | Workday |  | Finance team to load 'Inception to Date' balances into Workday | 2020-12-01 |  | 2021-02-05 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Communication |  |  |  |  | Send Email communications to Announce System is OPEN for HCM/Payroll transactions on 12/16, with limited Finance | 2020-12-07 |  | 2020-12-15
| 4. Post-Cutover | Post Launch | FIN | ITD/Gifts | Legacy |  | Final upload from Access Database to Workday - Confirm ITD loaded values (Units & Fair Market Value & Net Book Value) | 2020-12-10 |  | 2020-12-10 | Joan Wilmotte
| 4. Post-Cutover | Manual - UI | HCM | Compensation | Workday |  | Adjustment of inflated hard coded OT rates for ~30 individuals | 2020-12-10 |  | 2020-12-15 | Joe Wagner
| 4. Post-Cutover | Manual - UI | FIN | Awards | Workday |  | Manually enter Payroll/Cost Share and Allocations Information | 2020-12-10 |  | 2020-12-15 | Carrie Johnston, Grant Managers
| 4. Post-Cutover | Pre-Financial | FIN | ITD/Gifts | Workday |  | Gifts through Nov 20 - EIB - ITD Donor Contribution - GIFTS_SUBMIT_DONOR_CONTRIBUTION.csv | 2020-12-10 |  | 2020-12-30 | Joan Wilmotte/Nigel Chong-You
| 4. Post-Cutover | Pre-Financial | FIN | ITD/Gifts | Workday |  | Gifts through Nov 20 - EIB - ITD Investment Pool Sale - GIFTS_SUBMIT_INVESTMENT_POOL_PURCH.csv | 2020-12-10 |  | 2020-12-30 | Joan Wilmotte/Nigel Chong-You
| 4. Post-Cutover | Pre-Financial | FIN | ITD/Gifts | Workday |  | Gifts through Nov 20 - EIB - ITD Gift Investment Statement - GIFTS_SUBMIT_INVESTMENT_STATEMENT.csv | 2020-12-10 |  | 2020-12-30 | Joan Wilmotte/Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Gifts | Workday |  | Execute tasks on Gifts ITD | 2020-12-10 |  | 2021-01-15 | Joan Wilmotte/Nigel Chong-You
| 4. Post-Cutover | Critical Date | TECH |  | Workday |  | Gold Tenant Deletion | 2020-12-11 |  | 2020-12-11 | Kristen Flannery/Mel Roberts | [5 empty] | 5 days after MTP
| 4. Post-Cutover |  | FIN | Expenses | Legacy |  | State of Washington Invoice Voucher for employee confirming reimbursements received by Accounts Payable. Confirming reimbursement missing this deadline or after 12/15/2020 must be created in Workday Go Live. | 2020-12-15 |  | 2020-12-15 | Departments
| 4. Post-Cutover | Hard Freeze | FIN | A/P |  |  | Reconcile Transactions in PaymentNet by 12/15/2020. Transactions posted 12/15/2020 and after will be available in Workday Go Live. | 2020-12-15 |  | 2020-12-15 | Departments
| 4. Post-Cutover |  | HCM | Supervisory Org | Workday |  | Process anyone remaining in SP000002 and inactivate | 2020-12-15 |  | 2020-12-15 | Wendy Weber
| 4. Post-Cutover | Pre-Financial | FIN | ITD/Budget/GL | Workday |  | FY21 Monthly FY21 Nov Expense Journal - EIB - ITD Journal | 2020-12-15 |  | 2020-12-31 | Chris Conway/Jodi Heins
| 4. Post-Cutover | Pre-Financial | FIN | ITD/Budget/GL | Workday |  | FY21 Nov Revenue Journal - EIB - ITD Journal | 2020-12-15 |  | 2020-12-31 | Chris Conway/Jodi Heins
| 4. Post-Cutover | Integrations | HCM | Core HR | Workday |  | INT146 - CBORD - Demographic Data - CCW - Outbound | 2020-12-16 |  | 2020-12-16 | Jim Lowery
| 4. Post-Cutover | Hard Freeze | FIN | A/P | Legacy |  | Default all Pcard/CTA transactions not reconciled in PaymentNet by 12/16/2020. | 2020-12-16 |  | 2020-12-16 | Allyson Comstock, Ken Dragoo | [5 empty] | Travel Services
| 4. Post-Cutover | Hard Freeze | FIN | A/P | Legacy |  | Freeze Payment Requests (invoices) for FY2021 | 2020-12-16 |  | 2020-12-16 | Nancy Olin, George Rhodes
| 4. Post-Cutover | Integrations | FIN | A/P | Workday |  | INT038a - JP Morgan - Pcard Transactions - CCF - Inbound | 2020-12-16 |  | 2020-12-16 | Ken Dragoo
| 4. Post-Cutover | Integrations | FIN | A/P | Workday |  | INT038b - JP Morgan - Pcard Transactions - CCF - Inbound | 2020-12-16 |  | 2020-12-16 | Ken Dragoo
| 4. Post-Cutover | Integrations | HCM | Recruiting |  |  | INT089 - MIM - Employee and Location - RaaS - Outbound | 2020-12-16 |  | 2020-12-16 | Sabrina McPherson
| 4. Post-Cutover | Integrations | HCM | Recruiting |  |  | INT103 - HireRight - Background Check Result - SI - Inbound | 2020-12-16 |  | 2020-12-16 | Sabrina McPherson
| 4. Post-Cutover | Integrations | HCM | Recruiting |  |  | INT165 - CAHNRS - Mailing List - Outbound | 2020-12-16 |  | 2020-12-16 | Sabrina McPherson
| 4. Post-Cutover | Communication | HCM | Time/Absence |  |  | Collect anticipated time offs from university for 12/1 - 12/15 from departments | 2020-12-16 |  | 2020-12-22 | Emily/Dora
| 4. Post-Cutover | Manual - UI | HCM | Time/Absence | Workday |  | Employees who have requested and been approved for time off in the future - Enter time in Employee Self Service (ESS) | 2020-12-16 |  | 2020-12-31 | Employees
| 4. Post-Cutover |  | HCM | Compensation | Workday |  | As per the Minimum Wage increase, create new Classified Grades, Grade Profiles, and Steps (data provided by the state of Washington). | 2020-12-16 |  | 2021-01-01 | Joe Wagner
| 4. Post-Cutover |  | HCM | Compensation | Workday |  | As per the Minimum Wage increase, in update all existing Classified Grades, Grade Profiles, and Steps (data provided by the state of Washington). | 2020-12-16 |  | 2021-01-01 | Joe Wagner | [5 empty] | Washington State will announce in October
| 4. Post-Cutover |  | HCM | Compensation | Workday |  | As per the Minimum Wage increase, inactivate obsolete Classified Grades, Grade Profiles, and Steps (data provided by the state of Washington). | 2020-12-16 |  | 2021-01-01 | Joe Wagner | [5 empty] | Washington State will announce in October
| 4. Post-Cutover |  | HCM | Compensation | Workday |  | Prepare and run Request Compensation Change EIB to move all EEs to their correct Grades, Grade Profiles, and Steps for minimum wage increase (effective 01/01/2021) | 2020-12-16 |  | 2021-01-01 | Joe Wagner/Shawn Ismail | [5 empty] | Washington State will announce in October
| 4. Post-Cutover |  | FIN | Effort Reporting | Workday |  | First Workday Effort Cert Period | 2020-12-16 |  | 2021-05-01 | SPS/Departments
| 4. Post-Cutover | Integrations | HCM | Compensation | Workday |  | INT166 - Digital Measures - Appointment - Outbound | 2020-12-16 |  | 2021-12-16 | Joe Wagner
| 4. Post-Cutover | Critical Date | Payroll | Payroll | Legacy |  | Last day to enter time (DAR's due in positive pay) - 2pm | 2020-12-17 |  | 2020-12-17 | Kim Lawton | [5 empty] | Departments Central Payroll
| 4. Post-Cutover | Manual - UI | HCM | Compensation | Workday |  | PID - Identify the EE population > 11 days of LWOP (along with other criteria) and dock their Progression Start Date in WD by one month in order to exclude them from the PID integration. | 2020-12-17 |  | 2020-12-31 | Joe Wagner/Shawn Ismail/Lisa Neal
| 4. Post-Cutover | Critical Date | TECH | Awards/General Accounting | Legacy |  | Remove access to FACTS from Campus - Grants that termed before 12/31/2020 should be prioritized for closure to avoid converting to Workday. Awards terming 12/04 – 12/18 we assume will be converted if activity still needs to happen | 2020-12-18 |  | 2020-12-18 | Christine Galbreath/Chris Conway
| 4. Post-Cutover |  | Payroll | Payroll |  |  | Payroll Compare - Last legacy vs. first Workday payroll | 2020-12-19 |  | 2021-01-07 | Brigham Hubbard/Mel Roberts/Benjamin Howard
| 4. Post-Cutover | Critical Date | HCM | Benefits | Workday |  | Load DCP inbound change files from ppd 12/10 and 12/25 | 2020-12-20 |  | 2020-12-20 | Wendy Weber
| 4. Post-Cutover |  | HCM | Compensation | Workday |  | Launch PID integration in SBX tenant to ensure it works properly. | 2020-12-20 |  | 2020-12-31 | Joe Wagner/Shawn Ismail
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st outbound INT081 DRS DCP Eligibles/Enrollment (weekly, thereafter) | 2020-12-21 |  | 2020-12-21 | Wendy Weber
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st outbound INT171 Health and Wellness Employees (continue weekly on Monday am, thereafter) | 2020-12-21 |  | 2020-12-21 | Steven Perkins
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st "inbound" HCA INT056 Data Validation (continue daily on Monday am, thereafter) | 2020-12-21 |  | 2020-12-21 | Steven Perkins
| 4. Post-Cutover |  | FIN | A/P | Legacy |  | Confirming reimbursements approved by Accounts Payable by 12/21/2020 | 2020-12-21 |  | 2020-12-21 | Nancy Olin, Ken Dragoo
| 4. Post-Cutover | Hard Freeze | FIN | A/R - Sponsored | Legacy |  | Last day sponsor payments will be received in legacy | 2020-12-23 |  | 2020-12-23 | Christine Galbreath, Carrie Johnston
| 4. Post-Cutover |  | FIN | Expenses | Legacy |  | Cash advance overages receipted by Cashier's Office by 12/23/2020. | 2020-12-23 |  | 2020-12-23 | Cashier's Office
| 4. Post-Cutover | Hard Freeze | FIN | General Accounting | Legacy |  | Last date to submit accounting journals December | 2020-12-23 |  | 2020-12-23 | Chris Conway
| 4. Post-Cutover |  | FIN | Gifts/Endowments | Legacy |  | Last earnings distribution from Gifts for October | 2020-12-23 |  | 2020-12-23 | Joan Wilmotte | [5 empty] | JW: Per Karen Kellerman, subject to change in June 2020
| 4. Post-Cutover |  | FIN | Expenses | Legacy |  | Outstanding cash advances list compiled by 12/23/2020. | 2020-12-23 |  | 2020-12-23 | Allyson Comstock,Karen Kellerman
| 4. Post-Cutover |  | FIN | Expenses | Legacy |  | Payment request created and final ACH transmission or check print by 12/23/2020 | 2020-12-23 |  | 2020-12-23 | Allyson Comstock,Karen Kellerman
| 4. Post-Cutover | Hard Freeze | FIN | Expenses | Legacy |  | Process all Pcard/CTA transactions through Doggier and post to AIS mainframe by 12/23/2020. Transactions posted 12/23/2020 and after will be available in Workday Go Live. | 2020-12-23 |  | 2020-12-23 | Ken Dragoo | [5 empty] | Travel Services
| 4. Post-Cutover | Hard Freeze | FIN | Awards | Legacy |  | Sponsored payments for invoices will be held from 12/24 to 12/31 will be held and entered into Workday on or after 01/01 | 2020-12-23 |  | 2020-12-23 | SPS | [5 empty] | Payments will be recorded on account in Workday as Open AR will not be recorded until Grants ITD process is completed weeks later
| 4. Post-Cutover | Soft Freeze/Hard Freeze | FIN | Awards | Legacy |  | Grant Invoicing/Billing (minus Dec payroll in Workday - 12/16-12/31) - Invoice will be in January | 2020-12-23 |  | 2020-12-31 | Casey St. Clair/SPS | [5 empty] | Coordinate with ITD process - 01/08/2021
| 4. Post-Cutover | Soft Freeze/Hard Freeze | FIN | Grants | Legacy |  | Last day to enter Z sheets (invoices) batch in receivables into PeopleSoft (A/R) | 2020-12-23 |  | 2020-12-31 | Carrie Johnston/Christine Galbreath
| 4. Post-Cutover |  | FIN | A/R - Sponsored | Legacy |  | Sponsor payments for invoices will be held from 12/24 to 12/31 will be held and entered into Workday on or after 01/01 | 2020-12-23 |  | 2021-01-01 | Christine Galbreath, Carrie Johnston | [5 empty] | CPM: Date determined based on Internal Closing Schedule for FY2020
| 4. Post-Cutover | Critical Date | FIN |  | Legacy | Christine to follow up with SPS | Cash disbursement transaction for final legacy payroll | 2020-12-24 |  | 2020-12-24 | SPS
| 4. Post-Cutover | Hard Freeze | FIN | Grants | Legacy |  | Last LOC Drawdown | 2020-12-24 |  | 2020-12-24 | Kim Akin/Christine Galbreath | [5 empty] | Likely, draw for last payroll period (12/15/2020) and freeze after that until after go-live.
| 4. Post-Cutover | Cutover Team | TECH |  | Legacy |  | Decommission legacy systems as appropriate | 2020-12-26 |  | 2020-12-26 | Brant Schroeder, Mike Corwin
| 4. Post-Cutover |  | HCM | Benefits |  |  | True up Workday to TIAA Seed File (any VIP/VIP Roth Changes) | 2020-12-28 |  | 2020-12-28 | Ann Monroe
| 4. Post-Cutover | Delta Load | TECH | Conversion | Extracts |  | Load Finance Delta Load Transactions from 12/23/2020 snapshot | 2020-12-28 |  | 2020-12-31 | Brad Dudra/Keerthinath Manoharan
| 4. Post-Cutover | Post Launch | TECH | Conversion | Workday |  | Load Awards, Purchase Orders from 12/23 Snapshot (Capital Assets - TBD) | 2020-12-28 |  | 2020-12-31 | Brant Schroeder, Jane Thomas
| 4. Post-Cutover |  | FIN | Controller | Legacy |  | Reconcile state draw and record true up entry | 2020-12-29 |  | 2020-12-29 | Tami Bidle, Chris Conway
| 4. Post-Cutover | Post Launch | HCM | Conversion | Workday |  | Process Open Enrollment Change File From HCA due evening of 12/28 and load changes to Workday (Health-Medical/Dental/Tobacco/Spousal Surcharges and Dependents) | 2020-12-29 |  | 2020-12-31 | Brad Dudra/Jemima Joseph
| 4. Post-Cutover | Manual - UI | FIN | Gifts/Endowments | Workday |  | Add gift GF004157 - necessary for ITD processing | 2020-12-30 |  | 2020-12-31 | Joan Willmotte
| 4. Post-Cutover | Manual - UI | FIN | Gifts/Endowments | Workday |  | Add gift GF005325/72464421 - necessary for ITD processing | 2020-12-30 |  | 2020-12-31 | Joan Willmotte
| 4. Post-Cutover |  | FIN | A/R |  | Decision | eCommerce (i.e. Student Payments) | 2020-12-31 |  | 2020-12-31 | George Rhodes/Clint McGregor |  |  |  |  | George Rhodes/Clint McGregor
| 4. Post-Cutover | Hard Freeze | FIN | A/R | Legacy |  | Last day for receipts for goods or services sold by a department | 2020-12-31 |  | 2020-12-31 | George Rhodes/Clint McGregor
| 4. Post-Cutover | Pre-Financial | FIN | ITD/Budget/GL | Workday |  | FY21 Core Budget - EIB - Budget | 2020-12-31 |  | 2020-12-31 | Chris Conway/Jodi Heins
| 4. Post-Cutover | Post Launch | FIN | ITD/Banking | Workday |  | Cash Balances - EIB - ITD Beg Balance Cash | 2020-12-31 |  | 2021-01-01 | Joan Wilmotte/Ed Nieskes
| 4. Post-Cutover | Post Launch | FIN | ITD/Banking | Workday |  | Execute tasks on Banking ITD | 2020-12-31 |  | 2021-02-05 | Joan Wilmotte/Ed Nieskes
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st outbound TIAA INT009b Census/Enrollment | 2021-01-01 |  | 2021-01-01 | Wendy Weber
| 4. Post-Cutover | Critical Date | HCM | Benefits | Workday |  | TIAA Starts Accepting VIP/VIP Roth Changes in their portal | 2021-01-01 |  | 2021-01-01 | Wendy/TIAA
| 4. Post-Cutover | Integrations | HCM | Compensation | Workday |  | INT169 - Workday - PID Salary Progression - Boomerang | 2021-01-01 |  | 2021-01-01 | Joe Wagner
| 4. Post-Cutover | Integrations | Payroll | Payroll | Workday |  | INT015 - US Bank - Payroll Positive Pay Cancelled Checks - EIB - Outbound | 2021-01-01 |  | 2021-01-01 | Kim Lawton
| 4. Post-Cutover | Integrations | Payroll | Payroll | Workday |  | INT145 - Social Security - Validation Service - EIB - Outbound | 2021-01-01 |  | 2021-01-01 | Mayra Young
| 4. Post-Cutover |  | FIN | A/R - Sponsored | Workday |  | Sponsor payments can be recorded in Workday but placed on-account until ITD process is completed | 2021-01-01 |  | 2021-01-01 | Christine Galbreath, Carrie Johnston | [5 empty] | CPM: Date determined based on Internal Closing Schedule for FY2020
| 4. Post-Cutover | Integrations | FIN | Banking | Workday |  | INT018 - Bank of America - AP Positive Pay Cancelled Checks - EIB - Outbound | 2021-01-01 |  | 2021-01-01 | Joan Wilmotte
| 4. Post-Cutover | Integrations | FIN | Banking | Workday |  | INT018a - Bank of America - AP Positive Pay Issued Checks - EIB - Outbound | 2021-01-01 |  | 2021-01-01 | Joan Wilmotte
| 4. Post-Cutover | Integrations | FIN | A/P | Workday |  | INT024 - AiM - Supplier Invoicing - EIB - Inbound | 2021-01-01 |  | 2021-01-01 | Kelly Cornish, David Rovetto
| 4. Post-Cutover | Integrations | FIN | A/R | Workday |  | INT077 - Campus Solutions - Student Account Receivables - SI - Inbound | 2021-01-01 |  | 2021-01-01 | Clint McGregor
| 4. Post-Cutover | Integrations | FIN | A/P | Workday |  | INT078 - CBORD FSS - Accounts Payable - SI - Inbound | 2021-01-01 |  | 2021-01-01 | Gail Nash, Clint McGregor
| 4. Post-Cutover | Integrations | FIN | Banking | Workday |  | INT097 - Bank of America - Check Reconciliation - CCF - Inbound | 2021-01-01 |  | 2021-01-01 | Joan Wilmotte
| 4. Post-Cutover | Integrations | FIN | A/P | Workday |  | INT141 - Alma - Supplier Invoices - SI - Inbound | 2021-01-01 |  | 2021-01-01 | David Rovetto, Jennifer Yoshikawa, George Rhodes
| 4. Post-Cutover | Integrations | FIN | Banking | Workday |  | INT152 - Bank of America - ACH - CCP - Outbound | 2021-01-01 |  | 2021-01-01 | Joan Wilmotte
| 4. Post-Cutover | Integrations | FIN | A/R | Workday |  | INT179 - Ecommerce | 2021-01-01 |  | 2021-01-01 | Clint McGregor
| 4. Post-Cutover | Integrations | FIN | A/R | Workday |  | INT180 - ECSI | 2021-01-01 |  | 2021-01-01 | Clint McGregor
| 4. Post-Cutover | Integrations | FIN | A/P | Workday |  | INT061 - Oracle WebCenter - Supplier Invoice Imaging - EIB - Inbound | 2021-01-01 |  | 2021-01-01 | George Rhodes
| 4. Post-Cutover | Integrations | FIN | A/P | Workday |  | INT099 - Bank of America - ePayable Payments - CCP - Outbound | 2021-01-01 |  | 2021-01-01 | Ken Dragoo
| 4. Post-Cutover |  | FIN | Awards | Legacy |  | Send out final sponsor invoices from AIS | 2021-01-01 |  | 2021-01-31 | Casey St. Clair/SPS | [5 empty] | Coordinate with ITD process - 01/08/2021
| 4. Post-Cutover | Integrations | FIN |  | Workday |  | INT178 - MyResearch | 2021-01-01 |  |  | Carrie Johnston
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st inbound DRS INT053 DCP Inbound | 2021-01-03 |  | 2021-01-03 | Wendy Weber
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st outbound Navia INT050 Enrollment (weekly, thereafter) | 2021-01-04 |  | 2021-01-04 | Wendy Weber
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st outbound WageWorks INT055 Eligibility (weekly, thereafter) | 2021-01-04 |  | 2021-01-04 | Wendy Weber
| 4. Post-Cutover | Integrations | HCM | Compensation | Workday |  | First Workday PID runs on 01/04/2021, effective 01/01/2021 | 2021-01-04 |  | 2021-01-04 | Joe Wagner
| 4. Post-Cutover | Hard Freeze | FIN | Gifts/Endowments | Legacy |  | Last day to buy into an endowment - ACCESS database - effective date of 12/31/2020 | 2021-01-04 |  | 2021-01-04 | Joan Wilmotte
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st inbound DRS INT170 Service Credit Update (continue on 5th of month, monthly) | 2021-01-05 |  | 2021-01-05 | Wendy Weber
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st inbound HCA INT025 Inbound Wellness Reward | 2021-01-05 |  | 2021-01-05 | Steven Perkins
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st inbound Metlife INT048 Billing | 2021-01-05 |  | 2021-01-05 | Steven Perkins
| 4. Post-Cutover | Integrations | Payroll | Payroll | Workday |  | INT068 - Liberty Mutual - Payroll Deductions - SI - Inbound | 2021-01-05 |  | 2021-01-05 | Holly Sigurdsson
| 4. Post-Cutover | Integrations | Payroll | Payroll | Workday |  | INT101 - Tax Navigator - Status Update - SI - Inbound | 2021-01-05 |  | 2021-01-05 | Brandon Cross
| 4. Post-Cutover | Integrations | Payroll | Payroll | Workday |  | INT125 - Combine Fund - Payroll Deductions - SI - Inbound | 2021-01-05 |  | 2021-01-05 | Holly Sigurdsson
| 4. Post-Cutover | Integrations | Payroll | Payroll | Workday |  | INT156 - Payroll Access - Graduate Student Tuition Payroll Deduction Plan - Outbound | 2021-01-05 |  | 2021-01-05 | Holly Sigurdsson
| 4. Post-Cutover | Critical Date | Payroll | Payroll | Workday |  | Time due for first WSU Payroll - Pay date Jan 11 (Monday) | 2021-01-05 |  | 2021-01-05 | Brigham Hubbard, Mel Roberts, Benjamin Howard /Payroll | [5 empty] | Payroll complete 3 business days before payday
| 4. Post-Cutover | Critical Date | Payroll | Payroll | Workday |  | Process first WSU Payroll - Pay date Jan 11 (Monday) | 2021-01-05 |  | 2021-01-07 | Brigham Hubbard, Mel Roberts, Benjamin Howard /Payroll | [5 empty] | Payroll complete 3 business days before payday
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st outbound TIAA INT009a Remittance (continue 3 business days before check date, thereafter) | 2021-01-06 |  | 2021-01-06 | Wendy Weber
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st outbound HCA INT016 Remittance (continue on 3 business days before check date) | 2021-01-07 |  | 2021-01-07 | Steven Perkins
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st outbound Health Equity INT065 Contributions (continue 3 business days before check date, thereafter) | 2021-01-07 |  | 2021-01-07 | Steven Perkins
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st outbound Metlife INT049 Remittance | 2021-01-07 |  | 2021-01-07 | Steven Perkins
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st outbound Navia INT011 Remittance (continue 2 business days before check date, thereafter) | 2021-01-07 |  | 2021-01-07 | Wendy Weber
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st outbound OFM INT186 All files (continue 3 business days before check date, thereafter) | 2021-01-07 |  | 2021-01-07 | Wendy Weber
| 4. Post-Cutover | Integrations | Payroll | Payroll | Workday |  | INT012 - WFSE - Union Dues Remittance - EIB - Outbound | 2021-01-07 |  | 2021-01-07 | Kim Lawton
| 4. Post-Cutover | Integrations | Payroll | Payroll | Workday |  | INT013 - Liberty Mutual - Remittance Details - EIB - Outbound | 2021-01-07 |  | 2021-01-07 | Holly Sigurdsson
| 4. Post-Cutover | Integrations | Payroll | Payroll |  |  | INT015a - US Bank - Payroll Positive Pay Issued Checks - EIB - Outbound | 2021-01-07 |  | 2021-01-07 | Kim Lawton
| 4. Post-Cutover | Integrations | Payroll | Payroll | Workday |  | INT067 - VEBA - Contributions - EIB - Outbound | 2021-01-07 |  | 2021-01-07 | Jackie Meyer
| 4. Post-Cutover | Integrations | Payroll | Payroll | Workday |  | INT126 - Combine Fund - Contribution Amounts - EIB - Outbound | 2021-01-07 |  | 2021-01-07 | Holly Sigurdsson
| 4. Post-Cutover | Integrations | Payroll | Payroll |  |  | INT135 - US Bank - Payroll ACH Direct Deposit - CCP - Outbound | 2021-01-07 |  | 2021-01-07 | Kim Lawton
| 4. Post-Cutover | Integrations | Payroll | Payroll | Workday |  | INT138 - myWSU - Workstudy Payroll - Outbound | 2021-01-07 |  | 2021-01-07 | Kim Lawton
| 4. Post-Cutover | Integrations | Payroll | Payroll | Workday |  | INT167 - Tax Navigator - 1042-S - SI - Outbound | 2021-01-07 |  | 2021-01-07 | Brandon Cross
| 4. Post-Cutover | Integrations | Payroll | Payroll | Workday |  | INT190 - Synopsis - Payroll - Outbound | 2021-01-07 |  | 2021-01-07 | Benjamin Howard
| 4. Post-Cutover | Critical Date | Payroll | Payroll | Workday |  | Workday Payroll Processing Completes | 2021-01-07 |  | 2021-01-07 | Brigham Hubbard, Mel Roberts, Benjamin Howard /Payroll
| 4. Post-Cutover | Integrations | FIN | Banking | Workday |  | INT007 - US Bank - Account Reconciliation - CCF - Inbound | 2021-01-07 |  | 2021-01-07 | Joan Wilmotte
| 4. Post-Cutover | Integrations | FIN | General Accounting | Workday |  | INT017 - OFM - Revenue and Expenditure - EIB - Outbound | 2021-01-07 |  | 2021-01-07 | Chris Conway
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st outbound DRS INT054 Remittance/ERA MRL | 2021-01-08 |  | 2021-01-08 | Wendy Weber
| 4. Post-Cutover | Integrations | FIN | Gifts/Endowments | Workday |  | INT085 - Advance - Endowment Stewardship Reports - EIB - Outbound | 2021-01-08 |  | 2021-01-08 | Joan Wilmotte
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - CCT_JRNLS_GRNTS_FIXED_CS.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_FIXED_EX_1.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_FIXED_EX_1R.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_FIXED_EX_2.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_FIXED_EX_2R.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_LOC_CS.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_LOC_EX_1.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_LOC_EX_1R.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_LOC_EX_2.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_LOC_EX_2R.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_NONLOC_CS.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_NONLOC_EX_1.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_NONLOC_EX_1R.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_NONLOC_EX_2.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_NONLOC_EX_2R.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_PIA_EX.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Grants | Workday |  | Grant Journals - EIB - Grants ITD Journal - ACCT_JRNLS_GRNTS_PIA_EX_R.csv | 2021-01-08 |  | 2021-01-15 | Christine Galbreath, Nigel Chong-You
| 4. Post-Cutover | Integrations | FIN | Foundation | Workday |  | INT079 - AccuFund - Foundation Expenditures - EIB - Outbound | 2021-01-08 |  |  | Joan Wilmotte
| 4. Post-Cutover | Critical Date | Payroll | Payroll | Workday |  | First WSU Workday Paycheck | 2021-01-11 |  | 2021-01-11 | Brigham Hubbard, Mel Roberts, Benjamin Howard /Payroll
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st inbound WageWorks Billing INT073 (continue on 15th, monthly, thereafter) | 2021-01-15 |  | 2021-01-15 | Wendy Weber
| 4. Post-Cutover | Post Launch | FIN | ITD/Budget/GL | Workday |  | FY21 Dec Expense Journal - EIB - ITD Journal | 2021-01-15 |  | 2021-01-15 | Chris Conway/Jodi Heins
| 4. Post-Cutover | Post Launch | FIN | ITD/Budget/GL | Workday |  | FY21 Dec Revenue Journal - EIB - ITD Journal | 2021-01-15 |  | 2021-01-15 | Chris Conway/Jodi Heins
| 4. Post-Cutover | Post Launch | FIN | ITD/Gifts | Workday |  | Gifts through Dec 20 - EIB - ITD Donor Contribution - GIFTS_SUBMIT_DONOR_CONTRIBUTION.csv | 2021-01-15 |  | 2021-01-15 | Joan Wilmotte/Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Gifts | Workday |  | Gifts through Dec 20 - EIB - ITD Investment Pool Sale - GIFTS_SUBMIT_INVESTMENT_POOL_PURCH.csv | 2021-01-15 |  | 2021-01-15 | Joan Wilmotte/Nigel Chong-You
| 4. Post-Cutover | Post Launch | FIN | ITD/Gifts | Workday |  | Gifts through Dec 20 - EIB - ITD Gift Investment Statement - GIFTS_SUBMIT_INVESTMENT_STATEMENT.csv | 2021-01-15 |  | 2021-01-15 | Joan Wilmotte/Nigel Chong-You
| 4. Post-Cutover |  | HCM | Benefits | Workday |  | Check Retired/Deceased that with former SRP before OSA report and update personal Info for DOB/SSN | 2021-01-15 |  | 2021-02-01 | Wendy Weber
| 4. Post-Cutover | Post Launch | FIN | ITD/Banking | Workday |  | Outstanding Checks - EIB - ITD Outstanding Checks | 2021-01-15 |  | 2021-02-05 | Joan Wilmotte/Ed Nieskes
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 2nd outbound TIAA INT009b Census/Enrollment (continue on 1st and 16th, monthly) | 2021-01-16 |  | 2021-01-16 | Wendy Weber
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st TIAA INT014 Inbound VIP/VIP Roth Changes for 1/25 check (7 days ahead of check date) | 2021-01-18 |  | 2021-01-18 | Wendy Weber
| 4. Post-Cutover | Integrations | HCM | Benefits | Workday |  | Process 1st "inbound" HCA INT093 Billing Reconciliation (continue on the 20th of month, monthly) | 2021-01-20 |  | 2021-01-20 | Wendy Weber
| 4. Post-Cutover | Critical Date | FIN | Banking | Legacy |  | December Bank Reconciliations Completed and adjustments entered thru 12/31/2020 | 2021-01-22 |  | 2021-01-22 | TBD | [5 empty] | Plan to track and monitor and settling of all requisitions - CPM: Discussed with Robert Wright.
| 4. Post-Cutover | Integrations | HCM | Compensation | Workday |  | INT173 - IPED - HRS - (Connectivity Only) | 2021-01-31 |  | 2021-01-31 | Joe Wagner
| 4. Post-Cutover | Integrations | Payroll | Payroll | Workday |  | INT176 - Tax Navigator - 1042S AP | 2021-02-01 |  | 2021-02-01 | Brandon Cross
| 4. Post-Cutover |  | FIN | ITD/Beginning Balances | Legacy |  | Bank deposits posted - Outstanding checks and cash balances as of 12/31 - adhoc load for oustanding checks | 2021-02-01 |  | 2021-02-01 | Joan Wilmotte
| 4. Post-Cutover | Critical Date | TECH |  | Workday |  | IMPL Tenants Deletion | 2021-02-04 |  | 2021-02-04 | Kristen Flannery/Mel Roberts | [5 empty] | 60 days after MTP
| 4. Post-Cutover |  | FIN | General Accounting | Workday |  | First Period Close in WD | 2021-02-05 |  | 02/19/1021 | Chris Conway
| 4. Post-Cutover | Integrations | Payroll | Payroll |  |  | INT172 - OFM - Payroll | 2021-02-08 |  | 2021-02-08 | Kim Lawton
| 4. Post-Cutover |  | FIN | Effort Reporting | Legacy |  | Close legacy Effort system | 2021-02-28 |  | 2021-02-28 | Carrie Johnston/Christine Galbreath
| 4. Post-Cutover | Critical Date | TECH |  | Workday |  | IMPL SFTP Deletion | 2021-03-06 |  | 2021-03-06 | Kristen Flannery/Mel Roberts | [5 empty] | 90 days after MTP
| 4. Post-Cutover | Pre-Financial | FIN | ITD/Budget/GL | Workday |  | FY21 Monthly Expense Journals July - Oct - EIB - ITD Journal | TBD |  | 2020-12-31 | Chris Conway/Jodi Heins
| 4. Post-Cutover | Pre-Financial | FIN | ITD/Budget/GL | Workday |  | FY21 Monthly Revenue Journals July - Oct - EIB - ITD Journal | TBD |  | 2020-12-31 | Chris Conway/Jodi Heins
| 4. Post-Cutover | Critical Date | FIN | Controller | Legacy |  | Books close for December FY21 | TBD |  | TBD | George Rhodes/Clint McGregor | [5 empty] | Per Tami Bidle, normally occurs in August.
| 4. Post-Cutover | Integrations | FIN | Grants | Workday |  | INT174 - Advance - WSUF Grants | TBD |  | TBD | Ty Siamanson
| 4. Post-Cutover | Integrations | FIN | Gifts/Endowments | Workday |  | INT175 - Advance - Gift Accounts | TBD |  | TBD | Joan Wilmotte
| 4. Post-Cutover | Integrations | FIN | Gifts/Endowments | Workday |  | INT191 - Advance - Gift Status - RaaS - Outbound | TBD |  | TBD | Joan Wilmotte
| 4. Post-Cutover |  | FIN | General Accounting | Legacy |  | Reconcile legacy FACTS system | TBD |  | TBD | Chris Conway
| 4. Post-Cutover |  | FIN | A/R |  |  | Revenue Transfer Requests | TBD |  | TBD | George Rhodes/Clint McGregor | [5 empty] | CPM: Date determined based on Internal Closing Schedule for FY2020
FY21 Core Budget Create Extract
Create GL Expense Extracts
Create FY20 Rollover Core Budget Extract
Create FY20 Ending Financial Balances Extract
Create Grants ITD Extracts
Create Projects ITD Extracts

## Grouping Index
Section | Grouping | Meaning
1. Preparation for Cutover | Cutover Team | Administrative tasks absent of any data collection or direct tenant manipulation
1. Preparation for Cutover | Pre Catch-Up Activities | Legacy last transactions, freezes, and followup transaction capture
2. Pre-Cutover | Gold Build Configuration | Provision and Configure Tenant
3. Cutover | Gold Build | All Data Conversion for Transactions Transfer
3. Cutover | Tenant Readiness and Validation | Post load data validation and tenant smoke testing
4. Post Cutover | Soft Launch Tasks | WSU Administrator tenant update activities
4. Post Cutover | Catch-Up Activity | Loading all captured data from legacy freeze and updated transactions
4. Post Cutover | Employee Review | Tasking for employees to validate own data following Hard Launch
4. Post Cutover | Closeout | Administrative tasks to close out all but direct data or tenant activities

## Reference Critical Dates
Payroll
Payroll’s cycle dates for November - December) – Legacy: | Dec
November 1 - 15 pay period (payment date November 24)
November 16 -30 pay period (payment date December 10), processed December xx-xx
Payroll’s cycle date for December go-live – in Workday:
Catch up transactions for payroll-impacting transactions after Gold-to-Production transfer completes (12/7 - 12/9) |  | on 12/6/2020
December 1-15 pay period (payment date Dec 24th), processed 16-22 July – with preview calculation audits and comparison tests starting after catch-up transactions completed
Gold (Production) Build
Dates are subject to PMO approval
Gold Tenant Available | 2020-10-12
Gold Configuration | 11/02 - 11/20
Extract Effective Date | 2020-11-20
Extract Validation | 11/22 - 11/24
Gold Conversion | 11/25 - 12/5
HCM Catch-up Transaction Entry | 12/10 - 12/15
Technical Go-Live | 2020-12-06
Go Live* w/ limited Finance transactions available | 2020-12-16
All Finance transactions available | 2021-01-01
*Finance will have a rolling deployment (e.g. ITD balances)

## Project Team Roster
WSU WD Project Team Roster
| Organization | Name | Email | Workthread | Role | Function | FTE | Tent. Start Date | Location | Cell Phone | Desk Phone
| Deloitte | Akriti Agarwal | akriagarwal@deloitte.com | HCM | Recruiting Lead |  | Part-Time | 2019-03-01 | Los Angeles | 213-553-1412 | 3124860782
| Deloitte | Andrew Blakeslee | ablakeslee@deloitte.com | Tech Advisor | Senior Tech Advisor |  | Part-Time | 2018-09-01 | Atlanta | 404-202-3966 | 813-203-5327
| Deloitte | Anupama Yadav | anupyadav@deloitte.com | Change | Training Advisor |  | Part-Time | 2020-02-11 | Mumbai | 470-434-4988 | 470-434-4988
| Deloitte | Bhaswati Das | bhdas@deloitte.com | Change | Training Lead |  | Full-Time | 2019-02-17 | Philadelphia | 209-605-1981 | 3124864338
| Deloitte | Dan Hoover | dahoover@deloitte.com | Sustainment | Sustainment |  | Part-Time | 2019-09-09 | Pleasanton | 415-783-4560 | 415-783-4560
| Deloitte | David Boeker | daboeker@deloitte.com | PMO | Project Manager |  | Full-Time | 2018-09-01 | Sacramento | 510-258-2876 | 480-770-7320
| Deloitte | Deepti Sharma | deeptisharma@deloitte.com | Change | Offshore Training Lead |  | Full-Time | 2019-07-01 | Delhi | 919-871-9646 | 3124862991
| Deloitte | Devin Ruthstrom | druthstrom@deloitte.com | Change | Change Lead |  | Full-Time | 2018-11-01 | Denver | 303-513-3472 | 3124860468
| Deloitte | Ed Nieskes | enieskes@deloitte.com | Financials | Functional Lead |  | Full-Time | 2018-09-01 | Chicago | 262-685-7861 | 470-362-2781
| Deloitte | Hazel D Souza | hadsouza@deloitte.com | Change | Training Developer |  | Full-Time | 2020-07-30 | Mumbai | 678-299-9161 | 678-299-9161
| Deloitte | James Rutkowski | jrutkowski@deloitte.com | Change | Accessibility Advisor |  | Part-Time | 2020-02-11 | USDC - Mechanicsburg | 717-547-2341 | 717-547-2341
| Deloitte | Jane Thomas | jathomas@deloitte.com | Conversion | Conversion Lead |  | Full-Time | 2019-01-01 | Tampa | 352-339-9943 | 312-486-3602
| Deloitte | Jannet Garayua | jgarayua@deloitte.com | Testing | Testing Lead |  | Full-Time | 2019-07-15 | San Diego | 917-284-3845 | 4042201841
| Deloitte | Jay Dumphy | jdumphy@deloitte.com | PMO/ Engagement MD | Engagement Director |  | Part-Time | 2018-09-01 | Chicago | 312-203-1461 | 470-434-8407
| Deloitte | Jemima Joseph | jemjoseph@deloitte.com | Conversion | Conversion - Hoover |  | Full-Time | 2019-02-18 | Bengalaru | 470-434-8407 | 3032944210
| Deloitte | Jhilik Choudhurry | jhchoudhury@deloitte.com | Change | Training Developer |  | Full-Time | 2019-09-09 | Bengalaru | 470-434-7045 | 470-434-7045
| Deloitte | Jim Broucek | jbroucek@deloitte.com | HCM / PMO | Core HR Lead / PMO Support / Recruiting |  | Full-Time | 2018-09-17 | Denver | 303-641-9866 | 303-641-9866
| Deloitte | Jodi Heins | jheins@deloitte.com | Financials | Financial Core Lead |  | Full-Time | 2018-10-22 | Dallas | 512-226-4750 | 480-770-7119
| Deloitte | Julia Weigand | jweigand@deloitte.com | HCM / PMO | HCM Analyst / PMO Support |  | Full-Time | 2020-07-13 | Chicago | 312-486-4717 | 312-486-4717
| Deloitte | Keerthinath Manoharan | kemanoharan@deloitte.com | Conversion | Data Conversion |  | Full-Time | 2019-03-26 | USDC - Phoenix | 480-770-7119 | 3035133472
| Deloitte | Kristen Flannery | kflannery@deloitte.com | Tech | Tech Lead / Int Consultant |  | Full-Time | 2019-03-01 | Denver | 510-876-6240 | 3033053275
| Deloitte | Kyle Babinski | kbabinski@deloitte.com | HCM | HCM Lead |  | Full-Time | 2019-02-01 | Pleasanton | 415-314-2466 | 4157834299
| Deloitte | Lindsay Emer | liemer@deloitte.com | Financials | Procurement/Spend Lead |  | Full-Time | 2019-07-15 | Denver | 720-576-6812 | 509-335-2567
| Deloitte | Meagan Ciccarelli | meciccarelli@deloitte.com | HCM Advisor | Higher Ed SME |  | Part-Time | 2019-01-01 | Chicago | 312-292-8320 | 509-335-2367
br | Deloitte | Mel Roberts | meroberts@deloitte.com | Payroll | Payroll Lead |  | Full-Time | 2019-01-01 | Denver | 719-203-8458 | 509-335-4943
| Deloitte | Nasiruddeen "Ahmad" Tariq | ntariq@deloitte.com | Change | Communications Lead |  | Full-Time | 2019-07-15 | Wash DC | 301-323-3197 | 509-335-3663
| Deloitte | Nigel Chong-You | nchongyou@deloitte.com | Financials | Grant Lead |  | Full-Time | 2019-01-01 | Miami | 786-858-3424 | 509-335-3765
| Deloitte | Paulo Pagsambugan | ppagsambugan@deloitte.com | Testing | Testing Lead Support |  | Full-Time | 2019-07-29 | Sacramento | 916-893-7701 | 509-335-3941
| Deloitte | Renae Ebert | rebert@deloitte.com | Financials/ FDM Advisor | Higher Ed SME |  | Part-Time | 2018-09-01 | Chicago | 312-617-5138 | 509-335-3967
| Deloitte | Samantha Knighton | sknighton@deloitte.com | HCM/Recruiting Advisor | Recruiting SME |  | Part-Time | 2018-09-01 | Charlotte | 704-227-7958 | 509-335-4868
| Deloitte | Shalini Birla | sbirla@deloitte.com | Change | Offshore Training Lead |  | Full-Time | 2020-02-17 | Mumbai | 678-299-7356 | 678-299-7356
| Deloitte | Shawn Ismail | shismail@deloitte.com | HCM | Compensation Lead |  | Full-Time | 2019-01-01 | New York | 469-417-2223 | 509-335-4945
| Deloitte | Stacy Zhong | stzhong@deloitte.com | Change | Change Management Lead |  | Full-Time | 2018-12-01 | Sacramento | 916-204-0957 | 509-335-3955
| Deloitte | Suraj Kolimi | skolimi@deloitte.com | HCM | Benefits Lead |  | Full-Time | 2019-10-08 | USDC - Orlando | 347 802 6051 | 571-777-4891
| Deloitte | Sydney MacBain | smacbain@deloitte.com | HCM | Time and Absence Lead |  | Full-Time | 2018-10-22 | Pleasanton | 925-586-5463 | 347-802-6051
| Deloitte | Thresa Skeslien Jenkins | tskeslienjenkins@deloitte.com | HCM | HCM Analyst / PMO Support |  | Full-Time | 2019-09-09 | Houston | 713-982-2707 | 714-436-7990
| Deloitte | Wilson Ye | wilsye@deloitte.com | Financials | Financial Business Tech Analyst |  | Full-Time | 2019-02-25 | Seattle | 714-658-4933 | 713-982-2707
| WSU | Alexander Saari | alexander.saari@wsu.edu | Technology | IS Techno Strategist | Reporting | Full-Time | 2019-06-01 | Pullman | 906-281-8510 | 509-335-1836
| WSU | Annie Riedinger | a.riedinger@wsu.edu | Change | Organizational Change Management Lead |  | Full-Time |  | Pullman | 208-310-1606 | 509-335-2567
| WSU | Ashley Matson | ashley.matson@wsu.edu | Financials | Assistant To |  | Full-Time |  | Pullman | 509-432-4943 | 509-335-3025
| WSU | Ben Howard | benjamin.howard@wsu.edu | Financials | Business Analyst |  | Full-Time |  | Pullman | 509-592-0207 | 509-335-2072
| WSU | Bradley Dudra | bradley.dudra@wsu.edu | Technology | App Development - Journey | Integrations | Full-Time | 2018-07-30 | Pullman | 208-305-7059 | 509-335-3955
| WSU | Brant Schroeder | brant@wsu.edu | Technology | Information Systems Manager | Conversion & Integration | Part-Time |  | Pullman | 208-310-1212 | 509-335-0688
| WSU | Bringham Hubbard | bwhubbard@wsu.edu | Financials | Payroll Work Stream Lead |  | Full-Time |  | Pullman | 208-874-2243 | 509-335-2367
| WSU | Bryan Titen | bryan.titen@wsu.edu | Technology | Application Systems Analyst/Developer | Conversions | Part-Time |  | Remote | 818-298-3903
| WSU | Caleb Ericson | caleb.ericson@wsu.edu | Technology | Business Intelligence | Business Intelligence | Part-Time |  | Pullman | 208-284-4046 | 509-335-0633
| WSU | Cameron Zapf | cameron.zapf@wsu.edu | Technology | Data Architecture/Database Admin | Reporting | Part-Time |  | Remote |  | 509-335-5663
| WSU | Carrie Johnston | carriej@wsu.edu | Financials | Grants Work Stream Lead |  | Full-Time |  | Pullman | 509-552-9369 | 509-335-3627
| WSU | Chad Jeffreys | jeffreys@wsu.edu | Technology | Application Systems Analyst/Developer | Integrations | Part-Time |  | Pullman | 509-429-5588 | 509-335-5160
| WSU | Chris Conway | chris.conway@wsu.edu | Financials | Business Analyst |  | Full-Time |  | Pullman | 206-227-1751 | 509-335-3785
| WSU | Christine Galbreath | christine.galbreath@wsu.edu | Financials | Business Analyst |  | Full-Time |  | Pullman | 541-510-4942 | TBD
| WSU | Clint McGregor | clint.mcgregor@wsu.edu | Financials | Business Analyst |  | Full-Time |  | Pullman | 701-220-4048 | 509-335-3974
| WSU | Corinna Lo | corinna@wsu.edu | Technology | Reporting |  | Part-Time | 2019-02-01 | Pullman | 208-301-3013 | 509-335-1720
| WSU | Daniel Ornelas | daniel.ornelas@wsu.edu | Technology | Data Conversion | Data Conversion | Part-Time |  | Pullman | 907-306-8057 | 509-335-0969
| WSU | Dave Whelchel | whelchel@wsu.edu | Technology | Security | Security | Part-Time |  | Pullman | 509-336-4731
| WSU | David Rovetto | david.rovetto@wsu.edu | Financials | Procurement |  | Full-Time |  | Pullman | 208-473-1082 | 509-335-3701
| WSU | David Whelchel | whelchel@wsu.edu | Technology | Director Information Services | Conversions | Part-Time |  | Pullman |  | 509-335-5141
| WSU | Dawn Sparks | sparksd@wsu.edu | Technology | Data Conversion | Data Conversion | Part-Time |  | Pullman | 208-301-8008 | 509-335-1696
| WSU | Dora Tilles | dora.tilles@wsu.edu | HRS | Business Analyst - Time, Leave & Absence |  | Full-Time | 2020-03-16 | Pullman | 605-877-5152 | 509-335-1905
| WSU | Emily Akin | emily.akin@wsu.edu | Change | Change |  | Full-Time |  | Pullman | 971-232-7811 | 509-335-4889
| WSU | Emily Bailes | e.bailes@wsu.edu | Change | Change |  | Full-Time |  | Pullman | 360-224-5410 | 509-335-1720
| WSU | Emily Goodwin | emily.goodwin@wsu.edu | HRS | Business Analyst - Absence |  | Full-Time | 2019-06-24 | Pullman | 208-699-1283 | 509-335-6995
| WSU | George Rhodes | george.rhodes@wsu.edu | Financials | Procurement Work Stream Lead |  | Full-Time |  | Pullman | 509-553-3814 | 509-335-4945
| WSU | Gerik Kimble | gerik_kimble@wsu.edu | Financials | Asst. Dir Fin Systems Modernization |  | Full-Time |  | Pullman | 509-595-0558 | 509-335-1747
| WSU | Gunjan Sinha | sinha@wsu.edu | Technology | Systems Architecture | Systems Architecture | Part-Time |  | Pullman | 509-336-9130 | 509-335-3834
| WSU | Jasen Skelton | jasen_skelton@wsu.edu | Technology | Integrations | Integrations | Part-Time |  | Pullman | 509-254-1957 | 509-335-1747
| WSU | Jason Stucki | stucki@wsu.edu | Financials | Reporting |  | Full-Time |  | Pullman | 2008-310-2911 | 509-335-4624
| WSU | Jay Maylor | jay@wsu.edu | Technology | Data Conversion | Data Conversion | Part-Time |  | Pullman | 509-595-3080 | 509-335-7097
| WSU | Jennifer Klein | kleinj@wsu.edu | HRS | Director - HRMS |  | Full-Time |  | Mt Pleasant | 440-935-1610 | NA
| WSU | Jim Lowery | jlowery@wsu.edu | HRS | Business Anlayst - HCM Core |  | Full-Time | 2018-08-01 | Pullman | 253-304-5910 | 509-335-3701
| WSU | Joan Wilmotte | joan.wilmotte@wsu.edu | Financials | Business Analyst |  | Full-Time |  | Pullman | 509-217-2125 | 509-335-5663
| WSU | Joe Wagner | joe.wagner@wsu.edu | HRS | Business Analyst - Compensation |  | Full-Time | 2018-10-01 | Pullman | 208-305-5236 | 509-335-3627
| WSU | Joel Erickson | joel.erickson@wsu.edu | Technology | App Development - Journey | Integrations | Part-Time |  | Pullman | 425-647-0849 | 509-335-0645
| WSU | John Ericson | john.ericson@wsu.edu | Technology | Business Intelligence | Business Intelligence | Part-Time |  | Remote | 425-647-0849 | 509-335-5683
| WSU | Jonathan Lee | jonathan.lee@wsu.edu | HRS | Project Specialist |  | Full-Time | 2018-11-01 | Pullman | 909-697-7622 | 509-335-4889
| WSU | Josh Snook | jisnook@wsu.edu | Technology | Integrations/Conversions | Integrations | Part-Time |  | Pullman | 509-715-7779 | 509-335-9758
| WSU | Joy Morton | joy.morton@wsu.edu | Financials | Director Financial Systems Modernization |  | Full-Time |  | Pullman | 509-295-7233 | 509-335-3834
| WSU | Justin Hughes | justin.hughes@wsu.edu | Technology | Integrations | Integrations | Part-Time |  | Pullman | 208-596-5490 | 509-335-0637
| WSU | Karl Riley | karl.riley@wsu.edu | Technology | Data Conversion | Data Conversion | Part-Time |  | Pullman | 208-310-3064 | 509-335-1167
| WSU | Kameron Olsen | kameron.olsen@wsu.edu | Financials | Business Analyst |  | Full-Time | 2020-05-18 | Pullman | 509-948-0429
| WSU | Ken Dragoo | krdragoo@wsu.edu | Financials | Procurement |  | Full-Time |  | Pullman | 509-607-2304 | 509-335-0645
| WSU | Kohdy Pierce | kohdy.pierce@wsu.edu | Technology | Security - Journey | Security | Full-Time | 2018-09-28 | Pullman | 575-313-9657 | 509-335-5683
| WSU | Maria Gutierrez | mmgutierrez@wsu.edu | Technology | Integrations | Integrations | Part-Time |  | Pullman | 509-432-8330 | 509-335-6968
| WSU | Mark Schemmer | mark.schemmer@wsu.edu | Technology | Business Intelligence/Data Conversion | Business Intelligence | Part-Time |  | Pullman | 360-632-9730 | 509-335-9399
| WSU | Matt Skinner | skinnerm@wsu.edu | Financials | AVP Financial Services |  | Full-Time |  | Pullman | 208-310-0988 | 509-335-9875
| WSU | Michael Echanove | echanove@wsu.edu | Technology | Business Intelligence | Business Intelligence | Part-Time |  | Pullman | 509-288-2010 | 509-335-0512
| WSU | Mike Corwin | michael.corwin@wsu.edu | Technology | Associate VP | Technology | Part-Time |  | Remote | 352-222-7953 | 509-335-0018
| WSU | Noel Ellsworth | noel.ellsworth@wsu.edu | Technology | Integrations | Integrations | Part-Time |  | Pullman | 435-704-1689 | 509-335-1701
| WSU | Sabrina McPherson | sabrina.mcpherson@wsu.edu | HRS | Business Analyst - HCM Lead |  | Full-Time |  | Pullman | 360-281-8690 | 509-335-2026
| WSU | Shane Smith | sa.smith@wsu.edu | Technology | Integrations | Integrations | Part-Time |  | Pullman | 208-596-5844 | 509-335-7337
| WSU | Stacy Combs | combssc@wsu.edu | Technology | Data Conversion/Integrations | Data Conversion | Part-Time |  | Pullman | 509-432-6214 | 509-335-2039
| WSU | Stephanie Lamoureux | stephanie.lamoureux@wsu.edu | HRS | Principal Assistant - HRMS |  | Full-Time | 2018-05-07 | Pullman | 360-710-6876 | 509-335-3785
| WSU | Steven Perkins | steven.perkins@wsu.edu | HRS | Business Analyst - Benefits |  | Full-Time | 2019-12-01 | Pullman | 907-388-4827 | 509-335-2740
| WSU | Tiffany DeMeerleer | theath@wsu.edu | Technology | Assistant To |  | Full-Time | 2018-07-23 | Pullman | 509-330-2181 | 509-335-6953
| WSU | Tom Woods | woodstm@wsu.edu | Technology | Software Integration Architecture - Senior | Systems Architecture | Full-Time |  | Pullman | 509-432-1613 | 509-335-7371
| WSU | Trent Nelson | trent.nelson@wsu.edu | Technology | App Development - Senior | Integrations | Full-Time |  | Pullman | 208-596-0410 | 509-335-6951
| WSU | Ty Simanson | tasimanson@wsu.edu | Financials | [5 empty] | 509-592-6875 | 509-335-6953
| WSU | Vacant |  | Change | Training Coordinator |  | Full-Time
| WSU | Vacant (Beam) |  | Technology |  |  | Full-Time |  | Pullman
| WSU | Vacant (Thuse) |  | Technology |  |  | Full-Time |  | Pullman
| WSU | Vacant (Tunnicliff) |  | Technology | Integrations | Integrations |  |  | Pullman |  | 509-335-6951
| WSU | Wendy Funke | wendy.a.funke@wsu.edu | Financials | Principal Assistant |  | Full-Time |  | Pullman | 509-330-0647
| WSU | Wendy Weber | wendy.weber@wsu.edu | HRS | Business Analyst - Benefits Lead |  | Full-Time | 2018-02-12 | Pullman | 480-529-2566 | 509-335-3974
Note on I4: Boeker, David: Always cofirm with PM for latest

## DNU - WSU Cutover Key Dates
Project Domain | What | Description | Key Dependencies | Proposed Date
Awards | 2. Pre-Cutover | Communicate anything not completely closed will convert | Steering Committee |  | Go/No-Go Decision
Awards | Award Setup | Communicate that awards must be setup on guarantee for anything after 5/29/20. Or will be held and manually setup in WD
Awards | Award Closure | Communicate anything not completely closed will convert
Awards | ETR | Communicate to dept that last day to receive ETRs is 6/30. SPS has until 7/7
Payroll | Payroll on Grants | Communicate to dept last day for EAAs and Retros, giving PR enough time for data entry
Awards | FACTS | Communicate to dept and SPS last day for FACTS updates
Awards | New Subrecipients | Communicate last day for entering new subrecipients
Awards | Batch Peoplesoft Receivables | Communicate last day to enter Z sheets
Compensation | EEs with > 11 days of LWOP (along with other criteria) | Will need to identify the EE population that has taken > 11 days of LWOP to dock their Progression Start Date and exclude them from the PID integration. | Absence Team identifying this population. | 2020-06-22
Absence | LOA extract snapshot | Load employees on LOA's from ERDB snapshot for extract | Receiving info from Kendra from ERDB database | 2020-05-25
Absence | Leave balances extract | Leave balances extract | Receiving correct info from departments, depends on date that we request the balances
Absence | LOA Time Offs extract | Capturing time offs that are related to LOA's. Hours used in ERDB | Receiving info from Kendra from ERDB database | 2020-05-25
Absence | Leave entitlements extract | Leave entitlements and what has been used towards overall entitlement | Receiving info from Kendra from ERDB database | 2020-05-25
Absence | Custom Field extract | Load custom field info from ERDB database | Receiving info from Kendra from ERDB database | 2020-05-25
Conversion | AIS extract snapshot | Create snapshot for data warehouse for Workday extracts | Steering Committee
Core Hr | Capture AIS Transactions | Begin capturing all transactions (by the Depts and HRS) that would normally be captured by AIS. |  | 6/1/2020 - 6/20/2020
Recruitment |  | OPDRS job postings are closed. |  | 2020-06-29
Recruitment | 3. Cutover | New recruitment efforts are conducted in Workday. |  | Move To Production | Soft Launch | 2020-12-06 | 2020-12-06
Recruitment | 3. Cutover | New recruitment efforts are conducted in Workday. |  | Official GO-LIVE | Workday Live | 2020-12-16 | 2020-12-16
Recruitment | 3. Cutover
Expenses | CTA payment | CTA Last day to pay JPMC. Payment to JPMC will not be made from 6/16-6/30. | None. | 2019-06-15
Expenses | Facilities Fuel Card payment | Facilities: Last day to pay Comdata. Next payment on 7/1 from Workday. | None. | 2019-06-15
Expenses | Central Fuel Card payment | Central Fuel: Last day to pay Comdata. Next payment on 7/1 from Workday. | None. | 2019-06-15
Procurement | PaymentNet | Remove access to reconcile transactions in PaymentNet for PCards. | None. | 2019-06-16
Expenses | PaymentNet | Remove access to reconcile transactions in PaymentNet for CTAs. | None. | 2019-06-16
Expenses | Cash Advances | Last day to request a cash advance. Temporary policy change for request timelines and check issues may be needed. | None. | 2019-06-05
Expenses | Travel Expense Voucher | Remove ability to create new TEVs and remove ability to route TEVs to Travel Services. | None. | 2019-06-16
3. Cutover
4. Post-Cutover
Jason Stucki
|  | Critical Date |  |  | Workday Payroll Processing Completes |  |  | Brigham Hubbard
|  | Critical Date |  |  | First WSU Workday Paycheck | 2021-01-11 | 2021-01-11 | Brigham Hubbard

## DNU - WSU Catch Up Activities
Project Domain | What | Capture Method | Who? | Description | Volume Estimate
Compensation | Request Compensation Change | Report from AIS | IT | All compensation changes entered in AIS after the extract date. | 100 or less
Compensation | Request One-Time Payment | Report from AIS | IT | All one-time payments entered in AIS as Piece Rate after the extract date. | 20 or less
Compensation | Period Activity Pay | Report from AIS | IT | All summer appointments, coaching activities, [and other PAP use cases determined by Joe/Hally] entered in AIS after the extract date. | 200 - 250
Compensation | Request Post-Term Compensation | Report from AIS | IT | All EEs that are retired after the extract date and will be receiving TIAA supplementation moving forward. | 20 or less
Time Tracking | Work schedules | Spreadsheet from departments | Departments | Need to track any changes in schedules for individuals who change their schedule after our ask date | unknown - approx 100?
Absence | Cyclic Leave | Spreadsheets from Central and departments | Central HR, departments | Track any cyclic employees who will go on cyclic leave between the time we request and when we launch | unknown - approx 200?
Absence | Time off balances | Paper Time Card? | Departments | Need to collect and load Annual, sick, personal holiday, miliary leave used, LWOP that has happened between the time we request balances and load them into the system | All WSU employees | TBD on actual dates and capture method - may need to capture these at a later date in order to prevent as much adjustment
Absence | Change Jobs | Spreadsheet | Departments, Recruiting | Catch up on Change jobs for changes with accruals | unknown - approx 100? | Need to make sure that if there are any job changes after the 15th that change accruals, they are captured
Absence | LOA events | Spreadsheet from ERDB | DS | LOA events catch up from time extract is pulled to launch | approx 20 total
Absence | LOA time offs | Spreadsheet from ERDB | DS | Capturing time offs that are related to LOA's. Hours used in ERDB | approx 20 total
Absence | Custom Field load | Spreadsheet from ERDB | DS | Catch up on Custom fields load | approx 20 total
Absence | Leave entitlements | Spreadsheet from ERDB | DS | Leave entitlements and what has been used towards overall entitlement | approx 20 total
Absence | Trackers | Add Shared Leave Tracker, Parental Leave Tracker, Floating Holidays Tracker for FMLA | DS | Need to add the trackers onto each persons account to track accordingly | unknown - approx 20?
Core Hr | Future-Dated Transactions | Report from AIS |  | All future-dated transactions in AIS before and after the extract date
Core Hr | Job Titles | Report from AIS |  | All Job Titles entered into AIS after the extract date
Core Hr | Hire/Add Job/Change Job | EIB | HRS | All new appointments entered into AIS/PERMS/TEMPS after the extract date
Core Hr | Change Job | EIB | HRS | All appointment title, fte, etc. changes entered into AIS/PERMS/TEMPS after the extract date
Compensation | Compensation | EIB | HRS | All comp changes entered into AIS/PERMS/TEMPS after the extract date
Core Hr | Position Restrictions | EIB | HRS | All position changes entered into AIS after the extract date
Core Hr | Org | EIB | HRS | All supervisory org, term, costing, etc changes entered into AIS/PERMS/TEMPS after the extract date
Payroll | Direct Deposit |  | IT Payroll | All elections entered into AIS after the final conversion extract date | @250 per month in summer
Payroll | W4 |  | IT Payroll | W4: All elections entered into AIS after the final conversion extract date. | varies significantly @100 per month in summer
Payroll | New 2020 W4's | Spreadsheet or code Payroll will use to report more easily on these | Payroll |  | Not sure
Payroll | Deduction, elective |  |  | All elections entered into AIS after the final conversion extract date.
Payroll | Lock in Letters | Manually keeping these up to date | Modernization Payroll
Payroll | Garnishments | Manually keeping these up to date | Modernization Payroll |  | @6 per month
Payroll | Tax Treaties | Spreadsheet | Modernization Payroll |  | few if any during summer
Supplier Accounts | Suppliers | N/A | Accounts Payable | After 6/5/20, new suppliers will need to be entered into WD directly
Supplier Contracts | Supplier Contracts | N/A | CREO & Purchasing | After 6/15/20, new supplier contracts will need to be entered into WD directly
Procurement | Load PCard VCF files. | Retain VCF files in JPMC integration location. | Modernization | Load PCard VCF files from 6/15 through 6/30 into Workday. | 15 files.
Procurement | Settle PCard transactions. | n/a | Accounts Payable/Treasurey | After VCF files are loaded, run settlement of PCard transactions. | $2.5M.
Expenses | Load CTA VCF files. | Retain VCF files in JPMC integration location. | Modernization | Load CTA VCF files from 6/15 through 6/30 | 15 files.
Expenses | Settle CTA transactions. | n/a | Accounts Payable/Treasurey | After VCF files are loaded, run settlement of CTA transactions. | $0.5M.
Expenses | Load Facilities Fuel Card CDF files. | Retain CDF files in Comdata integration location. | Modernization | Load Facilities Fuel Card CDF files from 6/1 through 6/30 into Workday. | 1 file.
Expenses | Settle Facilities Fuel Card transactions. | n/a | Accounts Payable/Treasurey | After Facilities Fuel Card CDF files are loaded, run settlement of Facilities Fuel Card transactions. | $10k.
Expenses | Load Central Fuel Card CDF files. | Retain CDF files in Comdata integration location. | Modernization | Load Central Fuel Card CDF files from 6/1 through 6/30 into Workday. | 1 file.
Expenses | Settle Central Fuel Card transactions. | n/a | Accounts Payable/Treasurey | After Central Fuel Card CDF files are loaded, run settlement of Central Fuel Card transactions. | $10k.
Expenses | Cash Advances | Shadow systems. | Travel Services/Sponsored Programs | Load Cash Advances and a receivable.

## WSU Cutover Draft 1 (hidden)
Function | Workstream | Section | Grouping Index | Task Name | Duration | Start | Finish | Predecessors | Assigned To | Impacts | % Complete | Status | Comments
PMO | PMO |  |  | Tasks Initiating Week of November 2 (or before) |  |  |  |  | WSU Project Management
FIN | Payroll | Pre-Cutover |  | Payroll Compare - CompareEdge |  | 2020-01-01 | 2020-07-01 |  | Mel Roberts/Brigham Hubbard |  |  |  | 10/1/19 - 10/15/19 and 10/16/19 - 10/31/2019
| Steering Committee | Communication | Cutover Process Admin | Communicate discontinuation of HR transactions for dates 6/1/2020 and beyond into TEMPS/PERMS |  | 2020-01-01 | 2020-01-01 |  | WSU Leadership
| Steering Committee | Communication | Cutover Process Admin | Announce cutover plan to department administrators at FA&O meeting. |  | 2020-01-06 | 2020-06-29 |  | Finance | HRS/Departments
| Steering Committee | Communication | Cutover Process Admin | Send email communications of cutover plan to department hiring managers and administrators. |  | 2020-01-06 | 2020-06-29 |  | HRS | HRS/Departments
| Steering Committee | Communication | Cutover Process Admin | Communicate cutover plan for PERMS/TEMPS to Workday (i.e. if hire date is on/after 7/1, input in WD not PERMS/TEMPS). |  | 2020-01-06 | 2020-06-29 |  | HRS | HRS/Departments
HCM | HCM |  |  | Data Cleansing Completed |  | 2020-04-29 | 2020-04-29 |  | Jennifer Klein
HCM | HCM |  |  | List here |  | 2020-02-28 | 2020-02-28 |  | Jennifer Klein
FIN | Finance |  |  | Data Cleansing Completed |  | 2020-04-29 | 2020-04-29 |  | Joy Morton
FIN | Finance |  |  | Supplier Address |  | 2020-02-28 | 2020-02-28 |  | Joy Morton
| Steering Committee | Critical Date | Cutover Process Admin | Finalize WSU Cutover Plan |  | 2020-05-04 | 2020-05-04
PMO | PMO | Critical Date |  | Provision/Staging Gold Tenant | 1d | 2020-05-04 | 2020-05-04 |  | Mel Roberts/Ed Nieskes
TECH | Security |  |  | Create Implementer Accounts in Gold | 1d | 2020-05-05 | 2020-05-05 |  | Akriti Agarwal
PMO | PMO |  |  | Tenant build Activities |  | 2020-05-05 | 2020-05-13
FIN | Finance |  |  | Financials |  | 2020-05-05 | 2020-05-13 |  | Finance Leads
FIN | Finance |  |  | Load Fnancials - FDM
FIN | Finance |  |  | Load Financials - Business Process
FIN | ITD | Post-Cutover |  | Finance team to load 'Inception to Date' balances into Workday | 1d | 2020-07-01 | 2020-07-31 | [5 empty] | CPM: Date determined based on Internal Closing Schedule for FY2018
HCM | HCM |  |  | HCM |  | 2020-05-05 | 2020-05-13 |  | HCM Leads
HCM | HCM |  |  | Job Catalog
FIN | Finance |  |  | Load HCM - Business Process
FIN | Payroll |  |  | Payroll |  | 2020-05-05 | 2020-05-13 |  | Payroll Lead
FIN | Payroll |  |  | Earning Codes
FIN | Payroll |  |  | Load Payroll - Business Process
FIN | GA | Freeze Date |  | Last date to open/close a chart element | 1d | 2020-03-31 | 2020-03-31 |  | Chris Conway | Departments |  |  | CC: 99% of the FDM needs to be complete by then according to the MPP. No chart elements relating to Cost Centers can be open after November. Gift & Grants will need to have the ability to be opened up until near go-live, hence a pre-June 2020 freeze.
FIN | GA |  |  | Last date to submit a journal entry for FY2020 | 1d | 2020-06-30 | 2020-07-07 |  | Chris Conway | Departments |  |  | CC: Gives a few days to reconcile late June payments. Date determined based on Internal Closing Schedule for FY2020
FIN | GA |  |  | Load beginning balances - load Cash Balances into WD | 1d | 2020-07-01 | 2020-07-13 |  | Chris Conway
FIN | GA |  |  | All balance sheet accounts reconciled and adjustments made for FY2020 | 10d | 2020-07-01 | 2020-07-10 |  | Chris Conway
FIN | GA |  |  | Close legacy FACTS system | 1d | 2020-07-10 | 2020-07-10 |  | Chris Conway |  |  |  | CC: Close FACTS for the last time. Date determined based on Internal Closing Schedule for FY2020
FIN | GA |  |  | Period 13 Closes for FY2020 | 1d | 2020-07-15 | 2020-07-15 |  | Chris Conway |  |  |  | CC: Date determined based on Internal Closing Schedule for FY2019
FIN | GA |  |  | Restate beginning balances | 1d | 2020-07-27 | 2020-07-27 |  | Chris Conway
FIN | GA |  |  | First Period Close in WD | 5d | 2020-08-03 | 2020-08-08 |  | Chris Conway
FIN | GA |  |  | Last day for FY20 year end adjustments for financial statements | 1d | 2020-10-26 | 2020-10-26 |  | Chris Conway | Departments
FIN | Reporting |  |  | Books close for FY20, Financial Statements finalized | 1d | 2020-10-30 | 2020-10-30 |  | Chris Conway
FIN | FDM | Freeze Date |  | Open/Close Cost Centers | 5d | 2020-04-06 | 2020-04-10 |  | Hanna Long |  |  |  | JW: FDM Deadline of 5/1/20 for 100% of Cost Centers
FIN | FDM | Freeze Date |  | Open/Close Gifts, Grants, Projects, Programs | 6d | 2020-05-25 | 2020-06-01 |  | Hanna Long |  |  |  | JW: FDM Deadline of 5/1/20 for 100% of Cost Centers
FIN | FDM | Freeze Date |  | Last day to update or create new department | 1d | 2020-04-15 | 2020-04-15 |  | Hanna Long |  |  |  | JW: FDM Deadline of 5/1/20 for 100% of Cost Centers
FIN | FDM | Critical Date |  | Last day to add new value | 1d | 2020-06-05 | 2020-06-05 |  | Hanna Long |  |  |  | Need to have prior to end to end testing and associated Data Governance updated by 10/20/19
FIN | Banking | Critical Date |  | Last Vendor Payment Check Cycle | 1d | 2020-06-30 | 2020-06-30 |  | Joan Wilmotte |  |  |  | GR: Bank recon integration would have to be held until the checks cut in AIS are reconciled.
FIN | Banking | Critical Date |  | June Bank Reconciliations Completed and adjustments entered for FY2020 | 24d | 2020-07-01 | 2020-07-24 |  | Joan Wilmotte |  |  |  | Plan to track and monitor and settling of all requisitions - CPM: Discussed with Robert Wright.
FIN | Banking | Critical Date |  | All bank deposits posted to GL | 7d | 2020-07-01 | 2020-07-07 |  | Joan Wilmotte |  |  |  | CPM: Date determined based on Internal Closing Schedule for FY2018
FIN | Banking | Critical Date |  | Outstanding checks adhoc load | 7d | 2020-07-27 | 2020-07-28 |  | Joan Wilmotte |  |  |  | CPM: Date determined based on Internal Closing Schedule for FY2018
FIN | Expense |  |  | Expense Reports completed and approved | 1d | 2020-06-30 | 2020-06-30 | [5 empty] | GK: Need to be completed and approved by… Need Milestones on when it should be completed
FIN | Procurement | Freeze Date |  | Purchasing Services for Requisitions | 1d | 2020-04-30 | 2020-04-30 |  | George Rhodes |  |  |  | GK: We may not have to do a freeze on requisitions from the colleges. We would need to freeze processing of these within Purchasing Services.
FIN | Procurement | Freeze Date |  | Last Day to Add a Vendor (Supplier) | 1d | 2020-06-05 | 2020-06-05 |  | George Rhodes |  |  |  | GR: Freeze to support data conversion. May need to move back to provide team with enough time to extract, join, and convert vendor data.
FIN | Procurement | Freeze Date |  | Last Day to add contract to Cobblestone & Customers | 1d | 2020-06-05 | 2020-06-05 |  | George Rhodes |  |  |  | GR: New contracts as of 07/01/2020 will be create in Supplier Contracts or Customer Contracts.
FIN | Procurement | Freeze Date |  | Reconcile Transactions in PaymentNet. Transactions posted 6/15/2019 and after will be available in Workday Go Live. | 1d | 2020-06-15 | 2020-07-01 |  | George Rhodes | Departments |  |  | GR: We need to make sure we remove the ability to recon transactions in PaymentNet on this date.
FIN | Procurement | Freeze Date |  | Invoice Entry for FY2020 | 1d | 2020-06-23 | 2020-06-23 |  | George Rhodes |  |  |  | Depends on snapshot date for beginning balances; needs minimum 1 week before 6/30/20 for checks to get printed.
FIN | Procurement |  |  | Beginning Balance snapshot for Pcard/CTA/Travel/Fuel Cards | 1d | 2020-06-23 | 2020-06-23 |  | George Rhodes |  |  |  | GK: Need Milestones for Charges starting in March. Defaulting charges.
FIN | Procurement | Critical Date |  | Purchase Orders (No Freeze date) | 1d | 2020-06-30 | 2020-06-30 |  | George Rhodes |  |  |  | Tentative (needs review) - Open Purchase Orders can be loaded into Workday
FIN | Procurement | Critical Date |  | Receipts of Purchase Orders | 1d | 2020-06-30 | 2020-06-30 |  | George Rhodes |  |  |  | Cut off at same time as invoices ideally but realistically no blackout
FIN | Procurement |  |  | Reconcile Pcard/CTA/Travel/Fuel Cards | 1d | 2020-06-30 | 2020-06-30 |  | George Rhodes |  |  |  | GR: We need to make sure we remove the ability to recon transactions in PaymentNet on this date.
FIN | Procurement | Freeze Date |  | Last Pcard/CTA transaction load - Manually schedule | 1d | 2020-06-30 | 2020-06-30 |  | George Rhodes |  |  |  | GR: This should be caught in the same financial load as everything else starting 07/01/2020. Posts before 13th month - GK: These are uploaded via journal, we have to get them released in June.
FIN | Procurement |  |  | Unreconciled charges defaulted - 13th month | 1d | 2020-07-31 | 2020-07-31 | [5 empty] | GR: Do we need to default unreconciled charges or can we load them in Workday for Recon? - Default in 13th month
FIN | Expense | Freeze Date |  | Cash Advances for FY2020 | 1d | 2020-05-31 | 2020-05-31 | [5 empty] | GK: Need milestones for reconciliation. GR: Cash advances all need to be reconciled before EOB 06/30/2020
FIN | Expense |  |  | Cash Advances for FY2021 - entered into WD | 1d | 2020-07-01 | 2020-07-01 | [5 empty] | GK: Need milestones for reconciliation. GR: Cash advances all need to be reconciled before EOB 06/30/2020
FIN | Expense |  |  | FY2021 Expense will have to be re-entered into WD | 7d | 2020-07-01 | 2020-07-07 | [5 empty] | GR: We need to process the TEVs through reimbursement before EOB 06/30/2020. Any TEV after 06/15/2020 will be created in WD without spend authorization.
FIN | Travel |  |  | FY2021 Travel will have to be re-entered into WD | 7d | 2020-07-01 | 2020-07-07 | [5 empty] | GR: No freeze but entering TAs as the spend authorization in WD is preferred.
FIN | Grants | Freeze Date |  | Award Setups/Closures - (all elements in COA will be frozen in Jan) | 1d | 2020-05-29 | 2020-05-29 |  | Carrie Johnston/Christine Galbreath | Departments/SPS |  |  | Remove access to FACTS - Grants that termed before 6/30/2020 should be prioritized for closure to avoid converting to Workday. Awards terming 4/1/20 – 6/30/20 we assume will be converted if activity still needs to happen
FIN | Grants | Freeze Date |  | FACTS Updates/Changes | 1d | 2020-05-29 | 2020-05-29 |  | Carrie Johnston/Christine Galbreath
FIN | Grants | Freeze Date |  | New Vendors / Subrecipients | 1d | 2020-06-05 | 2020-06-05 |  | Carrie Johnston/Christine Galbreath
FIN | Grants | Freeze Date |  | Grant Invoicing/Billing | 1d | 2020-06-23 | 2020-06-23 |  | Carrie Johnston/Christine Galbreath | Departments/SPS
FIN | Grants | Freeze Date |  | Last day to enter Z sheets (invoice info) batch in receivables into PeopleSoft | 1d | 2020-06-24 | 2020-06-24 |  | Carrie Johnston/Christine Galbreath
FIN | Grants | Freeze Date |  | Last LOC Drawdown | 1d | 2020-06-24 | 2020-06-24 |  | Carrie Johnston/Christine Galbreath | SPS |  |  | Likely, draw for last payroll period (6/24/20) and freeze after that until after go-live.
FIN | Grants |  |  | ETR Transfers for Grants | 1d | 2020-06-30 | 2020-07-07 |  | Carrie Johnston/Christine Galbreath | Departments/SPS |  |  | Default to 13th month
FIN | Effort |  |  | Paper Effort Certification Period End 05/15/2020 |  | 2020-06-01 | 2020-07-10 |  | Carrie Johnston/Christine Galbreath | Departments/SPS
FIN | Effort |  |  | Last Paper Effort Certification Period End 06/30/2020 |  | 2020-07-10 | 2020-08-31 |  | Carrie Johnston/Christine Galbreath | Departments/SPS |  |  | The effort period ending 6/30 won’t be available until about 7/11, I think we’ll need to keep the legacy system open for only effort and allow the team to finish processing. Maybe we plan on shutting it down on 9/30/20.
FIN | Effort |  |  | Close legacy Effort system | 1d | 2020-08-31 | 2020-09-01 |  | Carrie Johnston/Christine Galbreath | Departments/SPS |  |  | The effort period ending 6/30 won’t be available until about 7/11, I think we’ll need to keep the legacy system open for only effort and allow the team to finish processing. Maybe we plan on shutting it down on 9/30/20.
FIN | Treasury |  |  | Last earnings distribution for FY2020 | 1d | 2020-06-17 | 2020-06-17 |  | Joan Wilmotte (or 06/15-16) |  |  |  | JW: Per Karen Kellerman, subject to change in June 2020
FIN | Endowment |  |  | Last day to buy in to an endowment for FY2020 | 1d | 2020-06-29 | 2020-06-30 |  | Joan Wilmotte |  |  |  | JW: Per Karen Kellerman, subject to change in June 2020
FIN | Endowment |  |  | Final upload from Access Database to Workday | 1d | 2020-07-20 | 2020-07-21 |  | Joan Wilmotte |  |  |  | JW: Preliminary estimated date
FIN | Endowment |  |  | Load Beginning statements into WD | 1d | 2020-07-27 | 2020-07-28 |  | Joan Wilmotte |  |  |  | JW: Per Karen Kellerman
FIN | Budget |  |  | FY2021 Allocations entered into WD | 1d | 2020-07-01 | 2020-07-02 |  | Chris Conway |  |  |  | CC: If we are doing our Planning outside of Workday the Area's should have that EIB ready to load. Otherwise, the central allocation will be made in Workday at launch and the Area's will have to adjust to Cost Center and Ledger.
FIN | Budget |  |  | Post Carryforward - Same as 13th month closing | 1d | 2020-07-17 | 2020-07-17 |  | Chris Conway (or 07/27-28) |  |  |  | CC: Gives 4 business days to validate the balances after FACTS has been closed
FIN | Assets | Freeze Date |  | Cut-off for pre-assigned inventory tag numbers | 1d | 2020-03-01 | 2020-03-01 |  | George Rhodes/Clint McGregor (or 01/02) |  |  |  | CPM: Preliminary estimated date
FIN | Assets | Freeze Date |  | Last date to add/delete/change an asset for FY2020 | 1d | 2020-06-01 | 2020-06-02 |  | George Rhodes/Clint McGregor |  |  |  | JW: Dependent on freeze of new assets via PO, AP, PCard for Object 6, 10 and Small & Attractive items. Will freeze be 6/1/20?
FIN | Assets | Soft Freeze |  | Final Fixed Assets upload from AIS and manual worksheets to Workday | 1d | 2020-06-05 | 2020-06-05 |  | George Rhodes/Clint McGregor (or 07/27) |  |  |  | This will need to align with the last conversion. All asset changes after last snapshot will need to be loaded using a catch-up load
FIN | Assets | Soft Freeze |  | Last day for asset creation, modification, and disposal | 1d | 2020-06-05 | 2020-06-05 |  | George Rhodes/Clint McGregor |  |  |  | This will need to align with the last conversion. All asset changes after last snapshot will need to be loaded using a catch-up load
FIN | Assets |  |  | FY2021 Assets entered into WD | 1d | 2020-07-01 | 2020-07-01 |  | George Rhodes/Clint McGregor (or 08/01)
FIN | Assets |  |  | Depreciation calculated and posted for FY2020 | 1d | 2020-07-24 | 2020-07-25 |  | George Rhodes/Clint McGregor |  |  |  | JW: Per Tami Bidle, normally occurs in August, but with freeze on asset changes after 6/1/20, will confirm if late July date is reasonable.
FIN | A/R | Freeze Date |  | Last day to add a Customer | 1d | 2020-06-05 | 2020-06-05 |  | George Rhodes/Clint McGregor |  |  |  | CPM: Date determined based on Internal Closing Schedule for FY2020
FIN | A/R | Freeze Date |  | Last day to issue an Invoice (or 06/23?) | 1d | 2020-06-26 | 2020-06-26 |  | George Rhodes/Clint McGregor |  |  |  | CPM: Date determined based on Internal Closing Schedule for FY2020
FIN | A/R | Freeze Date |  | Last day for Accounts Receivable Recordings and Adjustments | 1d | 2020-06-26 | 2020-06-26 |  | George Rhodes/Clint McGregor |  |  |  | CPM: Date determined based on Internal Closing Schedule for FY2020
FIN | A/R |  |  | Last day for receipts for goods or services sold by a department | 1d | 2020-06-30 | 2020-06-30 |  | George Rhodes/Clint McGregor |  |  |  | CPM: Date determined based on Internal Closing Schedule for FY2020
FIN | A/R | Post-Cutover |  | Revenue Transfer Requests | 1d | 2020-07-07 | 2020-07-08 |  | George Rhodes/Clint McGregor |  |  |  | CPM: Date determined based on Internal Closing Schedule for FY2020
FIN | A/R | Post-Cutover |  | Load ECSI Loans receivable balances | 1d | 2020-07-07 | 2020-07-08 |  | George Rhodes/Clint McGregor |  |  |  | CPM: Date based on expected day when ECSI will provide monthly reporting to WSU.
FIN | Billing | Post-Cutover |  | General Billing | 1d | 2020-07-07 | 2020-07-07 | [5 empty] | CPM: Date determined based on Internal Closing Schedule for FY2018
FIN | Billing | Post-Cutover |  | IRI's | 1d | 2020-07-07 | 2020-07-07 | [5 empty] | CPM: Date determined based on Internal Closing Schedule for FY2018
HCM | Core | Strategize |  | Determine what OPDRS security changes are needed post July 2020 (i.e. remove create new posting button to prevent new postings from being submitted). |  | 2020-01-06 | 2020-01-20 |  | HRS/OPDRS
HCM | Core | Strategize |  | Determine what OPDRS security changes are needed post November 2020 (i.e. view only access on recruiting). |  | 2020-01-06 | 2020-01-20 |  | HRS/OPDRS
HCM | Core | Strategize |  | Last day to enter hires into AIS |  | 2020-01-06 | 2020-01-20 |  | HRS/OPDRS
HCM | Benefits | Strategies |  | Strategize recruitment needs with departments. |  | 2020-01-06 | 2020-01-20 |  | HRS
HCM | Compensation | Configuration |  | MSI/Minimum Wage - update all existing AP/Faculty Grades (max values) by X% (data provided by WSU) |  | 2020-11-02 | 2020-11-19 |  | Joe Wagner/Shawn Ismail | Note: Gold will be available
HCM | Compensation | Configuration |  | MSI/Minimum Wage - Create/Update new classified grades, grade profiles and steps |  | 2020-11-02 | 2020-11-19 |  | Joe Wagner/Shawn Ismail | Note: Gold will be available
HCM | Compensation | Post-Cutover |  | PID - Launch PID integration in SBX tenant to ensure it works properly. |  | 2020-12-16 | 2020-12-16 |  | Joe Wagner/Shawn Ismail | Test in SBX
HCM | Compensation | Post-Cutover |  | PID - Identify the EE population > 11 days of LWOP (along with other criteria) and dock their Progression Start Date in WD by one month in order to exclude them from the PID integration. |  | 2020-12-16 | 2020-12-16 |  | Joe Wagner/Shawn Ismail | Test in SBX
HCM | Compensation | Post-Cutover |  | MSI/Minimum Wage - Prepare and run Request Compensation Change EIB to move all EEs to their correct post-MSI Grades, Grade Profiles, and Steps. |  | 2020-12-16 | 2020-12-16 |  | Joe Wagner/Shawn Ismail | Test in SBX
HCM | Compensation | Pre-Cutover |  | Last legacy PID Compenstion update |  | 2020-12-04 | 2020-12-04 |  | Jay Maylor | Jay will provide report
HCM | Compensation | Post-Cutover |  | PID - Update Compensation Step for the employees that progressed on 12/01 |  | 2020-12-16 | 2020-12-16 |  | Joe Wagner/Shawn Ismail
HCM | Benefits | Communication |  | Update Orientation Presentation Materials/Benefits Website for launch |  | 2020-04-01 | 2020-04-01 |  | Ann Monroe
HCM | Benefits |  |  | Summer Benefits Check 1 of 2 |  | 2020-05-10 | 2020-05-12 |  | Wendy Weber | Payroll
HCM | Benefits |  |  | Train Benefits on EIB templates for Catch-Up Transactions |  | 2020-05-04 | 2020-05-15 |  | Wendy Weber
HCM | Benefits | Critical Date |  | Request HCA Pay1 file for Gold Build be provided on 06/02/2020 |  | 2020-05-18 | 2020-05-19 |  | Wendy Weber
HCM | Benefits | Critical Date |  | Request DRS History File for Gold Build be provided on 6/2/2020 |  | 2020-05-18 | 2020-05-19 |  | Wendy Weber
HCM | Benefits |  |  | Summer Benefits Check 2 of 2 |  | 2020-05-25 | 2020-05-26 |  | Payroll/Benefits
HCM | Benefits | Conversion |  | Request updates and final review of DOD, Semester by Semester, 480/6/8, Seasonal, 2 year averaging, Court Ordered coverage lists from Benefits due by 6/5 |  | 2020-05-25 | 2020-05-29 |  | Wendy Weber
HCM | Benefits |  |  | Validate data between PayNat and HEPPS for sync pre-conversion file snapshot. (SEIB field) |  | 2020-05-25 | 2020-06-05 |  | Jay Maylor
HCM | Benefits |  |  | Validate data between Campus Community and HEPPS pre-conversion file snapshot. (Valid addresses, zipcodes) |  | 2020-05-25 | 2020-06-05 |  | Stacy Combs
HCM | Benefits |  |  | Identify cyclic, non-summer and no-B line individuals to verify assignments |  | 2020-06-01 | 2020-06-05 |  | Wendy Weber
HCM | Benefits | Configuration |  | Edit Tenant Setup - Disable Beneficiary, Emergency Contact and Dependent Linking (mark the box) |  | 2020-06-01 | 2020-06-05 |  | Wendy Weber
HCM | Benefits | Critical Date |  | Pull and hold DCP Inbound change files from ppd 6/10, 6/25, 7/10 |  | 2020-06-01 | 2020-07-11 |  | Wendy Weber
HCM | Benefits | Critical Date |  | Pull and hold VIP/VIP Roth inbound change files from ppd 6/10, 6/25, 7/10 |  | 2020-06-01 | 2020-07-11 |  | Wendy Weber
HCM | Benefits | Conversion |  | Build DRS Job Classification Flag File |  | 2020-06-08 | 2020-06-12 |  | Wendy Weber
HCM | Benefits | Conversion |  | Build Semester By Semester, 70/5/12, Min 8, Seasonal EIB Files (4) |  | 2020-06-08 | 2020-06-12 |  | Wendy Weber
HCM | Benefits |  |  | Pull and merge Date of Death File (S drive and HEPPS data) |  | 2020-06-08 | 2020-06-12 |  | Wendy Weber
HCM | Benefits |  |  | Start keying into EIB Templates for Catch Up Transactions |  | 2020-06-09 | 2020-07-06 |  | Ann Monroe
HCM | Benefits | Conversion |  | Identify Retirement, DCP and VIP enrollments that have been removed from HEPPS for limits and add to EIB Template for enrollment |  | 2020-06-15 | 2020-07-10 |  | Wendy Weber
HCM | Benefits | Conversion |  | Identify additional Benefits eligibility overrides and add to EIB (LWOP, multiple positions, federal employees, whitcom, fall-outs) |  | 2020-06-15 | 2020-06-19 |  | Wendy Weber
HCM | Benefits |  |  | Identify the Retirement Plan "B" (in enrollment window) and launch enrollments |  | 2020-06-29 | 2020-07-03 |  | Wendy Weber
HCM | Benefits |  |  | Update Workday for Court Ordered Coverage |  | 2020-06-29 | 2020-07-03 |  | Wendy Weber
HCM | Benefits |  |  | Update benefits packets to remove forms for enrollments captured in Workday |  | 2020-07-10 | 2020-07-11 |  | Wendy Weber
HCM | Benefits |  |  | Identify data items to fix for catch up loads and fix.. Including missing position terms, dates of birth. Also, temporarily adjust date of birth for age range changes that happen "in the window" for special handling. All dependents who are turning 26, need to be kept 25 through conversion and load and all employees on the edge of moving to 35, 45 or 50 (HSA) need to be kept their lower age until after conversion loads. |  | 2020-07-13 | 2020-07-14 |  | Wendy Weber
HCM | Benefits |  |  | Load EIB For Benefits Catchup/Fallout Transactions |  | 2020-07-13 | 2020-07-17 |  | Wendy Weber
HCM | Benefits |  |  | Enter CBFLE-Insurance and CBFLE-Additional fallouts-manually |  | 2020-07-13 | 2020-07-17 |  | Wendy Weber
HCM | Benefits |  |  | Catch Up for LTD Optional Payments for Hourly employees (behind one cycle currently) |  | 2020-07-13 | 2020-07-17 |  | Wendy Weber
HCM | Benefits | Critical Date |  | Load DCP inbound change files from ppd 6/10, 6/25, 7/10 and 7/25 |  | 2020-07-13 | 2020-07-17 |  | Wendy Weber
HCM | Benefits | Critical Date |  | Load VIP/VIP Roth inbound change files from ppd 6/10, 6/25, 7/10 and 7/25 |  | 2020-07-13 | 2020-07-17 |  | Wendy Weber
HCM | Benefits |  |  | Identify people in "Enrollment Window" and add to EIB to update their Retirement plans for "pre-choice" coded plans. |  | 2020-07-13 | 2020-07-17 |  | Wendy Weber
HCM | Benefits |  |  | Put dates of birth back for those adjusted for cutover (dependents aging out and retirement participants aging up and run events to correct with appropriate effective dates. ) |  | 2020-07-13 | 2020-07-17 |  | Wendy Weber
HCM | Benefits |  |  | Load updates for YTD on all benefits and check limits |  | 2020-07-17 | 2020-07-18 |  | Wendy Weber | Payroll
HCM | Time/Absence |  |  | Need to request Work Schedules - ask for predicted work schedules for launch so they are most accurate |  | 2020-10-01 | 2020-12-01 |  | Emily/Dora/Hally | Departments
HCM | Time/Absence |  |  | Need to collect those who will be on cyclic leave when we launch both from central and from AIS |  | 2020-10-01 | 2020-12-01 |  | Emily/Dora/Hally | Departments, Central HRS
HCM | Time/Absence |  |  | Need to identify those who are active but not on an appt for launch but will be starting their appt again soon so that we can make sure they are hired or terminated in the system |  | 2020-10-01 | 2020-12-01 |  | Emily/Dora/Hally | Departments, Central HRS
HCM | Time/Absence |  |  | Need to collect and load Annual, sick, personal holiday, military leave used, LWOP. Assure on one line per employee and not like on comp balances where there were multiple lines |  | 2020-10-01 | 2020-12-01 |  | Emily/Dora/Hally | Departments, Central HRS
HCM | Time/Absence |  |  | People who have requested and been approved for time off in the future - Employee Self Service |  | 2020-12-16 | 2020-12-31 |  | Emily/Dora/Hally | Departments, Central HRS
HCM | Core |  |  | Determine WHEN the Provost office will direct the departments to use the new Faculty Titles, and HOW they will direct them to use the NEW Titles and Tracks |  | 2020-01-01 | 2020-03-31 |  | Jim Lowery | Provost Office
HCM | Core |  |  | Supervisor Org, Structure, employee changes, unit name changes, CC, Fund, Function, Region - default orgs for Terminated, Retirees |  | 2020-05-18 | 2020-06-05 |  | Wendy Weber | Departments
HCM | Core |  |  | Academic Appt changes, tenure changes Chair/director changes |  | 2020-05-18 | 2020-06-17 |  | Jim Lowery | Provost Office
HCM | Core |  |  | Determine what are the high-frequency activities performed by the Records group that occur in August. |  | 2020-07-01 | 2020-07-13 |  | Jim Lowery | HR-Records and Admin
HCM | Recruiting |  |  | Work with JobElephant to test Workday external jobsite scraping. |  | 2019-12-09 | 2020-04-27 |  | Sabrina McPherson | HRS
HCM | Recruiting |  |  | Close OPDRS postings from job sites by 6/29/20. - open until filled |  | 2020-01-06 | 2020-06-29 |  | Sabrina McPherson | HRS
HCM | Recruiting |  |  | If security changes are needed, test changes in OPDRS sandbox site. |  | 2020-01-27 | 2020-05-25 |  | Sabrina McPherson | HRS
HCM | Recruiting |  |  | Communicate background check processing changes. |  | 2020-04-06 | 2020-07-13 |  | Sabrina McPherson | HRS
HCM | Recruiting | Critical date |  | Update website templates (i.e. offer letters). |  | 2020-03-02 | 2020-05-25 |  | Sabrina McPherson | HRS
HCM | Recruiting | Critical date |  | Update Jobs splash site. Incl. internal worker messaging. |  | 2020-04-06 | 2020-05-25 |  | Sabrina McPherson | HRS
HCM | Recruiting | Critical date |  | Update HRS Recruitment Toolkit. |  | 2020-04-06 | 2020-05-25 |  | Sabrina McPherson | HRS
HCM | Recruiting | Communication |  | Post transition announcement to OPDRS users on internal OPDRS site. |  | 2020-05-04 | 2020-07-13 |  | Sabrina McPherson | OPDRS Admin
HCM | Recruiting | Communication |  | Post transition announcement to candidates on external WSUJobs site. Incl. internal worker messaging. |  | 2020-05-18 | 2020-07-13 |  | Sabrina McPherson | OPDRS Admin
HCM | Recruiting | Communication |  | Communicate with internal workers on new way to apply for jobs. |  | 2020-05-18 | 2020-07-13 |  | Sabrina McPherson | HRS
HCM | Recruiting | Freeze Date |  | Freeze on Requisitions 6/3 |  | 2020-06-03 | 2020-07-01 |  | Sabrina McPherson |  |  |  | Central Office (with input from Mod Project)
HCM | Recruiting | Freeze Date |  | Prevent departments from creating new recruitments by security change or denying new postings. |  | 2020-06-22 | 2020-06-22 |  | Sabrina McPherson | OPDRS Admin
HCM | Recruiting | Communication |  | Communicate with internal workers on new way to apply for jobs. |  | 2020-05-18 | 2020-07-13 |  | Sabrina McPherson | HRS
HCM | Recruiting | Communication |  | Communicate with candidates of canceled recruitment efforts to reapply in Workday. |  | 06/292020 | 06/292020 |  | Sabrina McPherson | Departments
HCM | Recruiting |  |  | Manually enter Hire in Workday after recruitment effort is complete in OPDRS. |  | 06/292020 | 06/292020 |  | Sabrina McPherson | Departments?
HCM | Recruiting |  |  | JobElephant no longer scrapes job postings from OPDRS as of 6/30/20 |  | 2020-06-30 | 2020-06-30 |  | Sabrina McPherson
HCM | Recruiting |  |  | JobElephant scrapes job postings from Workday as of 7/1/20. |  | 2020-07-01 | 2020-07-01 |  | Sabrina McPherson
HCM | Recruiting |  |  | New recruitment efforts are conducted in Workday as of 7/1/20. |  | 2020-07-01 | 2020-07-01 |  | Sabrina McPherson
HCM | Recruiting |  |  | Complete (fill or cancel) recruitment efforts within OPDRS by 10/31/20. |  | 2020-10-26 | 2020-10-26 |  | Sabrina McPherson | Departments / HRS
FIN | Payroll | Communication |  | Get Cost Share obligation and PCA information |  | 2020-01-15 | 2020-04-01 |  | Brigham Hubbard | Departments, Position Control, Central Payroll |  |  | Must have communication by first half of May for department
FIN | Payroll | Communication |  | PFML, Unemployment - Communication concerning the differences out of state workers will see (Still needed?) |  |  |  |  | Brigham Hubbard | Departments, Position Control, Central Payroll |  |  | Must have communication by first half of May for department
FIN | Payroll | Communication |  | Costing Allocations > 07/01/2020 will NOT be converted |  |  |  |  | Brigham Hubbard | Departments, Position Control, Central Payroll |  |  | Must have communication by first half of May for department
FIN | Payroll | Pre-Cutover |  | Determine what Payroll Cutoff Activities (currently performed by the Records group) that will be impacted. | 1d | 2020-04-13 | 2020-04-14 |  | Brigham Hubbard | HR-Records and Admin
FIN | Payroll | Communication |  | Comp Time Payout Communication | 1d | 2020-05-15 | 2020-05-15 |  | Brigham Hubbard |  |  |  | Must have communication by first half of May for department
FIN | Payroll | Freeze Date |  | Last HEPPS update in Legacy will be June 26, 2020, any accounting adjustments need to be in to position control/payroll before this date | 20d | 2020-05-28 | 2020-06-30 |  | Brigham Hubbard |  |  |  | BH: This will need to align with the last conversion. If requests are for current FY, give them just enough time to enter before the snapshot. If for future FY, not allowed
FIN | Payroll | Pre-Cutover |  | Comp Time Payout | 1d | 2020-05-31 | 2020-05-31 |  | Brigham Hubbard |  |  |  | BH: Kendra talking with BU reps to finalize plan. When departments would have to communicate that they want to pay out comp time (end of May).
FIN | Payroll | Duplicate |  | Any comp time earned needs to be used or cashed out before May 28th 2020. Any new comp time earned after this date needs to be used or cashed out before June 26th 2020. Any comp time not used or cashed out will have to be manually handled as we are not planning on converting comp time. | 1d | 2020-05-28 | 2020-06-26 |  | Brigham Hubbard |  |  |  | BH: Kendra talking with BU reps to finalize plan. When departments would have to communicate that they want to pay out comp time (end of May).
FIN | Payroll | Pre-Cutover |  | Payroll Compare on Gold | 1d |  |  |  | Brigham Hubbard
FIN | Payroll | Critical Date |  | Last WSU legacy payroll - Pay date July 10 | 1d | 2020-07-02 | 2020-07-02 |  | Brigham Hubbard |  |  |  | BH:second half of June 2020 which would be the July 10th paycheck.
FIN |  | Freeze Date |  | Last day to enter time (DAR and positive pay) |  | 2020-06-29 | 2020-07-02 |  | Brigham Hubbard
FIN | Payroll | Freeze Date |  | Payroll Costing Allocations - Need to check with HR | 20d | 2020-06-06 | 2020-07-01 |  | Brigham Hubbard |  |  |  | BH: This will need to align with the last conversion. If requests are for current FY, give them just enough time to enter before the snapshot. If for future FY, not allowed
FIN | Payroll |  |  | Position control must have all changes entered into the system |  |  |  |  | Brigham Hubbard
FIN | Payroll |  |  | Retro payroll costing allocation changes entered into the system |  |  |  |  | Brigham Hubbard |  |  |  | If only for retro the June 26 date needs to be by payroll. (23rd HR, … etc. Need details)
FIN | Payroll | Soft Freeze |  | Change elective deductions | 20d | 2020-06-06 | 2020-06-26 |  | Brigham Hubbard |  |  |  | BH: This will need to align with the last conversion. All elective deductions after last snapshot will need to be loaded using a catch-up load
FIN | Payroll | Freeze Date |  | Last day to change elective deductions | 1d | 2020-06-26 | 2020-06-26 |  | Brigham Hubbard |  |  |  | BH: Manual entry into WD
FIN | Payroll |  |  | Tracking of deductions that need to be manually entered into Workday |  |  |  |  | Brigham Hubbard |  |  |  | BH: Effort needs to be input into AIS before the last snapshot
FIN | Payroll | Freeze Date |  | Last day to change effort distribution | 1d | 2020-06-05 | 2020-06-05 |  | Brigham Hubbard |  |  |  | BH: Effort needs to be input into AIS before the last snapshot
FIN | Payroll |  |  | Garnishments/levies - Manual Process | 1d | 2020-06-30 | 2020-06-30 |  | Brigham Hubbard |  |  |  | BH: No conversion of data because it does not exist in AIS. This will be a manual entry into Workday. No freeze date
FIN | Payroll | Critical Date |  | First WSU Payroll - Pay date July 24 (Friday) | 1d | 2020-07-21 | 2020-07-21 |  | Brigham Hubbard |  |  |  | Payroll complete 3 business days before payday
FIN | Payroll | Post-Cutover |  | Payroll Compare - Last legacy vs. first Workday payroll | 2d | 2020-07-06 | 2020-07-07 |  | Brigham Hubbard
TECH | Data Conversion | Critical Date |  | HCM/Finance Crosswalks Finalized |  | 2020-06-01 | 2020-06-01
TECH | Data Conversion | Critical Date |  | Change to setups for conversion |  | 2020-06-01 | 2020-06-01
TECH | Data Conversion | Critical Date |  | Conversion Activities |  | 2020-06-06 | 2020-07-05
TECH | Data Conversion |  |  | Snapshot #1 of Payroll, HCM and Finance data | 1 day | 2020-06-06 | 2020-06-06 |  | WSU Conversion team |  |  |  | Snapshot taken after Payroll has completed
TECH | Data Conversion |  |  | Build Conversion Warehouse | 1 day | 2020-06-07 | 2020-06-08 |  | WSU Conversion team
TECH | Data Conversion |  |  | Extracts Completed | 1 day | 2020-06-09 | 2020-06-09 |  | WSU Conversion team
TECH | Data Conversion |  |  | Validate Payroll, HCM and Finance extracts | 1 day | 2020-06-10 | 2020-06-11 |  | WSU Functional Leads
TECH | Data Conversion |  |  | Load Payroll, HCM and Finance data | 7 days | 2020-06-12 | 2020-06-19 |  | WSU/Deloitte Conversion team
TECH | Data Conversion |  |  | Supplemental Loads | 3 days | 2020-06-20 | 2020-06-22 |  | WSU/Deloitte Conversion team
TECH | Data Conversion | Critical Date |  | Snapshot #2 of Payroll, HCM and Finance data | 1 day | 2020-06-20 | 2020-06-20 |  | WSU Conversion team |  |  |  | Snapshot taken after Payroll has completed
TECH | Data Conversion | Critical Date |  | Catch-Up Loads -HCM and Finance | 1 day | 2020-06-22 | 2020-07-05 |  | WSU/Deloitte Conversion team |  |  |  | Snapshot taken after Payroll has completed
TECH | Data Conversion |  |  | Applicant/Hires |  |  |  |  | WSU/Deloitte Conversion team |  |  |  | Snapshot taken after Payroll has completed
TECH | Data Conversion |  |  | Add List HERE |  |  |  |  | WSU/Deloitte Conversion team |  |  |  | Snapshot taken after Payroll has completed
TECH | Data Conversion/UAT |  |  | UAT Conversion Prep
TECH | Data Conversion/UAT
TECH | Data Conversion/UAT
TECH | Data Conversion/UAT
TECH | Data Conversion/UAT |  |  | Payroll Processing Completes
TECH | Data Conversion/UAT |  |  | Run Dumpy
TECH | Data Conversion/UAT |  |  | UAT Data Warehouse build - static?
TECH | Data Conversion/UAT |  |  | Create UAT Extracts
TECH | Data Conversion/UAT |  |  | Run FDM Validation report
TECH | Data Conversion/UAT |  |  | Correction of Configuration data - HCM
TECH | Data Conversion/UAT |  |  | Correction of Configuration data - Finance
TECH | Data Conversion/UAT |  |  | Ken
TECH | Data Conversion/UAT |  |  | Christine
TECH | Data Conversion/UAT |  |  | Wendy
TECH | Data Conversion/UAT |  |  | Validation of Locations
TECH | Data Conversion/UAT |  |  | Validation of Supervisory Organizations
TECH | Data Conversion/UAT |  |  | Provide security to UAT tenant prior to hire for specific validators
TECH | Data Conversion/UAT |  |  | Hire
TECH | Data Conversion/UAT |  |  | Provide security to UAT tenant for validators
TECH | Data Conversion/UAT
TECH | Data Conversion/UAT
TECH | Data Conversion/UAT
TECH | Integrations |  |  | Vendor/Application owner communications |  | 2020-05-18 | 2020-05-25 |  | Integration Leads
TECH | Integrations |  |  | Confirm Integration and Reporting objects in Object Master tenant that need to be transferred to Gold tenant |  | 2020-05-18 | 2020-05-25 |  | Integration Leads
TECH | Integrations |  |  | Confirm Connectivity and Scheduling details |  | 2020-05-18 | 2020-05-25 |  | Integration Developers
TECH | Integrations |  |  | Submit final test checks to Bank for MICR testing |  | 2020-05-25 | 2020-06-01 |  | Integration Developers | Payroll
TECH | Integrations |  |  | Finalize first run strategy and launch parameters for integrations |  | 2020-06-01 | 2020-06-08 |  | Integration Developers
TECH | Integrations |  |  | Turn-off deprecated integrations in legacy systems |  | 2020-06-01 | 2020-06-08 |  | Integration Developers
TECH | Integrations |  |  | Update Production FTP/web service credentials in LastPass (or other repository) |  | 2020-06-08 | 2020-06-15 |  | Integration Leads
TECH | Integrations |  |  | Confirm Vendors ready for go live |  | 2020-06-08 | 2020-06-15 |  | Integration Leads
TECH | Integrations |  |  | Confirm all "Last Integration Run Date Times" in legacy system |  | 2020-06-08 | 2020-06-15 |  | Integration Leads
TECH | Integrations |  |  | Confirm notification configuration in production |  | 2020-06-15 | 2020-06-22 |  | Integration Leads
TECH | Integrations |  |  | Move Integrations and Reports to Gold and confirm all ISU's are attached to the respective reports and integrations |  | 2020-06-15 | 2020-06-22 |  | Integration Developers
TECH | Integrations |  |  | Confirm all integration run schedules have been completed / signed off for all integrations |  | 2020-06-15 | 2020-06-22 |  | Integration Leads
TECH | Integrations |  |  | Configure Transport Protocol environment restrictions |  | 2020-06-15 | 2020-06-22 |  | Integration Developers
TECH | Integrations |  |  | Validate report sharing permissions |  | 2020-06-15 | 2020-06-29 |  | Integration Developers
TECH | Integrations |  |  | Validate integration migrations and confirm connectivity |  | 2020-06-15 | 2020-06-29 |  | Integration Developers
TECH | Integrations |  |  | Validate BP triggered integrations |  | 2020-06-15 | 2020-06-29 |  | Integration Developers
TECH | Integrations |  |  | Validate all integration object exceptions by running Audit reports. |  | 2020-06-15 | 2020-06-29 |  | Integration Developers
TECH | Integrations |  |  | Set up "first run" and ongoing schedules |  | 2020-06-15 | 2020-06-29 |  | Integration Developers
TECH | Integrations |  |  | Integration Configuration (E.g. Attributes, Maps, Filters, Overrides, Prompts) Peer Review |  | 2020-06-15 | 2020-06-29 |  | Integration Developers
TECH | Integrations |  |  | Establish Production passwords where needed between systems |  | 2020-06-15 | 2020-06-29 |  | Integration Developers
TECH | Integrations |  |  | Create Integration Segments/Segment Security Groups |  | 2020-06-15 | 2020-06-29 |  | Integration Developers
TECH | Integrations |  |  | Clone Core Connector Integrations for Ad-Hoc Instances |  | 2020-06-15 | 2020-06-29 |  | Integration Developers
TECH | Integrations |  |  | Confirm integration scheduled process ownership |  | 2020-06-22 | 2020-06-29 |  | Integration Developers
TECH | Integrations |  |  | Confirm if the output file names are updated in the sequence generators as expected for PROD |  | 2020-06-22 | 2020-06-29 |  | Integration Developers
TECH | Integrations |  |  | Confirm if required ISUs are added to the Password exempt authentication policy |  | 2020-06-22 | 2020-06-29 |  | Integration Developers
TECH | Integrations |  |  | Confirm all vendors, external, or internal systems using IP filtering for file exchange purposes have been provided production IP addresses |  | 2020-06-22 | 2020-06-29 |  | Integration Leads
TECH | Integrations |  |  | Confirm all SFTP sites established and tested for file exchanges / signed off |  | 2020-06-22 | 2020-06-29 |  | Integration Leads
TECH | Integrations |  |  | Confirm all ISSG and ISU's are migrated to Gold |  | 2020-06-22 | 2020-06-29 |  | Integration Leads
TECH | Integrations |  |  | Switch OMS Restriction on Notification Condition Rule |  | 2020-06-22 | 2020-06-29 |  | Integration Leads
TECH | Integrations |  |  | GOLD moves to PRODUCTION - Announce Copy of Prod available for smoke testing |  | 2020-06-22 | 2020-06-29 |  | Integration Leads
TECH | Integrations |  |  | Load Catch Up Runs for applicable integration (BAI2 files, inbound benefits etc.) |  | 2020-06-29 | 2020-07-06 |  | Integration Developers
TECH | Integrations |  |  | Monitor integration runs and fix any issues |  | 2020-06-29 | 2020-07-06 |  | Integration Developers
TECH | Security |  |  | Configure SSO in Production |  | 2020-06-22 | 2020-06-29 |  | Security Leads
PMO | PMO |  |  | Tasks Initiating Week of May 11
HCM | HCM |  |  | Pre-Validation Process Planning
HCM | HCM |  |  | Pre-Validation Timeline Comms
PMO | PMO |  |  | Tasks Initiating Week of May 18
TECH | Conversion | Critical Date |  | Create Summer Job Extract for PAP conversion |  | 2020-05-18 | 2020-05-18
| Steering Committee |  |  | Review Draft Go No-Go Criteria
PMO | PMO |  |  | Tasks Initiating Week of May 25
PMO | All |  |  | Memorial Day - holiday |  | 2020-05-25 | 2020-05-25
| Steering Committee |  |  | Review and Finalize Go No-Go Criteria
PMO | PMO |  |  | Tasks Initiating Week of June 1
TECH | Integrations |  |  | Submit final test checks to Bank for MICR testing
PMO | PMO |  |  | Tasks Initiating Week of June 8
PMO | PMO |  |  | Tasks Initiating Week of June 15
PMO | PMO |  |  | Tasks Initiating Week of June 22
PMO | PMO |  |  | Tasks Initiating Week of June 29
TECH | Tenant Management |  |  | Turn on email notifications & disable email redirect |  | 2020-07-01 | 2020-07-01
PMO | All |  |  | July 4 - holiday |  | 2020-07-03 | 2020-07-03
PMO | PMO |  |  | Tasks Initiating Week of July 6
PMO | PMO |  |  | Tasks Initiating Week of July 13
PMO | PMO |  |  | Tasks Initiating Week of July 20
PMO | PMO |  |  | Tasks Initiating Week of July 27
OCM | Change |  |  | Launch Guides for Managers and Employees developed
OCM | Change |  |  | Desk drop for all staff developed
HCM | Compensation | Manual |  | Update the Default Comp for AP/Faculty and Hourly Positions |  | 2020-12-16 | 2020-12-16 |  | Joe Wagner/Shawn Ismail
|  |  |  | INT166 - Digital Measures - Appointment - Outbound |  |  |  |  | Joe Wagner
HCM | Compensation |  |  | INT169 - Workday - PID Salary Progression - Boomerang |  |  |  |  | Joe Wagner |  |  |  | Report PER856 report can be used to assign the appropriate step to the worker from the 12/01 PID process
|  |  |  | INT173 - IPED - HRS |  |  |  |  | Joe Wagner
TECH | Data Cleansing |  |  | Maintain Contract Addresses (Zip Code) - Data cleansing in myWSU |  | 2020-05-01 | 2020-06-01

## B. HCM_VCC (hidden)
Task # | Section | Grouping | Function | Wave | Workstream | Target System | Open Questions | Task Description | Sublist Tab Name | Need EIB? | Start Date | Start Time | End Date | Assigned to (Name(s)) | Status | Final Comments / Notes | Send Communication | Identify Process to Capture Transaction outside of Legacy System - START | Identify and Communicate Interim Process to Complete in Interim (Legacy) - STOP | Identify Process to Hold and Subsequently Complete Transaction (Workday) - CATCH-UP
1530 | 4. Post-Cutover | Catch-Up Activity | HCM |  | Organization | Workday |  | Cleanup of academic unit hierarchy |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
1535 | 4. Post-Cutover | Catch-Up Activity | HCM |  | Organization |  |  | Cleanup of supervisory organization |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
1710 | 4. Post-Cutover | Catch-Up Activity | HCM |  | Benefits | Workday |  | For people with multiple jobs, ensure the primary job is the benefits job. If it's not, use the "Switch Primary Job" BP to make the benefits job primary |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
1750 | 4. Post-Cutover | Catch-Up Activity | HCM |  | Recruiting | Workday |  | For Job Requisitions Approved and not posted in Legacy System, Create Job Requisitions in Workday |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
1760 | 4. Post-Cutover | Catch-Up Activity | HCM |  | Payroll / Time / Absence | Workday |  | Update FMLA/LOA status for indiviuals in those statuses because this status is not being converted |  | Y | 2020-06-29 |  | 2020-07-06 | Institutions
1770 | 4. Post-Cutover | Catch-Up Activity | HCM |  | Compensation | Workday |  | Enter Period Activity Pay (paments that are outstanding) |  | Y | 2020-06-29 |  | 2020-07-06 | Institutions
1771 |  |  | HCM |  | Compensation | Workday |  | Enter comp changes (after 5/31) |  | Y | 2020-06-29 |  | 2020-07-06 | Institutions
1780 | 4. Post-Cutover | Catch-Up Activity | HCM |  | All | Workday |  | Enter any HR transactions (Benefits updates, hires, terms, corrections, addition of CW's, comp updates, LWOP, custom ID updates, ACA passive events, medicare eligibile date adjustments) / Enter any W4 Election changes since freeze in to WD; payment elections, withholding orders, taxes |  | Y | 2020-06-29 |  | 2020-07-06 | Institutions
1790 | 4. Post-Cutover | Catch-Up Activity | HCM |  | Payroll / Time / Absence | Legacy |  | Enter the absence balances from freeze period |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
1730 | 4. Post-Cutover | Soft Launch Tasks | HCM |  | All | Workday |  | Correct data conversion errors |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
1810 | 4. Post-Cutover | Gold Build | HCM |  | All | Workday |  | Change Licenses, passports and visas, contracts, one-time payments, payroll inputs |  | Y | 2020-06-29 |  | 2020-07-06 | Institutions
1811 |  |  | HCM |  | All | Workday |  | Process future one-time payments (crossing the year or ones that were held by the institutions) |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
1812 |  |  | HCM |  | All | Workday |  | Process future payroll inputs |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
1815 |  |  | HCM |  | All | Workday |  | Add secondary job(s) to individuals if only one job was converted for your institution |  |  | 2020-06-29 |  | 2020-07-06 | Institutions

## C. HCM_ER (hidden)
Task # | Section | Grouping | Function | Wave | Workstream | Target System | Open Questions | Task Description | Sublist Tab Name | Need EIB? | Start Date | Start Time | End Date | Assigned to (Name(s)) | Status | Final Comments / Notes
4. Post-Cutover | Employee Review |  | HCM |  | Payroll / Time / Absence | Workday |  | Enter any leave of absence requests whose approval process did not complete by 5/31/20 |  |  | 2020-07-07 |  | 2020-07-21 | Institutions |  | Follow up w/SLP to determine date for this item
4. Post-Cutover | Employee Review |  | HCM |  | Payroll / Time / Absence | Workday |  | Enter any time off requests whose approval process did not complete by 5/31/20 |  |  | 2020-07-07 |  | 2020-07-21 | Institutions |  | (Employee As Self) Follow up w/SLP to determine date for this item
4. Post-Cutover | Employee Review |  | HCM |  | Core HR | Workday |  | Review & Correct Data for Direct Deposit & Benefits Deductions |  |  | 2020-07-07 |  | 2020-07-21 | Institutions |  | (Employee As Self)
4. Post-Cutover | Employee Review |  | HCM |  | Core HR | Workday |  | Review Additional Data Student Status. Let Academic HR Lead if data is incorrect. |  |  | 2020-07-07 |  | 2020-07-21 | Institutions |  | (Employee As Self)
4. Post-Cutover | Employee Review |  | HCM |  | Benefits | Workday |  | Review Benefits Plan Enrollment and coverages. Let Benefits Partner if data is incorrect. |  |  | 2020-07-07 |  | 2020-07-21 | Institutions |  | (Employee As Self)
4. Post-Cutover | Employee Review |  | HCM |  | Benefits | Workday |  | Review Benefits Service date and Vesting dates. Let Benefits Partner know if data is incorrect. |  |  | 2020-07-07 |  | 2020-07-21 | Institutions |  | (Employee As Self)
4. Post-Cutover | Employee Review |  | HCM |  | Compensation | Workday |  | Review Compensation, Annual Salary and Period Activity Pay Assignments. Let Manager and Compensation Partner know if data is incorrect. |  |  | 2020-07-07 |  | 2020-07-21 | Institutions |  | (Employee As Self)
4. Post-Cutover | Employee Review |  | HCM |  | Core HR | Workday |  | Review Contact Information, Emergency Contact Info & Dependent information. Correct data in ESS if incorrect. |  |  | 2020-07-07 |  | 2020-07-21 | Institutions |  | (Employee As Self)
4. Post-Cutover | Employee Review |  | HCM |  | Core HR | Workday |  | if you're a Manager, Review Direct Reports. Let HR Partner and Security Partner know if it is incorrect. |  |  | 2020-07-07 |  | 2020-07-21 | Institutions |  | (Manager as Self)
4. Post-Cutover | Employee Review |  | HCM |  | Payroll | Workday |  | Review federal and state income tax information. Update information in ESS if it is incorrect. |  |  | 2020-07-07 |  | 2020-07-21 | Institutions |  | (Employee As Self)
4. Post-Cutover | Employee Review |  | HCM |  | Core HR | Workday |  | As an employee, Review Manager Relationship. Let Manager and HR Partner know if it's incorrect. |  |  | 2020-07-07 |  | 2020-07-21 | Institutions |  | (Employee As Self)
4. Post-Cutover | Employee Review |  | HCM |  | Core HR | Workday |  | Review Personal Information. Correct in ESS if it is incorrect. |  |  | 2020-07-07 |  | 2020-07-21 | Institutions |  | (Employee As Self)
4. Post-Cutover | Employee Review |  | HCM |  | Payroll / Time / Absence | Workday |  | Review Time Off Balances. If it is incorrect, let Manager and Absence Partner know. |  |  | 2020-07-07 |  | 2020-07-21 | Institutions |  | (Employee As Self)
4. Post-Cutover | Employee Review |  | HCM |  | Core HR | Workday |  | Upload Photo of Yourself in ESS. |  |  | 2020-07-07 |  | 2020-07-21 | Institutions |  | (Employee As Self)
2300 | 4. Post-Cutover |  | HCM |  | Core HR | Workday |  | For employees that hold a security role, Review & Validate Supporting Organizations (use My Supporting Organizations report). If it is incorrect, let Security Partner know. |  |  | 2020-07-07 |  | 2020-07-22 | Institutions |  | (Manager as Self)

## D. FIN_VCC (hidden)
Task # | Section | Function | Wave | Workstream | Target System | Open Questions | Task Description | Sublist Tab Name | Need EIB? | Start Date | Start Time | End Date | Assigned to (Name(s)) | Status | Final Comments / Notes
1520 | 4. Post-Cutover | FIN |  | Assets | Workday |  | Insert Catchup Asset Changes or Disposals on Converted Assets for FY20-21 |  |  | 2020-06-29 |  | 2020-07-06 | Institutions |  | Enter Asset Changes or Disposals (UI)
1820 | 4. Post-Cutover | FIN |  | Assets | Workday |  | Insert Catch-Up Transactions for Asset Additions for FY20-21 |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
1830 | 4. Post-Cutover | FIN |  | Amend Awards | Workday |  | Insert Catch-Up Transactions for Awards |  |  | 2020-06-29 |  | 2020-07-06 | Institutions |  | Add /Update / Amend Awards & Award Budgets - 6/1 (EIB)
1840 | 4. Post-Cutover | FIN |  | Credit Card | Workday |  | Insert Catch-Up Transactions for Credit Card Charges |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
1850 | 4. Post-Cutover | FIN |  | Customer | Workday |  | Insert Catch-Up Transactions for Customer Unapplied Payments |  |  | 2020-06-29 |  | 2020-07-06 | Institutions |  | Load Unapplied Payments (EIB)
1860 | 4. Post-Cutover | FIN |  | Travel | Workday |  | Insert Catch-Up Transactions for Expense Reports |  |  | 2020-06-29 |  | 2020-07-06 | Institutions |  | Load Open Expense Reports (EIB)
1870 | 4. Post-Cutover | FIN |  | Sponsor Award |  |  | Insert Catch-Up Transactions for New Award Information |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
1880 | 4. Post-Cutover | FIN |  | Customer | Workday |  | Insert Catch-Up Transactions for New or Update Customer Information |  |  | 2020-06-29 |  | 2020-07-06 | Institutions |  | Load New / Updates to Customers - 6/1 (EIB)
1890 | 4. Post-Cutover | FIN |  | Sponsor Award | Workday |  | Insert Catch-Up Transactions for New or Update Sponsor Information |  |  | 2020-06-29 |  | 2020-07-06 | Institutions |  | Load New / Updates to Sponsors - 6/1 (EIB)
1900 | 4. Post-Cutover | FIN |  | Supplier | Workday |  | Insert Catch-Up Transactions for New or Update Supplier Information |  |  | 2020-06-29 |  | 2020-07-06 | Institutions |  | Load New / Updates to Suppliers - 6/1 (EIB)
1910 | 4. Post-Cutover | FIN |  | Procurement | Workday |  | Insert Catch-Up Transactions for PO Change Orders |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
1920 | 4. Post-Cutover | FIN |  | Procurement | Workday |  | Insert Catch-Up Transactions for Purchase Orders |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
1930 | 4. Post-Cutover | FIN |  | Travel | Workday |  | Insert Catch-Up Transactions for Spend Authorizations (Cash Advance) |  |  | 2020-06-29 |  | 2020-07-06 | Institutions |  | Load Open Spend Authorizations (EIB)
1940 | 4. Post-Cutover | FIN |  | Sponsor Award | Workday |  | Insert Catch-Up Transactions for Sponsor Invoices |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
1970 | 4. Post-Cutover | FIN |  | Budgets | Workday |  | Insert Transactions for Financial Budgets Changes (Amendments or Changes to the Budgets that were loaded) |  |  | 2020-06-29 |  | 2020-07-06 | Institutions |  | Load New Financial Budgets (EIB??) and (Hoover)
2080 | 4. Post-Cutover | FIN |  | Budgets |  |  | Insert Catch-Up Transactions for Project Budgets |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
2090 | 4. Post-Cutover | FIN |  | Budgets |  |  | Insert Catch-Up Transactions for Award Budgets |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
2100 | 4. Post-Cutover | FIN |  | Budgets |  |  | Insert Catch-Up Transactions for Position Budgets |  |  | 2020-06-29 |  | 2020-07-06 | Institutions
2210 | 4. Post-Cutover | FIN |  | Customer Invoices | Workday |  | Insert Catch-Up Transactions for Customer Invoices |  |  | 2020-07-05 |  | 2020-07-06 | Institutions |  | Load Open Customer Invoices (EIB)
Note on P20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependent upon closing AR in legacy.